## East Inbound (NJ,VA, SC)
WH | PO# | VESSEL | MBL# | HBL # | CONT# | Model | Item Code | Tariff (%) | PCS | PLT | ETD | ETA/ATA | Updated ETA | WH ETA | DO received | Discharging Date | Discharging lead time | LFD | Outgated | Pickup lead time | Unloaded date | Delivery lead time | Current status/drayage plan | Remark
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | MSKU8048304 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | CZZU0453945 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | MAGU5198655 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | HASU5031823 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | MRKU2558016 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | MAEU8375377 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | TGHU9439706 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | HASU4516100 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GUNHILDE MAERSK | SUDUN8SOL0144721 | SHTC18100247 | MRKU2167840 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-07 |  |  | 2018-12-06 |  | DELIVERED (PSS) | PSS
PSS | 71800098 | GUNHILDE MAERSK | SUDUN8SOL0149891 | SHTC18100248 | MSKU8238156 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800098 | GUNHILDE MAERSK | SUDUN8SOL0149891 | SHTC18100248 | SUDU6800273 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800098 | GUNHILDE MAERSK | SUDUN8SOL0149891 | SHTC18100248 | PONU8037948 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | CLOSED IN CELLO ON 12/05 (PSS) | PSS
PSS | 71800098 | GUNHILDE MAERSK | SUDUN8SOL0149891 | SHTC18100248 | MSKU0791627 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-07 |  |  | 2018-12-07 |  | DELIVERED (PSS) | PSS
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8934349 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8789256 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8797204 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | BSIU9112190 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | AXIU1356857 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8730324 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | XINU8212352 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8431576 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8800015 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | FCIU8688646 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8576482 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8251609 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | BSIU9540286 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8973197 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL768256 | SHTC18110044 | ZCSU8606015 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8741571 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8569333 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCNU8395216 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | BMOU4760030 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | UESU5210435 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | CRSU9079168 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU7014198 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8465663 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8642687 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TEMU6802544 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8553830 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCNU4398650 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TGBU5776271 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8828141 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCNU4257055 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | FJKU6011002 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | GVCU5325602 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8945831 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | BSIU9614922 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | BSIU9587690 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | FCIU8912674 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU6501606 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TLLU5305354 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8818518 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCKU6020406 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCLU6622838 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TGBU5763356 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCNU8897533 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TCNU8778869 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | TEMU6770318 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU7121370 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8877763 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | GAOU6089721 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8740214 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | ZIMUSEL766804 | SHTC18100249 | ZCSU8598619 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800120 | GUNHILDE MAERSK | SUDUN8SOL0157311 | SHTC18110042 | TGHU8385924 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED OUT IN CELLO ON 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800120 | GUNHILDE MAERSK | SUDUN8SOL0157311 | SHTC18110042 | CRXU9143870 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-07 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800120 | GUNHILDE MAERSK | SUDUN8SOL0157311 | SHTC18110042 | PONU7671773 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800120 | GUNHILDE MAERSK | SUDUN8SOL0157311 | SHTC18110042 | MRKU3449534 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800120 | GUNHILDE MAERSK | SUDUN8SOL0157311 | SHTC18110042 | MRKU5343562 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-28 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | PONU7301341 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MSKU1769470 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU5765629 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU2842315 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRSU3881710 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MSKU8696837 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU2969505 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU3582207 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU5895936 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-01 |  | PAPERWORK RCVD AND CLOSED IN CELLO 12/4 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRSU3347561 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU5927503 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU3416504 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800102 | GUNHILDE MAERSK | MAEU966858310 | SHTC18110058 | MRKU4600060 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU1936140 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU9071947 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | FCIU8254779 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MRKU6318604 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | PONU7401891 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | PONU8259020 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MRSU3541221 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU8497244 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MRKU3575168 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU0989130 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | TCNU8498847 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU0518382 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/07 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800106 | GUNHILDE MAERSK | MAEU966848767 | SHTC18110054 | MSKU0566375 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | TCNU8000614 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MSKU9628483 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | PONU7414630 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | UESU4669230 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU4100737 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | TGBU6654160 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU5460511 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | HASU4151824 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MSKU1838499 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRSU3930202 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU2646457 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU4938308 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | BSIU9024593 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU3473905 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | SUDU6536366 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | TRLU6918310 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MSKU1386526 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800109 | GUNHILDE MAERSK | MAEU966867275 | SHTC18100310 | MRKU5296521 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/05 (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | MRSU3575129 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | DELIVERED (PSS) | PSS
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | TCKU6555096 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | CLOSED IN CELLO ON 12/05 (PSS) | PSS
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | TCNU1553705 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | MRKU3565832 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | MRKU6447371 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800109 | GUNHILDE MAERSK | MAEU966858407 | SHTC18110051 | MRKU6131070 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PSS | 71800103 | GUNHILDE MAERSK | MAEU966858358 | SHTC18110053 | MRKU3224543 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PSS) | PSS
PSS | 71800103 | GUNHILDE MAERSK | MAEU966858358 | SHTC18110053 | MRKU3594656 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-04 |  | CLOSED IN CELLO ON 12/05 (PSS) | PSS
PSS | 71800103 | GUNHILDE MAERSK | MAEU966858358 | SHTC18110053 | MRKU4395638 | Q.PEAK DUO L G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-04 | 2018-11-29 |  |  | 2018-11-26 |  |  | 2018-12-05 |  |  | 2018-12-03 |  | CLOSED IN CELLO ON 12/04 (PSS) | PSS
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | GAOU6139381 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | CAIU4415820 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU8938165 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU2313150 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TGHU9629500 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | XINU8017166 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-04 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | GCXU5008959 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | GAOU6104560 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | CAXU8155506 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8464440 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU6533115 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU7010058 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | DFOU8033329 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD 12/05 AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU6835363 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | UETU5273308 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU2301210 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-05 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/06 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | FSCU8173830 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU6825010 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU7087403 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU8781970 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | BMOU4521890 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | FCIU8748431 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | FCIU9039282 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-06 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU8934299 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | FCIU8640679 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TGBU5776672 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU5720800 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8210092 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-07 |  | DELIVERED (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8738881 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TLLU5904990 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TCNU2751074 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU7008220 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8661305 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TLLU4948021 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8724213 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU8789770 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | ZCSU7119326 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TGHU9744090 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | TGBU5763335 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | FSCU6958844 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | CAXU8013965 | Q.PLUS L-G4.2.5 AF 345 | 12001434 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PIONEER | 71801009 | MAERSK SEMAKAU | SSPHPKL8042592 | SDSMY20181026-01 | GIPU9522310 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-10-26 | 2018-11-30 |  |  | 2018-11-26 |  |  | 2018-12-06 |  |  | 2018-12-08 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/10 (PIONEER-NB) | Pioneer NB - for transloading
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | PONU8246655 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MSKU1676119 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-17 |  |  | 2018-12-03 |  |  | 2018-12-21 |  |  | 2018-12-20 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRKU4662586 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-17 |  |  | 2018-12-03 |  |  | 2018-12-21 |  |  | 2018-12-20 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MSKU9294010 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRKU2067481 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | HASU4618117 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRSU4040857 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-17 |  |  | 2018-12-03 |  |  | 2018-12-21 |  |  | 2018-12-20 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRKU3729577 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | DAYU6122529 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRSU3770439 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | SUDUN8SOL0159391 | SHTC18110041 | MRKU5012440 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-12-03 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PSS) | PSS
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | TCNU5401383 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | ZCSU8891740 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | ZCSU8744122 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | TCNU4257137 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | TCKU6005715 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | DRYU9094596 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | TEMU6749563 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | GAOU6038149 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | ZCSU8541608 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GJERTRUD MAERSK | ZIMUSEL768500 | SHTC18110107 | ZCSU8597253 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | ZCSU8785939 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | TCNU2755906 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | TCNU8184770 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | TCNU4339430 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | ZCSU8507178 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800122 | GJERTRUD MAERSK | ZIMUSEL769860 | SHTC18110110 | FCIU8955721 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | ZCSU7022378 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD ON 12/14; CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | TCNU5413980 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | SEGU5203376 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | ZCSU8437384 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | ZCSU7060130 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800122 | GJERTRUD MAERSK | ZIMUSEL769859 | SHTC18110109 | ZCSU7089685 | Q.PEAK DUO L-G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | FCIU8648556 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | TCNU8673003 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | ZCSU8634948 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-14 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | ZCSU8557501 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | TCNU2973718 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-11 |  | DELIVERED(PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | ZCSU8648324 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | SEGU5275761 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-17 |  |  | 2018-11-29 |  |  | 2018-12-21 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | GLDU7404622 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | TCNU8111937 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | ZCSU8913027 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | GCXU5009908 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-17 |  |  | 2018-11-29 |  |  | 2018-12-21 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | TLLU4451591 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | ZCSU7065765 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | TGCU5076292 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-12 |  |  | 2018-12-10 |  | DELIVERED (PSS) | PSS
PSS | 71800106 | GJERTRUD MAERSK | ZIMUSEL767380 | SHTC18100256 | BSIU9722383 | Q.PEAK DUO BLK-G5.0.2 315 | 30355104 |  | 832 | 26 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | PAPERWORK RCVD ON 12/12 AND CLOSE IN CELLO ON 12/13 (PSS) | PSS
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8903230 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8727001 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8826154 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8668017 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8577703 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | TCNU8934175 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU7007096 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-17 |  |  | 2018-11-29 |  |  | 2018-12-21 |  |  | 2018-12-19 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/20 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | GJERTRUD MAERSK | ZIMUSEL769588 | SHTC18110103 | ZCSU8454606 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-11 | 2018-12-06 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-10 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/11 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | BSIU9678700 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | BSIU9679707 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | BSIU9698179 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | CAIU4256841 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD ON 12/14; CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | FCIU8954514 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/19 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | GAOU6079092 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | SEGU5423339 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | SEGU5780090 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/13 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | SEGU5810385 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU2307178 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU2309210 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU2503144 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU5413743 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU5417646 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-17 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU6833400 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-19 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/20 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU8117175 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TEMU6769600 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TEMU6869390 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TEMU7610206 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TLLU5305312 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TLLU5314490 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | UESU5198319 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | PAPERWORK RCVD ON 12/12 AND CLOSE IN CELLO ON 12/13 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | XINU8095364 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU7117447 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU8419185 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU8611623 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | BSIU9699745 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | BSIU9768851 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | PAPERWORK RCVD ON 12/12 AND CLOSE IN CELLO ON 12/13 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | FCIU9040236 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | GAOU6101745 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | JXLU8680901 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | SEGU5274997 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD ON 12/14; CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU2308071 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU4764300 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU8391720 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TCNU8533887 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | TLLU4898471 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU6504020 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD ON 12/14; CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU7038538 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042593 | SDSMY20181029-01 | ZCSU8776881 | Q.PLUS L-G4.2.AF 345 | 12001434 |  | 638 | 22 | 2018-10-29 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TLLU4304380 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8470192 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8997310 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TEMU6122212 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | CLOSED IN CELLO ON 12/19 (PIONEER-EDION) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | BMOU4506220 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-19 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/20 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | GAOU6138277 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | DFSU6494990 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | CAIU8414349 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | FSCU8165583 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/19 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TGHU9372027 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8525356 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/13 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8970562 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TCNU6907226 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/17 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TGHU9589394 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8916875 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8818349 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-14 |  | PAPERWORK RCVD ON 12/14; CLOSED IN CELLO ON 12/18 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8541721 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | XINU8121458 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TCNU4255279 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | ZCSU8925943 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | FSCU8173790 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-12 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | BMOU4584882 | Q.PLUS L-G4.2.AF 345 | 12001374 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-13 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801009 | CAP ARNAUTI | SSPHPKL8042594 | SDSMY20181027-01 | TCNU5096720 | Q.PLUS L-G4.2.AF 345 | 12001374 |  | 638 | 22 | 2018-10-30 | 2018-12-07 |  |  | 2018-11-29 |  |  | 2018-12-13 |  |  | 2018-12-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 12/12 (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | FSCU6971321 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-18 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | ZCSU7132903 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | TCNU4555208 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-18 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | TCNU7368010 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | TCNU8750373 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | ZCSU7134974 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-20 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | TCNU6393913 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-19 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | TCNU5551948 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-18 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | BMOU5254247 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-18 |  | DELIVERED (PSS) | PSS
PSS | 71800122 | MAERSK SUZHOU | ZIMUSEL769926 | SHTC18110135 | DRYU9600903 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-18 | 2018-12-13 |  |  | 2018-12-07 |  |  | 2018-12-19 |  |  | 2018-12-18 |  | DELIVERED (PSS) | PSS
PIONEER | 71800102 | GEORG MAERSK | ZIMUSEL200191057 | SHTC18110189 | TEMU6195775 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GEORG MAERSK | ZIMUSEL200191057 | SHTC18110189 | ZCSU8743656 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-27 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GEORG MAERSK | ZIMUSEL200191057 | SHTC18110189 | TEMU6800834 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-27 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GEORG MAERSK | ZIMUSEL200191057 | SHTC18110189 | ZCSU8883431 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800102 | GEORG MAERSK | ZIMUSEL200191057 | SHTC18110189 | TGHU9356073 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-27 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU2305940 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-27 |  | PAPERWORK RCVD 12/28 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | FSCU8097241 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | ZCSU8730725 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | GAOU6089383 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/2/2019 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU4246220 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU8184790 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | ZCSU8733792 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | GAOU6092582 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TGHU9785524 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-28 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/2 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU2724382 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | ZCSU8442755 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU8754640 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | TCNU5546978 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | BMOU4115289 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-28 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/2 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | SEGU5202343 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800120 | GEORG MAERSK | ZIMUSEL769692 | SHTC18110190 | SEGU5681267 | Q.PLUS L-G4.2.6.A.F 345 | 30340810 |  | 638 | 22 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-13 |  |  | 2018-12-28 |  |  | 2018-12-31 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
CUSTOMER SITE | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | MRKU2569448 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-28 |  | DIRECT DELIVERY TO ELMSFORD, NY | VIVINT SOLAR NY-05 (SHTC18110202A)
PSS | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | TCNU8519580 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-27 |  | DELIVERED 12/27 (PSS) | PSS
CUSTOMER SITE | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | MRKU5303934 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-28 |  | DIRECT DELIVERY TO LAKEWOOD, NJ | VIVINT SOLAR NJ-04 (SHTC18110202B)
CUSTOMER SITE | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | MRKU4289889 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-28 |  | DIRECT DELIVERY TO WESTBURY, NY | VIVINT SOLAR NY-01 (SHTC18110202C)
CUSTOMER SITE | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | HASU5046171 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-28 |  | DIRECT DELIVERY TO NORTH HAVEN, CT | VIVINT SOLAR CT-01 (SHTC18110202D)
PSS | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | MRSU3482263 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-28 |  | DELIVERED 12/28 (PSS) | PSS
PSS | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | MRSU3690518 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-27 |  | DELIVERED 12/27 (PSS) | PSS
PSS | 71800116 | GEORG MAERSK | SUDUN8SOL0168881 | SHTC18110202 | TCNU4543969 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-11-25 | 2018-12-20 |  |  | 2018-12-17 |  |  | 2019-01-02 |  |  | 2018-12-27 |  | DELIVERED 12/27 (PSS) | PSS
PIONEER | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161301 | SHTC18110146 | MSKU9565148 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | SCANNED ON 1/11 CLOSED IN CELLO ON 1/13 (PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161301 | SHTC18110146 | TCNU8827475 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161301 | SHTC18110146 | MRKU2551937 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161301 | SHTC18110146 | SUDU6817050 | Q.PEAK DUO L G5.3.1.F 390 | 30360619 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | MRKU6303498 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | MRSU3265890 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | MSKU1527080 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | CAXU9282980 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/16 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | MIEU2022928 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | SUDU6728409 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800122 | MAERSK SHEERNESS | SUDUN8SOL0161291 | SHTC18110145 | HASU4407351 | Q.PEAK DUO L-G5.3.1.F 385 | 30360618 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-15 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU8995750 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU8712423 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-09 |  | DELIVERED (PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU8646105 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU6502876 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-09 |  | DELIVERED (PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU8492376 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU7134721 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-05 |  |  | 2019-01-03 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | TEMU6750630 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-05 |  |  | 2019-01-03 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | TCNU8548207 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-05 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71800118 | MAERSK SHEERNESS | ZIMUSEL769721 | SHTC18110149 | ZCSU8870959 | Q.PEAK L-G4.2.0.F 365 | 30320114 |  | 638 | 22 | 2018-11-23 | 2018-12-27 |  |  | 2018-12-17 |  |  | 2019-01-05 |  |  | 2019-01-03 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8849761 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8547571 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8683541 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | TEMU6747684 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8790278 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | TCNU2757283 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | XINU8130547 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | FSCU8146480 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/14 (PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8524200 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8240836 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU8828368 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | XINU8214308 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | FCIU8574474 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | BMOU4550202 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | ZCSU7035040 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | TCNU5326090 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL770427 | SHTC18120038 | TCNU4576453 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-04 |  |  | 2019-01-04 |  | DELIVERED (PSS) | PSS
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | GAOU6037780 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU6506336 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU6538101 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8715124 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8973664 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8493900 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | AXIU1381612 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | TRLU6819169 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8430311 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8609539 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | FSCU8224644 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | CRSU9050267 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-09 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | FCIU8640869 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED (PSS) | PSS
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8885521 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | TCNU8937066 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8534002 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | BSIU9609762 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | ZCSU8487810 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800116 | GERD MAERSK | ZIMUSEL771858 | SHTC18120037 | GAOU6114906 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | ZCSU8622145 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | CLOSED IN CELLO ON 1/8 (PSS) | PSS
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | GVCU5324437 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | ZCSU8965400 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | CLOSED IN CELLO ON 1/14 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | FSCU8166070 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | ZCSU8651971 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-11 |  | DELIVERED (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | BMOU4584305 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PSS | 71800112 | GERD MAERSK | ZIMUSEL770429 | SHTC18110242 | CAIU9223835 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-02 | 2018-12-27 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-14 |  | CLOSED IN CELLO ON 1/15 (PSS) | LACK OF CHASSIS IN THE PORT OF NY/NJ AND EXTREME CONGESTION
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8857237 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-08 |  | PAPERWORK RCVD CLOSED IN CELLO ON 1/9 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8674025 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | DRYU9599567 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-08 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8601029 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | PAPERWORK RCVD CLOSED IN CELLO ON 1/9 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU4560312 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | FSCU8165500 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8548768 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | FSCU8150665 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8428361 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TGHU9816902 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8520483 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU4247951 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8352116 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU1827468 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU7027343 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | BSIU9720441 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU7060280 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU2608079 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU8112023 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-03 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU7065024 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8772762 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU2301858 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8719644 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-09 |  |  | 2019-01-11 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/14 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU8114730 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | XINU8115590 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8672700 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-09 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8658507 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | XINU8141670 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-04 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | GAOU6113670 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TGBU5764331 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU7020251 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU4557670 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/8 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TGHU9361300 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8718653 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU4851339 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | SCANNED ON 1/11 CLOSED IN CELLO ON 1/13 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TLLU4595182 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-08 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | FSCU6838371 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/8 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | TCNU4421298 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-07 |  |  | 2019-01-07 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/8 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU8872442 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-11 |  | DELIVERED(PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | SEAMAX NORWALK | SSPHPKL8044050 | SDSMY20181126-01 | ZCSU7008678 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-27 | 2018-12-28 |  |  | 2018-12-20 |  |  | 2019-01-08 |  |  | 2019-01-09 |  | DELIVERED (PIONEER-KILMER) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | CAIU9984330 | Q.PLUS L-G4.2.5 AF 345 | 12001373 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | CAXU8093976 | Q.PLUS L-G4.2.5 AF 345 | 12001373 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | HMMU6035581 | Q.PLUS L-G4.2.5 AF 345 | 12001373 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | DRYU9183646 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | TCNU5089613 | Q.PLUS L-G4.2.5 AF 345 | 12001374 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | CAIU7667002 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | CAXU8039954 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/15 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | DRYU9160661 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | HDMU6692839 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | HDMU6848747 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801010 | MAERSK KAWASAKI | HDMUMYWB0800335 | SDSMY20181130-02 | SEGU4523415 | Q.PLUS L-G4.2.5 AF 345 | 12001375 |  | 638 | 22 | 2018-11-30 | 2019-01-08 |  |  | 2018-12-31 |  |  | 2019-01-15 |  |  | 2019-01-14 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | SEGU5203993 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | TGHU9340360 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | CAXU8083345 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-15 |  |  | 2019-01-15 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8731655 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8846314 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8677024 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8910373 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8838221 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8604809 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | CAIU4424288 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8257103 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8576991 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | SEGU5193935 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | UESU4685694 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8561610 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | TCNU8757193 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PSS) | PSS
PSS | 71800116 | GUNDE MAERSK | ZIMUSEL772125 | SHTC18120087 | ZCSU8981000 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-12-09 | 2019-01-08 |  |  | 2018-12-26 |  |  | 2019-01-16 |  |  | 2019-01-16 |  | DELIVERED (PSS) | PSS
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | MSKU1800723 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-16 |  |  | 2018-01-16 |  |  | 2019-01-21 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | MRKU4068363 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-21 |  |  | 2018-01-16 |  |  | 2019-01-25 |  |  | 2019-01-24 |  | DELIVERED (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | MSKU8596777 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-21 |  |  | 2018-01-16 |  |  | 2019-01-25 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | MSKU8058874 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-21 |  |  | 2018-01-16 |  |  | 2019-01-25 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | HASU4634904 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-18 |  |  | 2018-01-16 |  |  | 2019-01-24 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | GESU6011120 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-17 |  |  | 2018-01-16 |  |  | 2019-01-24 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | MRKU4756880 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-18 |  |  | 2018-01-16 |  |  | 2019-01-25 |  |  | 2019-01-24 |  | DELIVERED (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800116 | SAN CHRISTOBAL | SUDUN8SOL0163201 | SHTC18110191 | TCKU9769260 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 |  | 832 | 26 | 2018-11-26 | 2019-01-28 |  |  | 2018-01-16 |  |  | 2019-02-01 |  |  | 2019-01-30 |  | DELIVERED (PSS) | Maersk decided to omit the port of New York and for schedule recovery all containers have been discharged in Baltimore on 1/8. Hamburg Sud will be moving containers to H&M Depot in Kearny, NJ for customer retrieval. No ETA at this time, will advise by early next week.
PSS | 71800128 | GRETE MAERSK | ZIMUSEL772566 | SHTC18120132 | CAIU4433818 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-02-04 |  |  | 2019-02-04 |  | DELIVERED (PSS) | LOST - TERMINAL UNABLE TO LOCATE THIS CONTAINER; CONTAINER LOCATED
PSS | 71800128 | GRETE MAERSK | ZIMUSEL772566 | SHTC18120132 | BSIU9343590 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | PSS
PSS | 71800128 | GRETE MAERSK | ZIMUSEL772566 | SHTC18120132 | TCKU6561381 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | PSS
PSS | 71800128 | GRETE MAERSK | ZIMUSEL772566 | SHTC18120132 | TEMU6678330 | Q.PEAK-G4.1.0.F 305 | 30124902 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | CLOSED IN CELLO 1/25 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8486012 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8994522 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-23 |  | DELIVERED (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8850042 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | DELIVERED (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8243476 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | CLOSED IN CELLO 1/25 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8848976 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | CLOSED IN CELLO 1/25 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8652155 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-25 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8845025 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | DELIVERED (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8772850 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8882100 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU8718951 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-28 |  |  | 2019-01-24 |  | DELIVERED (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | TEMU6798110 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | CAIU7952587 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-23 |  | CLOSED IN CELLO ON 1/24 (PSS) | PSS
PSS | 71800126 | GRETE MAERSK | ZIMUSEL772565 | SHTC18120129 | ZCSU6551150 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 |  | 832 | 26 | 2018-12-16 | 2019-01-21 |  |  | 2019-01-03 |  |  | 2019-01-24 |  |  | 2019-01-24 |  | CLOSED IN CELLO 1/25 (PSS) | PSS
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | BSIU9540856 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | BSIU9611076 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | CAIU8621412 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | CAIU8765209 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | FCIU8928562 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | CLOSED IN CELLO 1/22 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | SEGU5196364 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TCNU2779235 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TCNU5347364 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TCNU5385805 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TCNU8769131 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TGBU5759973 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | TLLU5389057 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU7086351 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU7092307 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU7119100 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8214776 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8251240 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8468256 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8545054 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8667875 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801011 | RDO CONCERT | SSPHPKL8044666 | SDSMY20181211-01 | ZCSU8988751 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-11 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | CAIU9972284 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HDMU6651233 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HMMU6047704 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/17 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HMMU6016679 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | TCNU6978810 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | CAIU9974775 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | CAIU7397801 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/17 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | CAIU7486597 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | TGBU6352961 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HDMU6299570 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | BMOU4593117 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | TCNU7318339 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | TGBU6163232 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-24 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/25 (PIONEER) | TUNNEL RAIL DAMAGE-- PENDING TO BE PICKED UP; TRANS LOADED DUE TO MAJOR EXTENSIVE DAMAGE FROM TGBU6163232 to FSCU9607400 THEN FSCU9607400 HAD A HOLE IN THE ROOF SO THEY LOADED CONTAINER# MSKU8058874
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HMMU6095343 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | SEGU5833354 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HMMU6239116 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | TCNU7402692 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/16 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | CAIU8767095 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800455 | SDSMY20181130-03 | HMMU6121099 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-08 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | HMMU6117777 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | CAIU7154925 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/17 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | TLLU5839046 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | GAOU6192241 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | PAPERWORK RCVD ON 1/18 CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | CAIU7707609 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | BMOU4138896 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/17 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | DFSU6805243 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | HMMU6289380 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | BSIU9226059 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | PAPERWORK RCVD ON 1/18 CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | CAIU7402786 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | BMOU4144482 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | PAPERWORK RCVD ON 1/18 CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | HMMU 6127564 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | PAPERWORK RCVD ON 1/18 CLOSED IN CELLO ON 1/19 (PIONEER-EDISON)
PIONEER | 71801010 | RDO CONCERT | HDMUMYWB0800534 | SDSMY20181130-04 | CAIU7315383 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-11-30 | 2019-01-12 |  |  | 2019-01-07 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/17 (PIONEER-EDISON)
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | TCNU7311627 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | REVISED PAPERWORK RCVD AND CLOSE IN CELLO 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | BMOU4140070 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-22 |  |  | 2019-01-18 |  | REVISED PAPERWORK RCVD AND CLOSED IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | FSCU9607400 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | BSIU9202925 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | DRYU9220755 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-22 |  |  | 2019-01-18 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/21 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | GAOU6228684 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | HMMU6030050 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | CAIU7134195 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | CAIU8481060 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | TEMU7252885 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | HDMU6301467 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | TCNU7587451 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PSS | 71801010 | NORTHERN JAGUAR | HDMUMYWB0800708 | SDSMY20181130-05 | CAIU7441566 | Q.PLUS L-G4.2.5 AF 350 | 12001226 |  | 638 | 22 | 2018-12-19 | 2019-01-17 |  |  | 2019-01-07 |  |  | 2019-01-23 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PSS) | PSS
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | DFSU7063350 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | TCLU5493130 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | GESU5242974 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-21 |  | DELIVERED (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | TEMU7238300 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | FSCU8370340 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD AND CLOSED IN CELLO 1/24 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | APHU7286382 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | TCNU5383192 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | BEAU4024230 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-21 |  | PAPERWORK RCVD AND CLOSE IN CELLO ON 1/22 (PIONEER-EDISON) | Pioneer - Kilmer
PIONEER | 71801011 | CMA CGM LIBRA | CMDUAYN0511129 | PLIMY4801449 | GESU6150002 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-20 | 2019-01-14 |  |  | 2019-01-10 |  |  | 2019-01-21 |  |  | 2019-01-22 |  | PAPERWORK RCVD 1/22 AND CLOSED IN CELLO 1/23 (PIONEER-EDISON) | Pioneer - Kilmer
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | GAOU6041034 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | ZCSU8545521 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | GCXU5079253 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | CRSU9070577 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TCKU6646998 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-02-05 |  |  | 2019-02-04 |  | DELIVERED (PSS) | LOST - TERMINAL UNABLE TO LOCATE THIS CONTAINER; CONTAINER LOCATED
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TGBU5956720 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TCNU5338594 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | CAXU8061109 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | ZCSU8422194 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | ZCSU8540469 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TLLU5806886 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | BMOU4509385 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TCNU2966350 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | ZCSU8842509 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | RFCU5019004 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-30 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TGHU9349916 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-30 |  | DELIVERED (PSS) | PSS
PSS | 71800132 | GERNER MAERSK | ZIMUSEL772672 | SHTC18120207 | TCNU1060268 | Q.PEAK DUO BLK-G5.0.3 315 | 30355204 |  | 832 | 26 | 2018-12-30 | 2019-01-23 |  |  | 2019-01-21 |  |  | 2019-01-29 |  |  | 2019-01-29 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002092 | SHTC18120221 | GAOU6241665 | Q.PEAK DUO L-G5.2.0.F 385 | 30360218 |  | 174 | 6 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002092 | SHTC18120221 | GAOU6241665 | Q.PEAK DUO L-G5.2.0.F 385 | 30360218 |  | 20 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002068 | SHTC19010046 | EITU1985754 | Q.PEAK DUO BLK-G5.0.2 320 | 30355105 |  | 192 | 6 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002068 | SHTC19010046 | EITU1985754 | Q.PEAK DUO BLK-G5.0.2 320 | 30355105 |  | 25 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002068 | SHTC19010046 | EITU1985754 | Q.PEAK DUO G5.0.2.F 315 | 30350104 |  | 544 | 17 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002068 | SHTC19010046 | EITU1985754 | Q.PEAK DUO G5.0.2.F 315 | 30350104 |  | 2 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002068 | SHTC19010046 | SEGU5287248 | Q.PEAK DUO BLK-G5.0.2 320 | 30355105 |  | 832 | 26 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002084 | SHTC19010048 | EISU9410618 | Q.PEAK DUO BLK-G5/SC 310 | 30359003 |  | 676 | 26 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002084 | SHTC19010048 | EITU1189660 | Q.PEAK DUO BLK-G5/SC 310 | 30359003 |  | 676 | 26 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002084 | SHTC19010048 | EGHU9306951 | Q.PEAK DUO BLK-G5/SC 310 | 30359003 |  | 598 | 23 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002084 | SHTC19010048 | EGHU9306951 | Q.PEAK DUO BLK-G5/SC 310 | 30359003 |  | 18 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002076 | SHTC19010047 | TGBU6611954 | Q.PEAK DUO BLK-G5.0.3 310 | 30355203 |  | 608 | 19 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002076 | SHTC19010047 | TGBU6611954 | Q.PEAK DUO BLK-G5.0.3 310 | 30355203 |  | 25 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002076 | SHTC19010047 | TCNU2708714 | Q.PEAK DUO BLK-G5.0.3 320 | 30355205 |  | 672 | 21 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71800125 | COSCO PRIDE | EGLV040900002076 | SHTC19010047 | TCNU2708714 | Q.PEAK DUO BLK-G5.0.3 320 | 30355205 |  | 25 | 1 | 2019-01-07 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-05 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU7023883 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | BMOU4516234 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | FSCU8088614 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | TLLU5324729 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | TCNU8187260 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU7112640 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | XINU8013113 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | TCNU2478226 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | TEMU6794794 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU7007178 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-06 |  | CLOSED IN CELLO 2/7 (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | TLLU5947375 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU8651903 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU8516586 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-08 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU8943886 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | FSCU8257680 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | SEGU5332347 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | BSIU9707898 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU8710924 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | BSIU9702520 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | MAERSK KLEVEN | SSPHPKL8045312 | SDSMY20181227-02 | ZCSU8825306 | Q.PLUS L-G4.2.AF 345 | 12001227 |  | 638 | 22 | 2018-12-27 | 2019-02-01 |  |  | 2019-01-25 |  |  | 2019-02-07 |  |  | 2019-02-07 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | ZCSU8785029 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | TEMU6794900 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 34 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | TCNU6835086 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | TCNU6954491 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | ZCSU8733703 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | TCNU6833859 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | ZCSU8442143 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | WSCU8529471 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | ZCSU8819258 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045430 | SDSMY20181230-02 | ZCSU6537168 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | BMOU4521230 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | ZCSU7117961 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | ZCSU8807494 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | BSIU9611327 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | ZCSU8756627 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | CAIU9226515 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | BMOU4098854 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | TCLU8701920 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | TCNU1764375 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | TCNU4858760 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-12 |  | CLOSED IN CELLO 2/13 (PSS) | PSS
PSS | 71801013 | NORTHERN MAJESTIC | SSPHPKL8045314 | SDSMY20181230-01 | TCNU8931160 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2018-12-30 | 2019-02-08 |  |  | 2019-02-04 |  |  | 2019-02-14 |  |  | 2019-02-13 |  | DELIVERED (PSS) | PSS
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | FBXU5008848 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | PAPERWORK RCVD AND CLOSED IN CELLO 02/22 (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRKU3676498 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRKU3738579 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | HASU4782856 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS) | RESCHEDULED TO FRIDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | PONU7822709 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRSU3843160 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRKU5064110 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS) | RESCHEDULED TO FRIDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRKU5141181 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | HASU4640337 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS) | RESCHEDULED TO FRIDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MRKU2484870 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | MSKU1573701 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967623061 | NPNESENYSSE45618 | TCNU5820230 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-22 |  | DELIVERED (PSS) | RESCHEDULED TO FRIDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU6552265 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8530007 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS); CLOSED IN CELLO 2/20
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU7259874 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8488798 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8463193 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | CRSU9012992 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU8605673 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | CAIU4253307 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU6500981 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8862439 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS); CLOSED IN CELLO 2/20
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | BSIU9753810 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | CAIU4423511 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU6952138 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8863395 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS); CLOSED IN CELLO 2/20
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | DFSU6538743 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8856380 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | DRYU9079230 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS); PAPERWORK RCVD AND CLOSED IN CELLO 2/20
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | JXLU8440520 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU8605143 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU4401250 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | TCNU5413553 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS), CLOSED IN CELLO 2/19
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | BSIU9769610 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-18 |  | DELIVERED (PSS)
PSS | 71900010 | GUNHILDE MAERSK | ZIMUSEL774966 | NPNESENYSSE45641 | ZCSU8981973 | Q.PEAK DUO BLK-G5/SC 315 | 30359004 | 25 | 676 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-20 |  |  | 2019-02-19 |  | DELIVERED (PSS); CLOSED IN CELLO 2/20
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | MRKU5156617 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | MSKU1567606 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | HASU4600838 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | HASU4869405 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | MSKU0223885 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | MRKU5889445 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | MSKU1807395 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-25 |  | DELIVERED (PSS) | DELAY IN DELIVEREIES RESULTING FROM THE TERMINAL CLOSURE AND WEATHER CASUING EXTREME CONGESTION.
PSS | 71900002 | GUNHILDE MAERSK | MAEU967624244 | NPNESENYSSE45677 | SUDU8513056 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900008 | GUNHILDE MAERSK | MAEU967624308 | NPNESENYSSE45675 | MSKU1826311 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS) | RESCHEDULED TO THURSDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900008 | GUNHILDE MAERSK | MAEU967624308 | NPNESENYSSE45675 | SUDU8716829 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-25 |  | DELIVERED (PSS) | RESCHEDULED TO FRIDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20; DELAY IN DELIVEREIES RESULTING FROM THE TERMINAL CLOSURE AND WEATHER CASUING EXTREME CONGESTION.
PSS | 71900008 | GUNHILDE MAERSK | MAEU967624308 | NPNESENYSSE45675 | TGHU6779873 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900008 | GUNHILDE MAERSK | MAEU967624308 | NPNESENYSSE45675 | TGBU6758966 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-21 |  | DELIVERED (PSS) | RESCHEDULED TO THURSDAY DUE TO SNOW STORM ALL PIERS ARE CLOSING AT 1PM 2/20
PSS | 71900008 | GUNHILDE MAERSK | MAEU967624308 | NPNESENYSSE45675 | MRSU3194863 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-20 | 2019-02-14 |  |  | 2019-02-08 |  |  | 2019-02-21 |  |  | 2019-02-20 |  | DELIVERED (PSS)
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TCNU2302860 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TCNU8764572 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TLLU5317972 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | ZCSU8973710 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TLLU5918232 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | GAOU6104045 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-03-01 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | FSCU8148992 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | BSIU9702495 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TCNU1061937 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TGBU5780712 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | TCNU4863392 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | ZCSU8825728 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | ZCSU8802255 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | ZCSU8597926 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900008 | GJERTRUD MAERSK | ZIMUSEL776791 | NPNESEATSSE45877 | ZCSU7134779 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-28 |  |  | 2019-02-28 |  | DELIVERED (PSS), CLOSED IN CELLO 3/1 | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | MRKU3706210 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-27 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | MRKU4689817 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | MSKU9086145 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | HASU5155700 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-28 |  | DELIVERED (PSS), CLOSED IN CELLO 3/1 | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | AMFU8797614 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PSS | 71900002 | GJERTRUD MAERSK | MAEU967624462 | NPNESENYSSE45676 | MRKU2544938 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-01-27 | 2019-02-21 |  |  | 2019-02-14 |  |  | 2019-02-27 |  |  | 2019-02-28 |  | DELIVERED (PSS) | APM Terminals, Elizabeth, will be closing our truck gates immediately due to the safety threat caused by severe high-winds 02/25/19.
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TCNU4544414 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | ECMU9692484 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-14 |  |  | 2019-03-15 |  | DELIVERED (PSS)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | CAXU8114873 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-22 |  |  | 2019-03-21 |  | DELIVERED (PSS) | APM CONGESTION DUE TO BROKEN MACHINE IN THE LOCATION AREA; RESCHEDULED DUE TO TERMINAL NOT ACCESSIBLE
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TGHU9472392 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-14 |  |  | 2019-03-15 |  | DELIVERED (PSS)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TLLU4566878 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE; WAS SCHEDULED WITH PIONEER BUT NOW WITH PSS
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TLLU4808930 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE; WAS SCHEDULED WITH PIONEER BUT NOW WITH PSS
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TEMU8389358 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-18 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TRLU7651969 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PSS)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | FSCU8996437 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | IRNU4603480 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TRLU7054264 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-15 |  | DELIVERED (PSS)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TCNU7084210 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TCLU9816312 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-18 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | CAIU8791830 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | CAIU9125802 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PSS) | WAS SCHEDULED WITH PIONEER BUT NOW WITH PSS
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TCLU9592790 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB) PAPERWORK RCVD AND CLOSED IN CELLO 3/19
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TCNU5736140 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | TGHU8702079 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PIONEER | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | APHU6808902 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-15 |  |  | 2019-03-18 |  | DELIVERED (PIONEER NB)
PSS | 71901001 | CMA CGM PELLEAS | CMDUAYN0517938 | SDSMY20190209-01 | SEGU4139122 | Q.PLUS L-G4.2.AF 345 | 12001507 | 25 | 638 | 22 | 2019-02-09 | 2019-03-08 |  |  | 2019-02-28 |  |  | 2019-03-22 |  |  | 2019-03-21 |  | DELIVERED (PSS) | RESCHEDULED DUE TO TERMINAL NOT ACCESSIBLE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU6527196 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8250393 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU6537492 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | CAXU8059523 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | FCIU8749058 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8990281 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-12 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | TCNU5501551 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | GCXU5004315 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-14 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | FCIU8634608 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | FSCU8224937 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-12 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU6501397 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | TCNU4265940 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | TCNU6952499 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | TCNU8905290 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8694253 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8543350 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-12 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8589962 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8745094 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-13 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900007 | GUDRUN MAERSK | ZIMUSEL775289 | NPNESEATSSE46130 | ZCSU8939720 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900017 | GUDRUN MAERSK | ZIMUSEL778038 | NPNESEATSSE46128 | ZCSU8845529 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900017 | GUDRUN MAERSK | ZIMUSEL778038 | NPNESEATSSE46128 | ZCSU8676455 | Q.PEAK DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900017 | GUDRUN MAERSK | ZIMUSEL778037 | NPNESEATSSE46129 | TGBU5971940 | Q.PEAK DUO BLK-G5.0.3.F 310 | 30355403 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900017 | GUDRUN MAERSK | ZIMUSEL778037 | NPNESEATSSE46129 | TCNU8931941 | Q.PEAK DUO BLK-G5.0.3.F 310 | 30355403 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU7089387 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | CAIU7697516 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU6502135 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | BMOU4764821 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-12 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU8716060 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-15 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | FSCU8097806 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-11 |  | DELIVERED (PSS)
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU8821430 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | SEGU5757589 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU8439427 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | CRSU9052589 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-11 |  | DELIVERED (PSS)
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | ZCSU8669060 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | BEAU5010415 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-12 |  | DELIVERED (PSS) REVISED PAPERWORK RCVD AND CLOSED IN CELLO 3/14 | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71900005 | GUDRUN MAERSK | ZIMUSEL775121 | NPNESEATSSE46134 | TCNU8547936 | Q.PLUS BFR-G4.1.0.A.F 285 | 30330028 | 25 | 832 | 26 | 2019-02-10 | 2019-03-06 |  |  | 2019-02-28 |  |  | 2019-03-13 |  |  | 2019-03-14 |  | DELIVERED (PSS) | DUE TO EXTREME TERMINAL CONGESTION NEED TO RESCHEDULE
PSS | 71901001 | SEROJA LIMA | SSPHPKL8045804 | SDSMY20190129-01 | GAOU6270200 | Q.PLUS L G4.2 AF 345 | 12001227 | 25 | 638 | 22 | 2019-01-31 | 2019-03-12 |  |  | 2019-02-28 |  |  | 2019-03-18 |  |  | 2019-03-18 |  | DELIVERED (PSS)
PSS | 71901001 | SEROJA LIMA | SSPHPKL8045804 | SDSMY20190129-01 | CAIU4415270 | Q.PLUS L G4.2 AF 345 | 12001227 | 25 | 638 | 22 | 2019-01-31 | 2019-03-12 |  |  | 2019-02-28 |  |  | 2019-03-18 |  |  | 2019-03-18 |  | DELIVERED (PSS)
PSS | 71901001 | SEROJA LIMA | SSPHPKL8045804 | SDSMY20190129-01 | TLLU4949748 | Q.PLUS L G4.2 AF 345 | 12001227 | 25 | 638 | 22 | 2019-01-31 | 2019-03-12 |  |  | 2019-02-28 |  |  | 2019-03-18 |  |  | 2019-03-18 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8634953 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | TLLU4858381 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | GCXU5002349 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8843932 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8555031 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8946566 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | TCNU8724456 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8771616 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-19 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8925943 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | AXIU1450966 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | TLLU5305138 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | TCNU2504135 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | TLLU5387162 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900017 | GEORG MAERSK | ZIMUSEL778416 | NPNESEATSSE46223 | ZCSU8815334 | DUO BLK-G5.0.2.F 315 | 30355304 | 25 | 832 | 26 | 2019-02-19 | 2019-03-14 |  |  | 2019-03-07 |  |  | 2019-03-20 |  |  | 2019-03-20 |  | DELIVERED (PSS)
PSS | 71900022 | GERD MAERSK | ZIMUSEL779637 | NPNESEATSSE46398 | ZCSU8656422 | Q.PEAK DUO BLK-G5/SC 310 | 30359003 | 25 | 676 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778417 | NPNESEATSSE46397 | TCNU5410343 | Q.PEAK DUO BLK-G5.0.3.F 310 | 30355403 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778417 | NPNESEATSSE46397 | TCNU2755362 | Q.PEAK DUO BLK-G5.0.3.F 310 | 30355403 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TCNU2977689 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | BMOU4519824 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8705975 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU6526097 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TCNU5355884 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8423441 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8460018 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TGBU7209174 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TLLU4595583 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8722817 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TCNU2298380 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | TEMU6800259 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8818884 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | GVCU5327185 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-22 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8566170 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8990379 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU6507585 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU8960327 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PSS | 71900017 | GERD MAERSK | ZIMUSEL778423 | NPNESEATSSE46350 | ZCSU7106798 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900013 | GERD MAERSK | ZIMUSEL778816 | NPNESEATSSE46373 | FSCU6851373 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-25 |  | DELIVERED (PSS)
PSS | 71900013 | GERD MAERSK | ZIMUSEL778816 | NPNESEATSSE46373 | TLLU4865729 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PSS | 71900013 | GERD MAERSK | ZIMUSEL778816 | NPNESEATSSE46373 | TCNU4554161 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-02-24 | 2019-03-20 |  |  | 2019-03-13 |  |  | 2019-03-26 |  |  | 2019-03-27 |  | DELIVERED (PSS)
PIONEER | 71901002 | MAERSK KAWASKAI | SSPHPKL8046857 | SDSMY20190219-01 | GCXU5070560 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-02-20 | 2019-03-29 |  |  | 2019-03-21 |  |  | 2019-04-04 |  |  | 2019-04-01 |  | DELIVERED (PIONEER-NB)
PIONEER | 71901002 | MAERSK KAWASKAI | SSPHPKL8046857 | SDSMY20190219-01 | TCNU5832605 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-02-20 | 2019-03-29 |  |  | 2019-03-21 |  |  | 2019-04-04 |  |  | 2019-04-01 |  | DELIVERED (PIONEER-NB)
PIONEER | 71901002 | MAERSK KAWASKAI | SSPHPKL8046857 | SDSMY20190219-01 | DFSU6494590 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-02-20 | 2019-03-29 |  |  | 2019-03-21 |  |  | 2019-04-04 |  |  | 2019-04-01 |  | DELIVERED (PIONEER-NB)
PIONEER | 71900013 | GUNDE MAERSK | ZIMUSEL778818 | NPNESEATSSE46487 | FSCU8227200 | Q.PEAK DUO G5.0.2.F 320 | 30350105 | 25 | 832 | 26 | 2019-03-04 | 2019-03-27 |  |  | 2019-03-21 |  |  | 2019-04-02 |  |  | 2019-03-29 |  | DELIVERED (PIONEER-NB)
PIONEER | 71900013 | GUNDE MAERSK | ZIMUSEL778818 | NPNESEATSSE46487 | ZCSU8447274 | Q.PEAK DUO G5.0.2.F 320 | 30350105 | 25 | 832 | 26 | 2019-03-04 | 2019-03-27 |  |  | 2019-03-21 |  |  | 2019-04-02 |  |  | 2019-03-29 |  | DELIVERED (PIONEER-NB)
PIONEER | 71900013 | GUNDE MAERSK | ZIMUSEL778818 | NPNESEATSSE46487 | MAGU5140400 | Q.PEAK DUO G5.0.2.F 320 | 30350105 | 25 | 832 | 26 | 2019-03-04 | 2019-03-27 |  |  | 2019-03-21 |  |  | 2019-04-02 |  |  | 2019-03-29 |  | DELIVERED (PIONEER-NB)
PIONEER | 71900013 | GUNDE MAERSK | ZIMUSEL778818 | NPNESEATSSE46487 | ZCSU8711258 | Q.PEAK DUO G5.0.2.F 320 | 30350105 | 25 | 832 | 26 | 2019-03-04 | 2019-03-27 |  |  | 2019-03-21 |  |  | 2019-04-02 |  |  | 2019-03-29 |  | DELIVERED (PIONEER-NB)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | TCNU7258939 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-16 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8739574 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8241051 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-16 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | TGBU5491685 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8712953 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU7013756 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | FCIU8685502 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | CAIU4304786 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | CAIU4291117 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8665701 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-16 |  |  | 2019-04-12 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU6518980 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8436161 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | TCNU4633912 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780940 | NPNESEATSSE46841 | ZCSU8708070 | Q.PEAK DUO BLK-G5.0.3.F 315 | 30355404 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780942 | NPNESEATSSE46856 | ZCSU7108722 | Q.PEAK DUO BLK-G5.0.3.F 320 | 30355405 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900029 | GUSTAV MAERSK | ZIMUSEL780942 | NPNESEATSSE46856 | BSIU9216240 | Q.PEAK DUO BLK-G5.0.3.F 320 | 30355405 | 25 | 832 | 26 | 2019-03-17 | 2019-04-10 |  |  | 2019-04-05 |  |  | 2019-04-17 |  |  | 2019-04-15 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | TCKU6645034 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | CRSU9044449 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | TCNU4953048 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | SEGU5279155 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | ZCSU8760761 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | CAIU4335642 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | TCNU2764301 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | LCRU9662762 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | CAIU4422032 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900026 | GUNHILDE MAERSK | ZIMUSEL781212 | NPNESEATSSE47095 | TCNU5367170 | Q.PEAK BLK-G4.1.0.F 295 | 30315030 | 25 | 832 | 26 | 2019-04-07 | 2019-05-02 |  |  | 2019-04-25 |  |  | 2019-05-08 |  |  | 2019-05-06 |  | DELIVERED (PSS)
PSS | 71900035 | YM UNIFORMITY | ONEYSELV34955500 | NPNESEATSSE47546 | TCLU6434743 | Q.PEAK DUO BLK-G5.0.3.F 320 | 30355405 | 25 | 832 | 26 | 2019-04-13 | 2019-05-07 |  |  | 2019-04-30 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED (PSS)
PSS | 71900035 | YM UNIFORMITY | ONEYSELV34955500 | NPNESEATSSE47546 | TCNU7720991 | Q.PEAK DUO BLK-G5.0.3.F 320 | 30355405 | 25 | 832 | 26 | 2019-04-13 | 2019-05-07 |  |  | 2019-04-30 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED (PSS)
PSS | 71900035 | GUDRUN MAERSK | ZIMUSEL784452 | NPNESEATSSE47892 | ZCSU8694090 | Q.PEAK DUO BLK-G5.0.3.F 320 | 30355405 | 25 | 832 | 26 | 2019-04-28 | 2019-05-23 |  |  | 2019-05-15 |  |  | 2019-05-30 |  |  | 2019-05-24 |  | DELIVERED (PSS)
PSS | 71900035 | GUDRUN MAERSK | ZIMUSEL784452 | NPNESEATSSE47892 | ZCSU8694090 | Lids (1000000060808) | Packing Materials | 25 | 5 | 1 | 2019-04-28 | 2019-05-23 |  |  | 2019-05-15 |  |  | 2019-05-30 |  |  | 2019-05-24 |  | DELIVERED (PSS)
PSS | 71900035 | GUDRUN MAERSK | ZIMUSEL784452 | NPNESEATSSE47892 | ZCSU8694090 | Lids (1000000062422) | Packing Materials | 25 | 2 | 1 | 2019-04-28 | 2019-05-23 |  |  | 2019-05-15 |  |  | 2019-05-30 |  |  | 2019-05-24 |  | DELIVERED (PSS)
PSS | 71900035 | GUDRUN MAERSK | ZIMUSEL784452 | NPNESEATSSE47892 | ZCSU8694090 | Carton (1000000060840) | Packing Materials | 25 | 5 | 1 | 2019-04-28 | 2019-05-23 |  |  | 2019-05-15 |  |  | 2019-05-30 |  |  | 2019-05-24 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU7073740 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8483040 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TLLU5926428 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8450787 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TLLU4898492 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8528530 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TLLU5923584 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | GCXU5000834 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TCNU5780287 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8922414 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | DFSU6303353 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TCNU4856752 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | FSCU8154932 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8549168 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | BSIU9768954 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8938149 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8739018 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TEMU6756304 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8955568 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | GLDU7407581 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TCLU5137139 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TCNU4850013 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | ZCSU8631445 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-12 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | TLLU4735480 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-11 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | BSIU9587637 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | GERD MAERSK | ZIMUSEL787818 | NPNESEATSSE48107 | SEGU5284948 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-12 | 2019-06-05 |  |  | 2019-06-04 |  |  | 2019-06-12 |  |  | 2019-06-10 |  | DELIVERED (PSS)
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU8716922 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS)
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU7123558 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS) CLOSED IN CELLO ON 6/17
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU8964960 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS) CLOSED IN CELLO ON 6/17
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU8786792 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS) CLOSED IN CELLO ON 6/17
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU8240327 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS)
PSS | 71900043 | ARTHUR MAERSK | ZIMUSEL787819 | NPNESEATSSE48240 | ZCSU6541912 | Q.PEAK DUO G5.0.2.F 325 | 30350106 | 25 | 832 | 26 | 2019-05-19 | 2019-06-12 |  |  | 2019-06-07 |  |  | 2019-06-18 |  |  | 2019-06-14 |  | DELIVERED (PSS) CLOSED IN CELLO ON 6/17
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | APHU6948057 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | APHU7188318 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-27 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | FCIU8794397 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-27 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | INKU6312950 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-27 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | SEGU4985898 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-27 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | TCNU5959307 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-27 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | TCNU7535273 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | TCNU8058679 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | TGHU6303043 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM THAMES | CMDUAYN0531163 | SDSMY20190530-01 | TRLU7321669 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-05-31 | 2019-06-24 |  |  | 2019-06-19 |  |  | 2019-07-01 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | KKFU8004166 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-02 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | TCNU5247540 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-02 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | BSIU9661077 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | CAIU9168574 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | TCNU7737905 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | NYKU4906498 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/3
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | TCLU8458940 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/2
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | ONEU0144679 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-02 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | TLLU5476887 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | ONEU0256540 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | KKFU7615704 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/3
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | ONEU0219654 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 638 | 22 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54357300 | NPNESEATSSE48578 | TCLU9274700 | Q.PEAK DUO L G5.3.0.F 380 | 30360417 | 25 | 609 | 21 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71900047 | ATHOS | ONEYSELV54359500 | NPNESEATSSE48580 | FSCU8567788 | Q.PEAK DUO L G5.3.0.F 385 | 30360418 | 25 | 203 | 7 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-06-28 |  | DELIVERED (PSS)
PSS | 71900046 | CORNELIA MAERSK | ZIMUSEL787821 | NPNESEATSSE48376 | BSIU9677767 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/3
PSS | 71900046 | CORNELIA MAERSK | ZIMUSEL787821 | NPNESEATSSE48376 | TEMU6131174 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-02 | 2019-06-26 |  |  | 2019-06-19 |  |  | 2019-07-02 |  |  | 2019-07-01 |  | DELIVERED (PSS)
PSS | 71901008 | GUSTAV MAERSK | HDMUMYNW0825290 | MY9050111101 | HDMU6734723 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-06-29 |  |  | 2019-06-24 |  |  | 2019-07-05 |  |  | 2019-07-03 |  | DELIVERED (PSS)
PSS | 71901008 | GUSTAV MAERSK | HDMUMYNW0825290 | MY9050111101 | TCLU8397361 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-06-29 |  |  | 2019-06-24 |  |  | 2019-07-05 |  |  | 2019-07-03 |  | DELIVERED (PSS)
PSS | 71901008 | GUSTAV MAERSK | HDMUMYNW0825290 | MY9050111101 | TCNU8655761 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-01 | 2019-06-29 |  |  | 2019-06-24 |  |  | 2019-07-08 |  |  | 2019-07-03 |  | DELIVERED (PSS)
PSS | 71901008 | GUSTAV MAERSK | HDMUMYNW0825290 | MY9050111101 | TEMU7252592 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-01 | 2019-06-29 |  |  | 2019-06-24 |  |  | 2019-07-05 |  |  | 2019-07-03 |  | DELIVERED (PSS)
PSS | 71901008 | GUSTAV MAERSK | HDMUMYNW0825290 | MY9050111101 | TLLU5292895 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-06-01 | 2019-06-29 |  |  | 2019-06-24 |  |  | 2019-07-08 |  |  | 2019-07-03 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | CRSU9067634 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | TCNU4497987 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | TCNU5720890 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | SLSU8050328 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | TGBU7070854 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900045 | MAERSK SHENZHEN | ZIMUSEL790793 | NPNESEATSSE48743 | BMOU4583973 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | TCNU2479222 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | GCXU5068515 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | ZCSU7058112 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | DRYU9136114 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | DRYU9143638 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900046 | MAERSK SHENZHEN | ZIMUSEL787820 | NPNESEATSSE48581 | ZCSU8697925 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | ZCSU7041824 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | CRSU9013237 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | ZCSU8820182 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | BSIU9752644 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | ZCSU8749211 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TCNU5406554 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | ZCSU8680898 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TCNU2752424 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | ZCSU8503059 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | GAOU6142472 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TCNU2301523 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-11 |  |  | 2019-07-09 |  | DELIVERED (PIONEER NEW) | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TLLU5918187 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TGHU9352951 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PIONEER | 71900045 | MAERSK SHENZHEN | ZIMUSEL790792 | NPNESEATSSE48742 | TEMU6774329 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204 | 25 | 676 | 26 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PIONEER NEW) CLOSED IN CELLO ON 7/9 | PIONEER - 2300 RT 1 North Brunswick, NJ 08902
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | BSIU9684180 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | FCIU8637232 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | SEGU5779090 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | TCNU4236005 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | TCNU6825391 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | ZCSU7052752 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | TCNU4248243 | Q.PLUS L-G4.2.5.A.F 350 | 30340711 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | ZCSU6504251 | Q.PLUS L-G4.2.5.A.F 350 | 30340711 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SHENZHEN | ZIMUSEL790812 | NPNESEATSSE48778 | ZCSU8921790 | Q.PLUS L-G4.2.5.A.F 350 | 30340711 | 25 | 638 | 22 | 2019-06-09 | 2019-07-03 |  |  | 2019-06-27 |  |  | 2019-07-10 |  |  | 2019-07-08 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | BMOU5187447 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | CAAU5138990 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | CAIU7451733 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | CAIU9974158 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | HMMU6004132 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | HMMU6212481 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | HMMU6269208 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | TCLU8035320 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | DFSU6605409 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SHANGHAI | HMDUMYWB0824152 | MY9050088201 | HMMU6195321 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-06-01 | 2019-07-06 |  |  | 2019-07-03 |  |  | 2019-07-11 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | CMAU4350995 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCNU3414843 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | BMOU6406051 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCKU6224565 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | CMAU5307458 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-15 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | APHU7133320 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | APHU6363191 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-15 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TEMU6308697 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCNU8410542 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | APHU7232766 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-15 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | CMAU7638630 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCNU9028051 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-15 |  |  | 2019-07-11 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCLU9586251 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | GESU6455465 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TGHU6377658 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TLLU5105090 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCNU2247340 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | ECMU9802811 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901007 | CMA CGM NORMA | CMDUAYN0532659 | SDSMY20190613-01 | TCNU9876047 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901008 | CMA CGM NORMA | CMDUAYN0532661 | SDSMY20190613-02 | CMAU7427133 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-15 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901008 | CMA CGM NORMA | CMDUAYN0532661 | SDSMY20190613-02 | ECMU9744320 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901008 | CMA CGM NORMA | CMDUAYN0532661 | SDSMY20190613-02 | ECMU9807937 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71901008 | CMA CGM NORMA | CMDUAYN0532661 | SDSMY20190613-02 | TCNU4202366 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901008 | CMA CGM NORMA | CMDUAYN0532661 | SDSMY20190613-02 | TGHU6294532 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-06-13 | 2019-07-09 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | AKLU6502400 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | BSIU9431639 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | CAIU8690012 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | DRYU9221936 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | FDCU0519233 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/16
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | GESU6231038 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-17 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | KKFU7830266 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | KKFU7961939 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | MOTU0777063 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-17 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | NYKU4303051 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | NYKU4339500 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | NYKU5985803 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-12 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCLU6695726 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCLU7769401 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-17 |  |  | 2019-07-15 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/16
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCLU7824263 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCLU8379619 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/16
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCNU4866350 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-17 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCNU8719362 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-17 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TCNU9464820 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/16
PSS | 71900049 | SEASPAN AMAZON | ONEYSELV59393800 | NPNESEATSSE48863 | TLLU5641153 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-15 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | GUTHORM MAERSK | ZIMUSEL791357 | NPNESEATSSE48822 | ZCSU8247722 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-16 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-15 |  | DELIVERED (PSS)
PSS | 71900049 | GUTHORM MAERSK | ZIMUSEL791357 | NPNESEATSSE48822 | TCNU4257899 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-16 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | GUTHORM MAERSK | ZIMUSEL791357 | NPNESEATSSE48822 | GAOU6046566 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-16 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | GUTHORM MAERSK | ZIMUSEL791357 | NPNESEATSSE48822 | TCNU2314027 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-16 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71900049 | GUTHORM MAERSK | ZIMUSEL791357 | NPNESEATSSE48822 | CAXU9198077 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-16 | 2019-07-10 |  |  | 2019-07-03 |  |  | 2019-07-16 |  |  | 2019-07-16 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SOFIA | HDMUMYNW0825657 | MY9060006001 | CAAU5144308 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-06-09 | 2019-07-13 |  |  | 2019-07-05 |  |  | 2019-07-18 |  |  | 2019-07-17 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SOFIA | HDMUMYNW0825657 | MY9060006001 | TGBU6340071 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-06-09 | 2019-07-13 |  |  | 2019-07-05 |  |  | 2019-07-18 |  |  | 2019-07-17 |  | DELIVERED (PSS)
PSS | 71901008 | MAERSK SOFIA | HDMUMYNW0825657 | MY9060006001 | SEGU5836815 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-06-09 | 2019-07-13 |  |  | 2019-07-05 |  |  | 2019-07-18 |  |  | 2019-07-17 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | SEGU4350768 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | NYKU0844037 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/31
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | CAIU8710973 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | NYKU5886159 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | TCLU5610597 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | TCLU5576240 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | DFSU6970823 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | ONEU0140800 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | KKFU8116818 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | MOTU1412012 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/31
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | TCLU8050243 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/31
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | DRYU9226265 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | TCNU4858272 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS)
PSS | 71900049 | ONE CONTRIBUTION | ONEYSELV57674800 | NPNESEATSSE48925 | TCNU5986154 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-26 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | BSIU9704029 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | DRYU9648131 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | FSCU8177347 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-31 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | GAOU6044687 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-26 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/28
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | SEGU5780819 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | TCNU2311856 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | TEMU6744617 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-26 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/28
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | TGBU5760573 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | UETU5274177 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-26 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/28
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | WFHU5198120 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | ZCSU6515488 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-26 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/28
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | ZCSU8476164 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | ZCSU8549764 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | ZCSU8849951 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-26 |  | DELIVERED (PSS) CLOSED IN CELLO ON 7/28
PSS | 71900049 | GJERTRUD MAERSK | ZIMUSEL791358 | NPNESEATSSE49035 | ZCSU8859970 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-06-30 | 2019-07-24 |  |  | 2019-07-18 |  |  | 2019-07-31 |  |  | 2019-07-29 |  | DELIVERED (PSS)
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MRKU4296893 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | SUDU8866731 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MSKU9841797 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MRKU4838443 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MSKU0849734 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-29 |  | DELIVERED (PSS) CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | TCLU5427499 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MRKU4377336 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-29 |  | DELIVERED (PSS) CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | CLHU8899450 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-30 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | MSKU1833157 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | AXEL MAERSK | MAEU583027103 | SDSMY20190627-01 | SUDU8799823 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-27 | 2019-07-27 |  |  | 2019-07-18 |  |  | 2019-08-01 |  |  | 2019-07-31 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | APHU6775780 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | APHU7335954 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | CMAU5334556 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | CMAU7638711 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | ECMU9924044 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | TGHU8856264 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | TGHU8868985 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | TGHU9532803 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | TLLU4517847 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71901012 | CMA CGM TAGE | CMDUAYN0536066 | SDSMY20190704-01 | TLLU5004828 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-07-04 | 2019-07-29 |  |  | 2019-07-23 |  |  | 2019-08-05 |  |  | 2019-08-02 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/4
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | CAIU9526600 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | DRYU9964206 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | KKFU8149302 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | NYKU4108760 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | NYKU4330329 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | NYKU4420968 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | NYKU5164407 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | TCLU5513405 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900049 | HUMEN BRIDGE | ONEYSELV57681600 | NPNESEATSSE49319 | TRLU7452170 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-06 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-06 |  |  | 2019-08-06 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SUZHOU | ZIMUSEL793327 | NPNESEATSSE49194 | CAIU4345321 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 493 | 17 | 2019-07-04 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-05 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SUZHOU | ZIMUSEL793327 | NPNESEATSSE49194 | CAIU4345321 | Q.PLUS L-G4.2.5.A.F 340 | 30340709 | 25 | 16 | 1 | 2019-07-04 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-05 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SUZHOU | ZIMUSEL793327 | NPNESEATSSE49194 | TCNU8770718 | Q.PLUS L-G4.2.5.A.F 345 | 30340710 | 25 | 609 | 21 | 2019-07-04 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-05 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SUZHOU | ZIMUSEL793327 | NPNESEATSSE49194 | TCNU6734990 | Q.PLUS L-G4.2.5.A.F 350 | 30340711 | 25 | 580 | 20 | 2019-07-04 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-05 |  | DELIVERED (PSS)
PSS | 71900040 | MAERSK SUZHOU | ZIMUSEL793327 | NPNESEATSSE49194 | TCNU6734990 | Q.PLUS L-G4.2.5.A.F 350 | 30340711 | 25 | 6 | 1 | 2019-07-04 | 2019-07-31 |  |  | 2019-07-23 |  |  | 2019-08-07 |  |  | 2019-08-05 |  | DELIVERED (PSS)
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU3676060 | Q.PLUS DUO L-G5.2 365 | 12002196STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-06 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MSKU8784692 | Q.PLUS DUO L-G5.2 365 | 12002196STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-06 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | CAIU8410451 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | FCIU8311884 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | GVCU5349498 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | HASU4322824 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU2086497 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU2323140 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU2464724 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU2483426 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU3070812 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/13 DUE TO PALLET ISSUE; CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU3999206 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU4492474 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU4602777 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-10 |  |  | 2019-08-12 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU4922261 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS) CLOSED IN CELLO ON 8/13 DUE TO PALLET ISSUE; CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU5026505 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MRKU5479498 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MSKU1335513 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-12 |  |  | 2019-08-12 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MSKU1801967 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MSKU1826440 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | MSKU9236420 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-08 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | SUDU6584868 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | MAEU583131689 | SDSMY20190630-05 | SUDU8601028 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | SSPHPKL8051943 | SDSMY20190630-03 | GCXU5083762 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | SSPHPKL8051943 | SDSMY20190630-03 | SEGU5428222 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-09 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | SSPHPKL8051943 | SDSMY20190630-03 | TCNU4634396 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901012 | MAERSK KARACHI | SSPHPKL8051943 | SDSMY20190630-03 | TLLU4872271 | Q.PLUS DUO L-G5.2 360 | 12002197STRA | 25 | 638 | 22 | 2019-06-30 | 2019-08-02 |  |  | 2019-07-29 |  |  | 2019-08-08 |  |  | 2019-08-07 |  | DELIVERED (PSS); CELL# 11CSTRA25
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU5726578 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU7337805 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | TCNU7485608 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | TCNU8492540 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU5302055 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | ECMU9770479 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | GESU6183074 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | MAGU5334134 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-21 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | TCKU6313003 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU4697140 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU4773066 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | CMAU7015711 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | DRYU9094981 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | GESU5598013 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71901014 | APL YANGSHAN | CMDUAYN0538438 | SDSMY20190725-01 | TCNU6992819 | Q.PLUS DUO L-G5.2 355 | 12002198 | 25 | 638 | 22 | 2019-07-25 | 2019-08-19 |  |  | 2019-08-12 |  |  | 2019-08-23 |  |  | 2019-08-22 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TLLU5306263 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | ZCSU8934478 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | ZCSU7039940 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TLLU4942229 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TGBU5769307 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TCNU6823130 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TLLU4586909 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-26 |  | DELIVERED (PSS)
PSS | 71900054 | GERD MAERSK | ZIMUSEL795712 | NPNESEATSSE49845 | TLLU4304306 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900060 | GERD MAERSK | ZIMUSEL796831 | NPNESEATSSE49846 | TLLU4949394 | Q.PEAK L-G4.2.1.F 365 | 30320514 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900060 | GERD MAERSK | ZIMUSEL796831 | NPNESEATSSE49846 | ZCSU7102494 | Q.PEAK L-G4.2.1.F 365 | 30320514 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900060 | GERD MAERSK | ZIMUSEL796831 | NPNESEATSSE49846 | TCNU8721009 | Q.PEAK L-G4.2.1.F 365 | 30320514 | 25 | 348 | 12 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900060 | GERD MAERSK | ZIMUSEL796831 | NPNESEATSSE49846 | TCNU8721009 | Q.PEAK L-G4.2.1.F 375 | 30320516 | 25 | 290 | 10 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900060 | GERD MAERSK | ZIMUSEL796831 | NPNESEATSSE49846 | ZCSU8932433 | Q.PEAK L-G4.2.1.F 375 | 30320516 | 25 | 638 | 22 | 2019-07-28 | 2019-08-21 |  |  | 2019-08-13 |  |  | 2019-08-28 |  |  | 2019-08-23 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | BMOU4508861 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | DFSU6305079 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | DFSU6534706 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | FCIU8641356 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | GAOU6082780 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | GAOU6085480 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU2525333 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-03 |  | DELIVERED (PSS) CLOSED OUT IN CELLO 9/4
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU2728259 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU2975156 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU4254591 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU5636773 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU6393410 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU8185966 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU8188522 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TCNU8539099 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TGBU5773760 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TGHU9745389 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | TLLU4312467 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU6510906 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU6522532 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU7065596 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8429007 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8516544 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8521880 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8635950 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8659822 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-08-30 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8733010 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71900054 | ARTHUR MAERSK | ZIMUSEL795235 | NPNESEATSSE49878 | ZCSU8771410 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-04 | 2019-08-28 |  |  | 2019-08-20 |  |  | 2019-09-04 |  |  | 2019-09-05 |  | DELIVERED (PSS)
PSS | 71901014 | CMA CGM FIDELIO | CMDUAYN0539490 | SDSMY20190808-01 | TCNU6900751 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-08-08 | 2019-09-03 |  |  | 2019-08-26 |  |  | 2019-09-09 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71901014 | CMA CGM FIDELIO | CMDUAYN0539490 | SDSMY20190808-01 | CMAU6010865 | Q.PLUS DUO L-G5.2 360 | 12002197 | 25 | 638 | 22 | 2019-08-08 | 2019-09-03 |  |  | 2019-08-26 |  |  | 2019-09-09 |  |  | 2019-09-04 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8427196 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-10 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8485504 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | TCKU6561397 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8256128 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | BSIU9683604 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | BMOU4505013 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS) CLOSED IN CELLO ON 9/10
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | TCNU8752627 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-09 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | TCNU2756902 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | TDRU5890552 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8446540 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | DRYU9017250 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8602940 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8941076 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-11 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | TCNU8238496 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71900054 | GRETE MAERSK | ZIMUSEL795236 | NPNESEATSSE50043 | ZCSU8240081 | Q.PEAK L-G4.2.1.F 370 | 30320515 | 25 | 638 | 22 | 2019-08-11 | 2019-09-04 |  |  | 2019-08-27 |  |  | 2019-09-11 |  |  | 2019-09-10 |  | DELIVERED (PSS)
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | CMAU4104693 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | CMAU4178021 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | CMAU5021989 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | CMAU5324624 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | GESU6694515 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-20 |  |  | 2019-09-18 |  | DELIVERED (PSS)
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | SEGU6059113 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-20 |  |  | 2019-09-18 |  | DELIVERED (PSS)
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | TCNU3235560 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901018 | CMA CGM LOIRE | CMDUAYN0541027 | SDSMY20190822-03 | TEMU7783027 | Q.PLUS DUO L-G5.2 355 | 12002141 | 25 | 638 | 22 | 2019-08-22 | 2019-09-16 |  |  | 2019-09-09 |  |  | 2019-09-23 |  |  | 2019-09-19 |  | DELIVERED (PSS) CLOSED IN CELLO 9/20
PSS | 71901016 | CMA CGM LIBRA | CMDUAYN0541028 | SDSMY20190830-01 | BMOU6414519 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-08-31 | 2019-10-03 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-08 |  | DELIVERED (PSS)
PSS | 71901016 | CMA CGM LIBRA | CMDUAYN0541028 | SDSMY20190830-01 | CMAU4479489 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-08-31 | 2019-10-03 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-08 |  | DELIVERED (PSS)
PSS | 71901016 | CMA CGM LIBRA | CMDUAYN0541028 | SDSMY20190830-01 | CMAU7448579 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-08-31 | 2019-10-03 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-08 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TEMU6769195 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TCNU8779103 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8664243 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | FSCU8220187 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8787269 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | CRSU9078958 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TGBU7088365 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TCNU8779314 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8802363 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | FCIU8707725 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8662908 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8601369 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TCLU5263836 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TEMU6756644 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU8614371 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | DFSU6949549 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | CRSU9071125 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-08 |  |  | 2019-10-04 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | BSIU9678059 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | TCNU8782724 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS | 71900065 | MEARSK YUKON | ZIMUSEL7000862 | NPNESEATSSE50681 | ZCSU6536937 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-09-08 | 2019-10-02 |  |  | 2019-09-25 |  |  | 2019-10-09 |  |  | 2019-10-07 |  | DELIVERED (PSS)
PSS |  | CHR | CHR |  |  | Packing Materials-box, lid, pallets, paddings, 30sets | [5 empty] | 2019-10-28 | [8 empty] | 2019-10-30 |  | DELIVERED (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | GAOU6188154 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | HDMU6645903 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | SEGU6022789 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | CAIU9843899 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | BMOU5182912 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/20 (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | CAIU9962809 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/20 (PSS)
PSS | 71901024 | MAERSK KAWASAKI | HDMUMYWB0840898 | SDSMY20191011-02 | TCNU4316538 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-12 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-19 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/20 (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | HMMU6231500 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-22 |  |  | 2019-11-19 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/20 (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | KOCU4045150 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/21 (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | HMMU6068179 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | TCNU7418847 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/21 (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | TCNU6024052 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | TCLU9897926 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | CAIU7436220 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | TEMU7318730 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | SEGU5851830 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/21 (PSS)
PSS | 71901024 | ARTHUR MAERSK | HDMUMYWB0841533 | SDSMY20191019-02 | HDMU6817005 | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 638 | 22 | 2019-10-19 | 2019-11-16 |  |  | 2019-11-11 |  |  | 2019-11-21 |  |  | 2019-11-20 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/21 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | KOCU4220210 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-25 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/26 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | BSIU9265076 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-25 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/26 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | BMOU4709660 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-25 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/26 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | HDMU6890135 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-25 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/26 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | HMMU6006433 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-25 |  | DELIVERED PAPERWORK RCVD & CLOSED IN CELLO ON 11/26 (PSS)
PSS | 71901024 | MAERSK SALTORO | HDMUMYWB0841537 | SDSMY20191019-03 | CAIU8246800 | Q.PLUS DUO L-G5.2 365 | 12002139 | 25 | 638 | 22 | 2019-10-19 | 2019-11-22 |  |  | 2019-11-18 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | MAERSK SANTANA | HDMUMYWB0842295 | SDSMY20191026-03 | BMOU4147429 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-23 |  |  | 2019-11-15 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | MAERSK SANTANA | HDMUMYWB0842295 | SDSMY20191026-03 | CAIU7232925 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-23 |  |  | 2019-11-15 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | MAERSK SANTANA | HDMUMYWB0842295 | SDSMY20191026-03 | TEMU7416802 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-23 |  |  | 2019-11-15 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | MAERSK SANTANA | HDMUMYWB0842295 | SDSMY20191026-03 | HDMU6854009 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-23 |  |  | 2019-11-15 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | MAERSK SANTANA | HDMUMYWB0842295 | SDSMY20191026-03 | HMMU6056162 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-23 |  |  | 2019-11-15 |  |  | 2019-11-29 |  |  | 2019-11-26 |  | DELIVERED (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | FSCU7998306 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-02 |  |  | 2019-11-27 |  | DELIVERED (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | CAIU8945371 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-02 |  |  | 2019-11-27 |  | DELIVERED (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | SEGU4359662 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-02 |  |  | 2019-11-27 |  | DELIVERED CLOSED IN CELLO ON 11/29 (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | CCLU7725114 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-03 |  |  | 2019-11-27 |  | DELIVERED CLOSED IN CELLO ON 11/29 (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | DFSU6182591 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-02 |  |  | 2019-11-27 |  | DELIVERED CLOSED IN CELLO ON 11/29 (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | OOLU9327115 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-03 |  |  | 2019-11-27 |  | DELIVERED CLOSED IN CELLO ON 12/02 (PSS)
PSS | 71901026 | CMA CGM CHENNAI | COSU6221734400 | SDSMY20191030-05 | FSCU8691700 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-25 |  |  | 2019-11-19 |  |  | 2019-12-03 |  |  | 2019-11-27 |  | DELIVERED CLOSED IN CELLO ON 11/29 (PSS)
PSS | 71901026 | SANTA TERESA | HDMUMYWB0842298 | SDSMY20191026-04 | KOCU4278845 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-29 |  |  | 2019-11-20 |  |  | 2019-12-05 |  |  | 2019-12-03 |  | DELIVERED (PSS)
PSS | 71901026 | SANTA TERESA | HDMUMYWB0842298 | SDSMY20191026-04 | HMMU6006449 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-29 |  |  | 2019-11-20 |  |  | 2019-12-05 |  |  | 2019-12-03 |  | DELIVERED (PSS)
PSS | 71901026 | SANTA TERESA | HDMUMYWB0842298 | SDSMY20191026-04 | CAIU4427250 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-29 |  |  | 2019-11-20 |  |  | 2019-12-05 |  |  | 2019-12-03 |  | DELIVERED (PSS)
PSS | 71901026 | SANTA TERESA | HDMUMYWB0842298 | SDSMY20191026-04 | KOCU4061232 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-29 |  |  | 2019-11-20 |  |  | 2019-12-05 |  |  | 2019-12-03 |  | DELIVERED (PSS)
PSS | 71901026 | SANTA TERESA | HDMUMYWB0842298 | SDSMY20191026-04 | HMMU6129206 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-26 | 2019-11-29 |  |  | 2019-11-20 |  |  | 2019-12-05 |  |  | 2019-12-03 |  | DELIVERED (PSS)
PSS | 71901026 | CORNELIA MAERSK | HDMUMYWB0842539 | SDSMY20191031-04 | BSIU9264866 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-30 |  |  | 2019-11-22 |  |  | 2019-12-05 |  |  | 2019-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/05 (PSS)
PSS | 71901026 | CORNELIA MAERSK | HDMUMYWB0842539 | SDSMY20191031-04 | CAIU8922036 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-30 |  |  | 2019-11-22 |  |  | 2019-12-05 |  |  | 2019-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/05 (PSS)
PSS | 71901026 | CORNELIA MAERSK | HDMUMYWB0842539 | SDSMY20191031-04 | HDMU6758941 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-30 |  |  | 2019-11-22 |  |  | 2019-12-05 |  |  | 2019-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/05 (PSS)
PSS | 71901026 | CORNELIA MAERSK | HDMUMYWB0842539 | SDSMY20191031-04 | HMMU6204655 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-30 |  |  | 2019-11-22 |  |  | 2019-12-05 |  |  | 2019-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/05 (PSS)
PSS | 71901026 | CORNELIA MAERSK | HDMUMYWB0842539 | SDSMY20191031-04 | TCNU7406790 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-11-30 |  |  | 2019-11-22 |  |  | 2019-12-05 |  |  | 2019-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/05 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787380 | SDSMY20191106-01 | DFSU7451709 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787380 | SDSMY20191106-01 | CSLU6146607 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | CCLU7458661 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | BMOU4941660 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | OOLU8446995 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | TCNU3228371 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | BSIU9566573 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | FCIU9534732 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | FCIU9619510 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | CCLU7359041 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-05 |  | DELIVERED CLOSED IN CELLO ON 12/06 (PSS)
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | CCLU7256790 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | TGCU5052726 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | DFSU6079304 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | TGHU6642535 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | FSCU8459715 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | FSCU8579855 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM TAGE | COSU6221787990 | SDSMY20191106-02 | CBHU9565421 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-08 | 2019-12-03 |  |  | 2019-11-26 |  |  | 2019-12-09 |  |  | 2019-12-06 |  | DELIVERED CLOSED IN CELLO ON 12/09 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172381 | SHTC19110081 | BEAU5214105 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 609 | 21 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-10 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172381 | SHTC19110081 | BEAU5214105 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 16 | 1 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-10 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172381 | SHTC19110081 | MRKU5579666 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172381 | SHTC19110081 | MRKU3034538 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 638 | 22 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-10 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | MSKU0260282 | Q.PEAK DUO L G5.2.0.V 380 | 30361017 | 25 | 19 | 1 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | MSKU0260282 | Q.PEAK DUO L G5.2.0.V 380 | 30361017 | 25 | 3 | 1 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | MSKU0260282 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 232 | 8 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | MSKU0260282 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 18 | 1 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | FCIU8906100 | Q.PEAK DUO L G5.2.0.V 385 | 30361018 | 25 | 638 | 22 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71900077 | MAERSK SHENZHEN | SUDUN9SOL0172401 | SHTC19110082 | MRKU2420114 | Q.PEAK DUO L G5.2.0.V 385 | 30361018 | 25 | 638 | 22 | 2019-11-10 | 2019-12-04 |  |  | 2019-11-26 |  |  | 2019-12-11 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCNU6371977 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU5153568 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TGBU5300053 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4928558 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU0849912 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCLU1789946 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4763150 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4861449 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | DFSU6774564 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | SEGU5857783 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU0762828 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCNU5248103 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED (PSS-Cell#11C25) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | MOTU0644076 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED (PSS-Cell#11C25) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCNU4278470 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED (PSS-Cell#11C25) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4238676 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED (PSS-Cell#11C25) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | CXDU1282888 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED (PSS-Cell#11C25) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCLU1694178 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCNU4837304 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | GESU6546610 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-09 |  | DELIVERED CLOSED IN CELLO ON 12/10 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCNU9486753 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-10 |  | DELIVERED CLOSED IN CELLO ON 12/11 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | KKFU7646942 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4074551 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | NYKU4934519 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | MOTU1421164 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | ANTWERPEN EXPRESS | ONEYPKGV47395900 | SDSMY20191031-06 | TCLU9300732 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-06 |  |  | 2019-11-26 |  |  | 2019-12-12 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | MAERSK KLEVEN | HDMUMYWB0842798 | SDSMY20191031-05 | GAOU6175732 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-11-27 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | MAERSK KLEVEN | HDMUMYWB0842798 | SDSMY20191031-05 | KOCU4114179 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-11-27 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | MAERSK KLEVEN | HDMUMYWB0842798 | SDSMY20191031-05 | DFSU6248868 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-11-27 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | MAERSK KLEVEN | HDMUMYWB0842798 | SDSMY20191031-05 | HMMU6287536 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-11-27 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | MAERSK KLEVEN | HDMUMYWB0842798 | SDSMY20191031-05 | DFSU6201583 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-11-27 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | MAGU5249710 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CBHU8991382 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CCLU7724653 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | OOLU8271855 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | BMOU5239406 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | TCNU7641927 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | BSIU9575410 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CCLU6865390 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CBHU9522271 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | MAGU5648602 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | FCIU9593226 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | GLDU7537498 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | BMOU4845116 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CSNU6964600 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | OOLU6894223 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | CMA CGM AMAZON | COSU6221769180 | SDSMY20191113-01 | CBHU7035119 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-13 |  | DELIVERED CLOSED IN CELLO ON 12/16 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | MAGU5526501 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | DFSU6642315 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | FCIU8455500 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | CSNU6278998 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | CBHU8664034 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | FCIU9476765 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | CBHU8784723 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | CMA CGM AMAZON | COSU6221763150 | SDSMY20191113-02 | CSLU6021847 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | TCNU8857680 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | CCLU7486621 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | CCLU7158031 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | TGHU8780636 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | UETU5350560 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | TGHU9141624 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM AMAZON | COSU6221788640 | SDSMY20191113-03 | CCLU6531562 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-15 | 2019-12-10 |  |  | 2019-12-05 |  |  | 2019-12-16 |  |  | 2019-12-12 |  | DELIVERED CLOSED IN CELLO ON 12/13 (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CBHU8722450 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-18 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CBHU8794249 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-17 |  | DELIVERED AND CLOSED IN CELLO ON 12/18 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CBHU8904285 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-18 |  |  | 2019-12-17 |  | DELIVERED AND CLOSED IN CELLO ON 12/18 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CCLU6989302 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CCLU7039449 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CCLU7180930 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-17 |  | DELIVERED AND CLOSED IN CELLO ON 12/18 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CCLU7269729 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | FCIU9705769 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-18 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | FSCU7266012 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-17 |  | DELIVERED AND CLOSED IN CELLO ON 12/18 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | CSLU6328833 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | FSCU8556628 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-18 |  |  | 2019-12-17 |  | DELIVERED AND CLOSED IN CELLO ON 12/18 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | OOLU9480377 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | TCNU8618161 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-17 |  |  | 2019-12-16 |  | DELIVERED AND CLOSED IN CELLO 12/17 (PSS 7) | PSS-7 NICHOLAS COURT
PSS | 71901026 | OOCL POLAND | COSU6221759530 | SDSMY20191031-03 | TGHU9830290 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-10-31 | 2019-12-10 |  |  | 2019-12-04 |  |  | 2019-12-16 |  |  | 2019-12-11 |  | DELIVERED CLOSED IN CELLO ON 12/12 (PSS 11) | PSS-11C NICHOLAS COURT
PSS | 71900088 | EXPRESS BERLIN | YMLUE360774099 | SHTC19110234 | SEGU4585952 | Q.PEAK BLK-G4.1.2.F 305 | 30315202 | 25 | 832 | 26 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900088 | EXPRESS BERLIN | YMLUE360774099 | SHTC19110234 | YMMU6082425 | Q.PEAK BLK-G4.1.2.F 305 | 30315202 | 25 | 304 | 10 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | BEAU4844840 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 319 | 11 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | BEAU4844840 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 21 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | BEAU4844840 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 11 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | BEAU4844840 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 20 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | MAGU5651355 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 638 | 22 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | MAGU5776603 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 638 | 22 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TEMU7014742 | Q.PEAK DUO L G5.2.0.V 405 | 30361057 | 25 | 87 | 3 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TEMU7014742 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 551 | 19 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TCNU4638154 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 638 | 22 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TGBU5550941 | Q.PEAK DUO L G5.2.0.V 395 | 30361055 | 25 | 493 | 17 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TGBU5550941 | Q.PEAK DUO L G5.2.0.V 395 | 30361055 | 25 | 4 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TGBU5550941 | Q.PEAK DUO L G5.2.0.V 385 | 30361018 | 25 | 4 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TGBU5550941 | Q.PEAK DUO L G5.2.0.V 385 | 30361018 | 25 | 2 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | TGBU5550941 | Q.PEAK DUO L G5.2.0.V 390 | 30361019 | 25 | 21 | 1 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900089 | EXPRESS BERLIN | YMLUE360774092 | SHTC19110236 | YMLU9027135 | Q.PEAK DUO L G5.2.0.V 400 | 30361056 | 25 | 638 | 22 | 2019-11-23 | 2019-12-21 |  |  | 2019-12-10 |  |  | 2019-12-30 |  |  | 2019-12-26 |  | DELIVERED CLOSED IN CELLO ON 12/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | BMOU4398770 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | BSIU9550983 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | CCLU7136011 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | CCLU7809508 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | CSLU6330091 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | CSNU6346599 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | CSNU6830319 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | DFSU7384909 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | FSCU8713938 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | MAGU5568282 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | OOCU6855365 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | OOCU6985230 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | OOLU9243420 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | OOLU9403832 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | TCNU3994398 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901029 | APL YANGSHAN | COSU6221786800 | SDSMY20191128-06 | TEMU6287948 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED CLOSED IN CELLO ON 12/30 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CAIU9121582 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CAIU9719960 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED CLOSED IN CELLO ON 12/30 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CBHU8780327 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CBHU9098477 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CCLU7845790 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CSLU6151624 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CSNU6031713 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | CSNU6607732 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | FCIU9867380 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | MAGU5263750 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOCU6933302 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOCU7852057 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOLU8760033 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOLU8901738 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOLU8917903 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | OOLU9392810 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | TGBU5966625 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | TGHU9282896 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786810 | SDSMY20191128-07 | TLLU4501305 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | BMOU4615664 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | BSIU9227029 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | BSIU9640639 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CAIU7035211 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CBHU8564415 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CBHU8745563 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED CLOSED IN CELLO ON 12/30 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CBHU8783352 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CBHU9590888 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CCLU7039897 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CCLU7384430 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CCLU7491145 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CCLU7659368 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CSLU6056376 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CSLU6242180 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CSNU6197216 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | CSNU6444189 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED CLOSED IN CELLO ON 12/30 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | FCIU9669023 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | MAGU5531621 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | OOLU8472654 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | OOLU8718748 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | TCNU1072150 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-27 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | TCNU1077255 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | TEMU6295440 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | TEMU7727240 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | UETU5266696 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-30 |  | DELIVERED CLOSED IN CELLO ON 12/31 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | APL YANGSHAN | COSU6221786820 | SDSMY20191128-05 | UETU5357203 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-11-29 | 2019-12-24 |  |  | 2019-12-16 |  |  | 2020-01-03 |  |  | 2019-12-31 |  | DELIVERED (PSS 11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | BMOU5670455 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | BSIU9425596 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CBHU9002346 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CBHU9016606 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CCLU7014311 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CSNU6080066 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CSNU6082310 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | CSNU6317369 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | FCIU9919797 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | FSCU8823236 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | MAGU5210072 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | OOLU8886090 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | OOLU9497960 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | OOLU9606911 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | RFCU4018317 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | RFCU4084725 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | TGHU6539759 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901030 | CMA CGM IVANHOE | COSU6221790180 | SDSMY20191204-01 | WBPU7038907 | Q.PEAK DUO L-G5.2 395 | 12002651 | 25 | 638 | 22 | 2019-12-05 | 2019-12-30 |  |  | 2019-12-23 |  |  | 2019-01-07 |  |  | 2020-01-06 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | DRYU9532753 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | FFAU1474286 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | KKFU7809850 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | NYKU4782186 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | NYKU4852030 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | NYKU5953386 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | ONEU0275637 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCLU6733765 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCNU2805611 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCNU3075457 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCNU5952323 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TGHU6114498 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TLLU4210911 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | GCXU5205243 | Q.PEAK L-G4.2.0.F 375 | 30320116 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TLLU4615925 | Q.PEAK L-G4.2.0.F 375 | 30320116 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | KKFU7526470 | Q.PEAK L-G4.2.0.F 365 | 30320114 | 25 | 638 | 22 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | ONEU0306996 | Q.PEAK L-G4.2.0.F 365 | 30320114 | 25 | 35 | 2 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | ONEU0306996 | Q.PEAK L-G4.2.0.F 370 | 30320115 | 25 | 108 | 4 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | ONEU0306996 | Q.PEAK L-G4.2.0.F 375 | 30320116 | 25 | 49 | 2 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCLU8923872 | Q.PEAK L-G4.2.0.F 365 | 30320114 | 25 | 290 | 10 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900092 | SEASPAN THAMES | ONEYSELVD2527600 | SHTC19120062 | TCLU8923872 | Q.PEAK L-G4.2.0.F 375 | 30320116 | 25 | 348 | 12 | 2019-12-12 | 2019-01-06 |  |  | 2019-12-30 |  |  | 2020-01-13 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | BSIU9705940 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | CAIU4302891 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | CAIU4423023 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | FCIU8638727 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | GAOU6097650 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | SEGU5762625 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCKU6014424 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU1823884 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU2314813 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU2501809 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU2752785 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/17
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU2760991 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU4579787 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU5832544 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU5840977 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU6393364 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU8391458 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU8542071 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TEMU6747468 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGBU5412264 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGBU5412346 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGBU5497343 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGBU5958790 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGBU5959729 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-17 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TGCU5079558 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TLLU5915336 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | UETU5270248 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU6513398 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU6529080 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU6531832 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU6538462 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU7002617 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-16 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU7077093 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU7127126 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-15 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/16
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU7134845 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU8478995 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU8514201 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-18 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/20
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU8585170 | Q.PLUS L-G4.2.5 AF 345 | 12001374 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | TCNU8531518 | Q.PLUS L-G4.2.5 AF 345 | 12001375 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71801010 | MAERSK KAWASAKI | SSPHPKL8044100 | SDSMY20181128-01 | ZCSU8994543 | Q.PLUS L-G4.2.5 AF 345 | 12001375 | 30 | 638 | 22 | 2018-11-28 | 2019-01-11 |  |  | 2019-01-02 |  |  | 2019-01-17 |  |  | 2019-01-21 |  | DELIVERED (PNCW) CLOSED IN CELLO 1/22
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TGHU9358585 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TCNU9011634 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | DRYU9648260 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | BSIU9702767 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU7038076 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU7015933 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TCNU1061731 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TEMU6745568 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TCNU4250235 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | DFSU6538661 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8734720 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8626388 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | BSIU9217674 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8548325 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | CAIU9220646 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU7083959 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-08 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8754964 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | TCNU5832987 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | DRYU9054973 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8663000 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8943696 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8652181 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | UESU5212459 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | DRYU9649420 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8257084 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8582891 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8546322 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | AMFU8917216 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8625503 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-10 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | FCIU8250346 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8259209 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8723990 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | MAERSK SEMAKAU | SSPHPKL8047949 | SDSMY20190331-01 | ZCSU8364708 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-03-31 | 2019-05-06 |  |  | 2019-04-29 |  |  | 2019-05-13 |  |  | 2019-05-09 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5005252 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | FCIU8065796 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | APHU6631191 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TGHU8966810 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TCNU9706499 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | ECMU9470255 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU4902522 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TCKU9742151 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TCNU5777410 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | FCIU8663606 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5835943 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CNCU5505008 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5140967 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | APHU6386690 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5553873 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | APHU6480330 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TRLU6987455 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5532443 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CAIU9671980 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TGHU6099963 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | GESU6454664 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-16 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5239477 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | HJMU1923406 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TRLU7553900 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5910414 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-16 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | ECMU9916809 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | TCNU4294589 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU4212471 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | SEGU6059371 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM ORFEO | CMDUAYN0524490 | SDSMY20190411-01 | CMAU5093417 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-11 | 2019-05-10 |  |  | 2019-05-03 |  |  | 2019-05-16 |  |  | 2019-05-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8779833 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-15 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8852929 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | TEMU6751405 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8660546 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8932480 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8903707 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | BSIU9770360 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | OWLU5512404 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | GAOU6076920 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8729344 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | DFSU6534199 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | ZCSU8239075 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-13 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/14
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | SEGU5281698 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-15 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | TEMU6620318 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71900031 | SEAMAX STRATFORD | ZIMUSEL784873 | NPNESEATSSE47495 | TCNU5350922 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-12 | 2019-05-10 |  |  | 2019-05-06 |  |  | 2019-05-17 |  |  | 2019-05-14 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/15
NORFOLK, VA | 71901003 | CAP ARNAUTI | SSPHPKL8048859 | SDSMY20190402-01 | ZCSU8245205 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-04 | 2019-05-13 |  |  | 2019-05-08 |  |  | 2019-05-20 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | CAP ARNAUTI | SSPHPKL8048859 | SDSMY20190402-01 | DRYU9113839 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-04 | 2019-05-13 |  |  | 2019-05-08 |  |  | 2019-05-20 |  |  | 2019-05-16 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901003 | CAP ARNAUTI | SSPHPKL8048859 | SDSMY20190402-01 | AXIU1665250 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-04 | 2019-05-13 |  |  | 2019-05-08 |  |  | 2019-05-20 |  |  | 2019-05-16 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CAP ARNAUTI | SSPHPKL8048483 | SDSMY20190407-01 | TCNU5369070 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-07 | 2019-05-13 |  |  | 2019-05-08 |  |  | 2019-05-20 |  |  | 2019-05-16 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CAP ARNAUTI | SSPHPKL8048483 | SDSMY20190407-01 | ZCSU8754368 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-07 | 2019-05-13 |  |  | 2019-05-08 |  |  | 2019-05-20 |  |  | 2019-05-15 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8515229 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8679623 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU8675834 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | FCIU8921167 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | FCIU8953903 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU8673003 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8717472 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8451145 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | FCIU8640299 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | BSIU9696598 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8947979 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/23
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8668104 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | BSIU9574645 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8982270 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | BSIU9705067 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8816860 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU5366214 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU5501079 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8939464 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU7128098 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU7009083 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU4420100 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TCNU8674252 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU8710396 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | TEMU6675497 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | BEAU5047271 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/23
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | FSCU8097200 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | DFSU6603155 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | CAIU8871176 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-20 |  | DELIVERED (PNCW) CLOSED IN CELLO 5/21
NORFOLK, VA | 71900031 | MAERSK SURABAYA | ZIMUSEL784874 | NPNESEATSSE47530 | ZCSU7028801 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-09 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/22
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TGHU6185486 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TCNU6998864 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU6490241 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU7176317 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU6388902 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU6410230 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU7225664 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TCNU7910728 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | FCIU9379050 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU6509692 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TRLU5932735 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TGHU9707650 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TLLU4391147 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CAIU9672630 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | HCIU8021470 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TEMU6607424 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU4250471 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | AMFU8865663 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | BMOU5908008 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-21 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TRLU7036595 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | GESU5459949 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | GESU5775865 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | TCLU8044322 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | APHU6560842 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | GESU6180429 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU4107476 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | GESU5538924 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-23 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU5980690 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | ECMU9805019 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU7696071 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU4057420 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-22 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM LOIRE | CMDUAYN0526384 | SDSMY20190418-01 | CMAU7621112 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-19 | 2019-05-17 |  |  | 2019-05-10 |  |  | 2019-05-23 |  |  | 2019-05-23 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU7024719 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8505257 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8894098 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | CAIU9230602 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU7080498 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | BMOU4509683 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU6524089 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8887627 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8730983 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8696997 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | CRSU9069827 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | CAIU8766545 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8259615 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-24 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | ZCSU8623265 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | MAERSK KARACHI | SSPHPKL8049216 | SDSMY20190416-01 | TCNU8888017 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-16 | 2019-05-20 |  |  | 2019-05-13 |  |  | 2019-05-28 |  |  | 2019-05-23 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU6421873 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU6441226 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU6677443 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU6810751 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU6948252 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | APHU7114254 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | BSIU9282284 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CAIU9300340 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU4069761 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU4133259 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU4304520 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU4368715 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU5133150 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU5565750 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU5587600 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU5823114 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CMAU5960734 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | CRXU9263794 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | ECMU9465623 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | ECMU9923310 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-28 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | GESU5580647 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | GLDU9950242 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TCLU8617804 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-30 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TCNU9148709 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TCNU9740180 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-30 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TEMU6318000 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-06-03 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TLLU4398584 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TLLU4511659 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TRLU7341686 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TRLU7433530 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | TRLU8252979 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | CMA CGM RHONE | CMDUAYN0526403 | SDSMY20190425-01 | UETU5512296 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-25 | 2019-05-23 |  |  | 2019-05-17 |  |  | 2019-05-30 |  |  | 2019-05-29 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71900031 | GUDRUN MAERSK | HDMUBUWB4891273 | NPNESEATSSE47869 | TLLU5849804 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-28 | 2019-05-25 |  |  | 2019-05-22 |  |  | 2019-05-31 |  |  | 2019-05-29 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/30
NORFOLK, VA | 71900031 | GUDRUN MAERSK | HDMUBUWB4891273 | NPNESEATSSE47869 | HDMU6680191 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-28 | 2019-05-25 |  |  | 2019-05-22 |  |  | 2019-05-31 |  |  | 2019-05-29 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/30
NORFOLK, VA | 71900031 | GUDRUN MAERSK | HDMUBUWB4891273 | NPNESEATSSE47869 | FSCU8509230 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-28 | 2019-05-25 |  |  | 2019-05-22 |  |  | 2019-05-31 |  |  | 2019-05-28 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/29
NORFOLK, VA | 71900031 | GUDRUN MAERSK | HDMUBUWB4891273 | NPNESEATSSE47869 | TCNU5219907 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-28 | 2019-05-25 |  |  | 2019-05-22 |  |  | 2019-05-31 |  |  | 2019-05-29 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | GUDRUN MAERSK | HDMUBUWB4891273 | NPNESEATSSE47869 | HMMU6114356 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-28 | 2019-05-25 |  |  | 2019-05-22 |  |  | 2019-05-31 |  |  | 2019-05-29 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/30
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | HDMUBUWB4890885 | NPNESEATSSE47803 | TEMU7289631 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | HDMUBUWB4890885 | NPNESEATSSE47803 | DFSU6480148 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | HDMUBUWB4890885 | NPNESEATSSE47803 | TCNU5064214 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | HDMUBUWB4890885 | NPNESEATSSE47803 | HMMU6082201 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | HDMUBUWB4890885 | NPNESEATSSE47803 | CAXU9338380 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TDRU5902680 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7121386 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8694063 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU5956083 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8604178 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | DFOU8030572 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8607069 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8836569 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7039051 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU2975388 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/4
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8452835 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8643030 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU5368198 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW) CLOSED IN CELLO 6/3
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8636658 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | CRSU9071526 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW) CLOSED IN CELLO 6/3
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | SEGU5808346 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | AMFU8869442 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | BSIU9686389 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU5757712 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU6528124 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU5370560 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7025274 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | BSIU9696896 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8528247 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8530542 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8532165 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8971430 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU5646555 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7088637 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/10
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU5501567 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8554170 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7070920 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | BMOU4656236 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | FCIU8911873 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TLLU4770454 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU6522487 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7088035 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7028210 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU7003871 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU2791713 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU1832459 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | CAIU7943585 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU2501603 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | GCXU5072393 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU6523307 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8953647 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU8184677 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7088302 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | RFCU5011322 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW) CLOSED IN CELLO 6/3
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7080214 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW) CLOSED IN CELLO 6/3
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | CAXU8233677 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | ZCSU8958778 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TCNU5416439 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | FCIU8643657 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | FSCU8149427 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7133633 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7061805 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TLLU4592352 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | CRSU9052629 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-03 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | COLUMBINE MAERSK | ZIMUSEL784875 | NPNESEATSSE47686 | TGBU7211510 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-04-26 | 2019-05-28 |  |  | 2019-05-17 |  |  | 2019-06-04 |  |  | 2019-06-04 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/5
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | TCNU8547854 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | TCNU8608749 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8521432 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8830160 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-29 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/30
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | FCIU8636560 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | BSIU9693520 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | JXLU8498055 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8845318 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | CAIU4416317 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8243080 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8441804 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 5/31
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | DFSU6496756 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8703720 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | TCNU4570368 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | BMOU4786306 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | TCNU8752102 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 37 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | RFCU5073670 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | TLLU4461943 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | BSIU9118692 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8433440 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | SEGU5423236 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-31 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8976600 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEROJA LIMA | SSPHPKL8049218 | SDSMY20190417-01 | ZCSU8591656 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-18 | 2019-05-28 |  |  | 2019-05-22 |  |  | 2019-06-04 |  |  | 2019-05-30 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | TCNU5832760 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | DFSU6489675 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8969350 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8603438 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8469843 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | TCNU6835717 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8894122 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/11
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8704290 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | CAIU4419656 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8471497 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/10
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | TGBU5498020 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | GAOU6078877 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | GCXU5062672 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8456260 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | CRSU9060516 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8651987 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/6
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8870429 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8768525 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | ZCSU8694593 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/11
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784876 | NPNESEATSSE47894 | TCNU4259989 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | FCIU9043111 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | GCXU5008603 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | GCXU5070045 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-06 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | RFCU4051613 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | SEGU5203273 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/10
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TCKU6019257 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TCNU1832593 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TCNU5360978 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TCNU5552250 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TCNU5776395 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TGBU5771990 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/11
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | TGBU7091219 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-05 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU6514223 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU6528720 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU7091358 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU8260107 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU8490120 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU8563720 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/10
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU8739424 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-07 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | ALBERT MAERSK | ZIMUSEL784806 | NPNESEATSSE47965 | ZCSU8989110 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-04 | 2019-05-31 |  |  | 2019-05-24 |  |  | 2019-06-07 |  |  | 2019-06-10 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/11
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TCNU4395970 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | DFSU6489865 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU8519121 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU8899084 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU7034609 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TCNU4851241 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | SLSU8051052 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU8833889 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | DFSU6744106 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU8842284 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | DRYU9902267 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TCNU8184487 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/11
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TCNU8533824 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | AXIU1611145 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | ZCSU8995180 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | BMOU4502457 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-11 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TCNU4633954 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | CBHU8441030 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | TGBU5973223 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | GAOU6111229 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | BMOU4584455 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-10 |  | DELIVERED (PNCW)
NORFOLK, VA | 71900031 | CLEMENTINE MAERSK | ZIMUSEL784776 | NPNESEATSSE48008 | SEGU5275951 | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 638 | 22 | 2019-05-06 | 2019-06-04 |  |  | 2019-05-30 |  |  | 2019-06-11 |  |  | 2019-06-12 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | BSIU9753635 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-18 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | CRSU9078135 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | TLLU5291585 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | ZCSU8533686 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | ZCSU8686026 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049631 | SDSMY20190430-02 | ZCSU8730854 | Q.PLUS L-G4.2.AF 345 | 12001227A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW)
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | DFSU6308925 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-18 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8510398 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8747266 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-18 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | SEGU5758944 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-18 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | BSIU9770988 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8754352 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU7084111 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | XINU8151792 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU7120250 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8592544 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | BSIU9538329 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | CAIU9226259 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TLLU5314335 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | CRSU9079722 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8905783 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | CRSU9044259 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU7025530 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU5775207 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU6191804 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8528334 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8610231 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU5775315 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TGBU7070432 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-13 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8855065 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU7255760 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | GAOU6102891 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8860101 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU5335640 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | AXIU1449158 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-14 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | TCNU5410641 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU7116899 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8782903 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8563130 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8800611 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU6502407 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU7108640 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-18 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01 | ZCSU8454587 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED - DIRECT SHIPMENT TO SUNENERGY1 AULANDER HOLLOMAN SOLAR
NORFOLK, VA | 71901004 | SEAMAX NORWALK | SSPHPKL8049014 | SDSMY20190430-01A | ZCSU8537146 | Q.PLUS L-G4.2.AF 345 | 12001434A | 25 | 638 | 22 | 2019-04-30 | 2019-06-10 |  |  | 2019-06-03 |  |  | 2019-06-17 |  |  | 2019-06-17 |  | DELIVERED (PNCW) CLOSED IN CELLO ON 6/18
NORFOLK, VA | 71900055 | GUDRUN MAERSK | ZIMUSEL795067 | NPNESEATSSE49559 | TGBU5770545 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-14 | 2019-08-13 |  |  | 2019-08-07 |  |  | 2019-08-19 |  |  | 2019-08-15 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GUDRUN MAERSK | ZIMUSEL795067 | NPNESEATSSE49559 | ZCSU8786940 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-14 | 2019-08-13 |  |  | 2019-08-07 |  |  | 2019-08-19 |  |  | 2019-08-15 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GUDRUN MAERSK | ZIMUSEL795067 | NPNESEATSSE49559 | FCIU8637891 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-14 | 2019-08-13 |  |  | 2019-08-07 |  |  | 2019-08-19 |  |  | 2019-08-15 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GUDRUN MAERSK | ZIMUSEL795067 | NPNESEATSSE49559 | TCNU8239872 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-14 | 2019-08-13 |  |  | 2019-08-07 |  |  | 2019-08-19 |  |  | 2019-08-15 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GUDRUN MAERSK | ZIMUSEL795067 | NPNESEATSSE49559 | TGHU6805083 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-14 | 2019-08-13 |  |  | 2019-08-07 |  |  | 2019-08-19 |  |  | 2019-08-15 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8561266 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TEMU6771757 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | GVCU5327858 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | FCIU8684996 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8993932 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8733853 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8642727 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8896022 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-22 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TEMU6751350 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | CAIU9223809 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TCNU8945375 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | GAOU6088807 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU7055540 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | SEGU5681550 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | GAOU6046606 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-23 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8783957 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | BSIU9754098 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TCNU5540521 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | SEGU5279828 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | CRSU9064770 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TCNU5411458 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | CRSU9077571 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8669190 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8972009 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU7055880 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | TLLU4857847 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | GAOU6079641 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8783690 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | ZCSU8808510 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | CLEMENTINE MAERSK | ZIMUSEL795213 | NPNESEATSSE49613 | BSIU9725090 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-22 | 2019-08-20 |  |  | 2019-08-13 |  |  | 2019-08-26 |  |  | 2019-08-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU7080440 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8839974 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-28 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8427745 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TCNU2777079 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-09-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8586897 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TCNU6953664 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-28 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TCNU8760432 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-28 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8555366 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-28 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8886003 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | GCXU5069764 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TCNU4259612 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TGBU7206278 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8992176 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TCNU2972244 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU7093432 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | FSCU8148987 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | CAIU9222654 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-29 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | GCXU5007850 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | ZCSU8626623 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | CLHU9131472 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TGBU5774113 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | TLLU4780236 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | MAERESK SINGAPORE | ZIMUSEL795214 | NPNESEATSSE49806 | CRSU9019467 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-25 | 2019-08-23 |  |  | 2019-08-19 |  |  | 2019-08-29 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | AXIU1648355 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | TCNU8757300 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-08-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | ZCSU6548157 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | ZCSU8777424 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | ZCSU8233800 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | ZCSU8513720 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | FCIU8914229 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900055 | GERD MAERSK | ZIMUSEL200201526 | NPNESEATSSE49844 | ZCSU8739419 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-07-28 | 2019-08-27 |  |  | 2019-08-21 |  |  | 2019-09-02 |  |  | 2019-09-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | BMOU4500860 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | BMOU5907300 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | BSIU9541359 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | CAIU8354070 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | CAIU9230217 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | CAXU8172930 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | CAXU8237271 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | DFSU6534748 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | DRYU9525142 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-24 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | FCIU8954900 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | FCIU8995067 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | FSCU8218718 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | GAOU6096145 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | SEGU5193940 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | SEGU5685405 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCLU8562738 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU2507664 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU2751794 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU2785412 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU4427444 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU4555907 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-25 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU5390674 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU5633060 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU6279480 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU7259637 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TCNU8774101 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TGBU5416043 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TGBU5774828 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TGBU7214057 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TGHU6053480 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TLLU4872991 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TLLU5302592 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | TLLU5315901 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | XINU8091836 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU7067217 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU7068635 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU7108825 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8244744 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8523420 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8532289 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8806986 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8807787 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8891463 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8905633 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-26 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8931289 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8940146 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SYDNEY | ZIMUSEL797386 | NPNESEATSSE50290 | ZCSU8966808 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-25 | 2019-09-22 |  |  | 2019-09-18 |  |  | 2019-09-29 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TCNU7250692 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TLLU4875028 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-27 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | BMOU4584060 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8565127 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | SEGU5279303 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TLLU4306931 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FCIU8643240 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | GLDU7404962 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FSCU8173491 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FSCU8088569 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU6521074 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TGBU5493292 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TGHU9890828 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TGBU5779199 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | CRSU9064316 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TLLU4461291 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-09-30 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | BSIU9693198 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | DFSU6538450 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TCNU4347014 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8923180 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8570247 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8668336 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | GAOU6141727 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FSCU8150691 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TLLU4576536 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8522207 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8962079 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | CAIU4420831 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-01 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | CAIU4418520 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FSCU8166785 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | CAIU8635165 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TCNU4557582 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8601142 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FCIU9041084 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8466628 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU7015337 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | CAXU8021852 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8576749 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8541444 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8474686 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | AMFU8770526 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8708275 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-02 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | BMOU4654064 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | FSCU8148626 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | SEGU5333404 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | SEGU5199867 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU8749588 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TGBU5762386 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | TCNU8901269 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MAERSK SHENZHEN | ZIMUSEL797387 | NPNESEATSSE50343 | ZCSU7035734 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-26 | 2019-09-24 |  |  | 2019-09-19 |  |  | 2019-09-30 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU7134336 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8485335 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-03 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | FSCU8090139 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU7029536 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | FSCU8221413 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8735096 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | TLLU4456844 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | DRYU9095400 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU7006470 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | FCIU8921125 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8473015 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8417897 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | DFSU6302070 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | TCNU4297504 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-04 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8728055 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | GAOU6048337 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | BSIU9694023 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | TGBU5416001 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | TLLU4449064 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | TLLU4308791 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8718123 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8916129 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-09 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | FSCU8252040 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | DRYU9056106 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8963183 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8829390 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-07 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU8873520 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | UETU5272446 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | ZCSU7006905 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 71900065 | MSC LISBON | ZIMUSEL797390 | NPNESEATSSE50344 | SLSU8051427 | Q.PEAK DUO L G5.2.0.V 395 | 30361055A | 25 | 638 | 22 | 2019-08-30 | 2019-09-28 |  |  | 2019-09-23 |  |  | 2019-10-04 |  |  | 2019-10-08 |  | DELIVERED (DIRECT SHIPMENT TO STRATA SOLAR)
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234062 | NEDFPKGARG44440 | BMOU5140250 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234062 | NEDFPKGARG44440 | DRYU9823790 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234062 | NEDFPKGARG44440 | EISU9444304 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234062 | NEDFPKGARG44440 | EMCU9826264 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234062 | NEDFPKGARG44440 | MAGU5256140 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | BEAU4452747 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | BMOU5399301 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | BMOU6026196 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | DRYU9445330 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EISU9235156 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EISU9372225 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-08 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EITU1124078 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EITU1124205 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EITU1636285 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EMCU9557993 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EMCU9662010 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | EMCU9689578 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | CLOSED IN CELLO 7/16 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | FCIU9015383 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | HMCU9150737 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | TCLU9140130 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | TEMU6264074 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | TGBU7126399 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | CMA CGM LIBRA | EGLV091030234071 | NEDFPKGARG43460 | WFHU5186319 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | BSIU9238677 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | CAIU8766761 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | GCXU5196394 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-06-30 |  | DELIVERED CLOSED IN CELLO ON 07/01 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | GCXU5218810 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | KKFU8126890 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | MOTU0625137 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | NYKU0812810 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/08 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | NYKU0834738 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | NYKU4340760 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TCLU1692299 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TCLU5100248 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TCLU8149771 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TCLU8240238 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TEMU7503846 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TEMU7565874 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TLLU4506035 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TLLU4600416 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRES | ONEYPKGA20703400 | NEDFPKGARD44394 | TRLU7390090 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | AXIU1653496 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | DRYU9650139 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | KKFU8140326 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | NYKU4397003 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCLU1541374 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-06-30 |  | DELIVERED CLOSED IN CELLO ON 07/01 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCLU7754361 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-06-30 |  | DELIVERED (PNCW20) VESSEL / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCLU8220524 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCLU8244188 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-03 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCLU9126683 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED CLOSED IN CELLO ON 07/06 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCNU2082277 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TCNU4694498 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TGBU5301790 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TLLU5596579 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TRLU7367084 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-02 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | YANTIAN EXPRESS | ONEYPKGA20702300 | NEDFPKGARD45540 | TRLU7598545 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-05-28 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-07 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | BEAU4469143 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | EGSU9134054 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | EMCU9569736 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | HMCU9137904 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 07/07 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | HMCU9159098 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-07 |  | DELIVERED CLOSED IN CELLO ON 07/08 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | APL MIAMI | EGLV091030250688 | NEDFPKGARJ95335 | TEMU8541455 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-05 | 2020-07-02 |  |  | 2020-06-26 |  |  | 2020-07-10 |  |  | 2020-07-07 |  | DELIVERED CLOSED IN CELLO ON 07/08 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | CAIU9205317 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED CLOSED IN CELLO ON 07/09(PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | FDCU0416600 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | KKFU7420240 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-09 |  | DELIVERED CLOSED IN CELLO ON 07/10 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | KKFU7620681 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-13 |  | DELIVERED CLOSED IN CELLO on 07/14 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | KKFU8150535 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED CLOSED IN CELLO on 07/13 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4290210 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-09 |  | DELIVERED CLOSED IN CELLO ON 07/10 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4306385 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED CLOSED IN CELLO ON 07/09(PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4325934 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-09 |  | DELIVERED CLOSED IN CELLO ON 07/10 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4708424 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4825890 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED CLOSED IN CELLO on 07/13 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4902450 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU4994858 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-13 |  | DELIVERED CLOSED IN CELLO on 07/14 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | NYKU5143472 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-09 |  | DELIVERED CLOSED IN CELLO ON 07/10 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | TCLU6093056 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-08 |  | DELIVERED (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | TCLU8681188 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED CLOSED IN CELLO on 07/13 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | TCNU4910529 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED CLOSED IN CELLO on 07/13 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | TEMU7180173 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-13 |  | DELIVERED CLOSED IN CELLO on 07/14 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001028 | MEISHAN BRIDGE | ONEYPKGA21990600 | NEDFPKGARG44624 | TGCU0201895 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-08 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-09 |  | DELIVERED CLOSED IN CELLO ON 07/10 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU0802216 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-13 |  | DELIVERED CLOSED IN CELLO on 07/14 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4343434 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-14 |  | DELIVERED CLOSED IN CELLO on 07/15 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4366091 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-14 |  | DELIVERED CLOSED IN CELLO on 07/15 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4803550 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-14 |  | DELIVERED CLOSED IN CELLO on 07/15 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU8869405 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-13 |  | DELIVERED CLOSED IN CELLO on 07/14 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU9561947 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-14 |  | DELIVERED CLOSED IN CELLO on 07/15 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCNU8007310 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-14 |  | DELIVERED CLOSED IN CELLO on 07/15 (PNCW20) / TUV-Label (No good to ship) | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | FDCU0522685 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU0842292 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4179784 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4390890 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4725329 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4826330 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | NYKU4835898 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | ONEU0275067 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU4940146 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU5933856 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU7816437 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU8580876 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TCLU9805494 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TEMU7181170 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TEMU8280789 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TGHU6166594 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TLLU5471015 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001033 | YM WELLHEAD | ONEYPKGA25149600 | NEDFPKGARP68256 | TLLU5524769 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | BMOU5386650 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | CAIU9916552 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | DRYU9596763 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | FCIU9050975 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | FDCU0517518 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | FDCU0570111 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | GESU6355893 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | KKFU7612135 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | KKFU7689712 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | KKFU7886178 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | KKFU7922927 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | KKFU8060703 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU0728823 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU0831148 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU0849363 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU4282597 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU4441195 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | NYKU5169538 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU1533379 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU4958741 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU5686421 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU5935437 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU6242334 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU6273700 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU8044549 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU8237770 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCLU9721243 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU3597451 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-16 |  | DELIVERED CLOSED IN CELLO 7/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU5312202 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU5828694 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU6100548 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU6812389 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU7029383 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU7331726 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-20 |  | DELIVERED CLOSED IN CELLO ON 07/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TCNU7782550 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TEMU6837284 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-17 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TEMU8563304 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TLLU4002230 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TLLU4218949 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-15 |  | DELIVERED CLOSED IN CELLO 7/16 (PNCW20) / Good to ship | Sun Energy Project
NORFOLK, VA | 72001034 | YM WELLHEAD | ONEYPKGA25151600 | NEDFPKGARP98942 | TRLU7455837 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-12 |  |  | 2020-07-07 |  |  | 2020-07-20 |  |  | 2020-07-18 |  | DELIVERED CLOSED IN CELLO 7/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | DFSU6688105 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED CLOSED IN CELLO 7/23 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | DFSU7309783 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | DRYU9553210 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EGHU9092398 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED CLOSED IN CELLO 7/23 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EITU1008191 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED CLOSED IN CELLO 7/23 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EITU1468710 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EITU1506208 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EITU1720800 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | EMCU9650154 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TCLU8816154 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED CLOSED IN CELLO 7/23 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TCNU4506224 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TCNU6380053 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TGBU6956133 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TGHU6659538 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | APL SOTHAMPTON | EGLV091030282172 | NEDFPKGARR50864 | TLLU4875455 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-06-18 | 2020-07-16 |  |  | 2020-07-08 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED CLOSED IN CELLO ON 07/22 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | CAIU8700960 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | GESU6566540 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | KKFU7962262 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | MOTU0650572 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | NYKU4802934 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | NYKU5159099 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | ONEU0202749 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TCLU8135187 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TCNU5961290 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TCNU6360273 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TCNU7683521 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TGBU5182789 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TLLU4599716 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TLLU4737501 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | ONE MAGNIFICENCE | ONEYPKGA25155300 | NEDFPKGARR60130 | TLLU5535465 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | ONE MAGNIFICENCE | ONEYPKGA26074400 | NEDFPKGARS56822 | AKLU6503109 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | ONE MAGNIFICENCE | ONEYPKGA26074400 | NEDFPKGARS56822 | KKFU7916122 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | ONE MAGNIFICENCE | ONEYPKGA26074400 | NEDFPKGARS56822 | NYKU4445652 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | ONE MAGNIFICENCE | ONEYPKGA26074400 | NEDFPKGARS56822 | TCNU4968460 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-25 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | ONE MAGNIFICENCE | ONEYPKGA26074400 | NEDFPKGARS56822 | TLLU5529400 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-18 | 2020-07-23 |  |  | 2020-07-16 |  |  | 2020-07-30 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 07/27 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | BSIU9510070 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | DRYU9293690 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EGSU9019127 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EISU9339839 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EISU9366562 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EITU1301070 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EITU1718906 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | EITU9026360 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | HMCU9196173 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | IMTU9019615 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | OCGU8025096 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | OCGU8060353 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | TCNU6276774 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | TCNU6278102 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282741 | NEDFPKGARR51575 | TEMU8844174 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | BMOU4684243 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | BMOU5006615 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | BMOU5138756 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | BMOU5302469 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | BMOU5802206 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | DFSU7295843 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | DRYU9573747 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGHU9110399 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGHU9252285 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGHU9337459 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGHU9392292 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-27 |  | DELIVERED CLOSED IN CELLO 7/28 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGSU9021572 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EGSU9195018 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EISU9351238 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU1137305 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU1174211 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU1297350 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU1925190 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU1984640 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EITU9113280 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | EMCU9574579 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | FFAU1119276 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | SEGU5881521 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TCLU4957447 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TCNU2897177 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TCNU3010060 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO 7/29 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TEMU6269163 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TEMU8524355 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-29 |  | DELIVERED CLOSED IN CELLO 7/30 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TGCU5080163 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-31 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | CMA CGM CHRISTOPHE COLOMB | EGLV091030282181 | NEDFPKGARR51870 | TLLU4144569 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-25 | 2020-07-25 |  |  | 2020-07-20 |  |  | 2020-07-31 |  |  | 2020-07-30 |  | DELIVERED CLOSED IN CELLO ON 07/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | CXDU2267208 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-03 |  | DELIVERED CLOSED IN CELLO 8/4 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | GATU8831294 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-03 |  | DELIVERED CLOSED IN CELLO 8/4 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | GESU5279485 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-03 |  | DELIVERED CLOSED IN CELLO 8/4 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | GESU6237838 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/5 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | KKFU7959042 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/5 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | MOTU0673460 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-03 |  | DELIVERED CLOSED IN CELLO 8/4 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU0784452 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/5 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU4274729 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-03 |  | DELIVERED CLOSED IN CELLO 8/4 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU4373130 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/5 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU5643436 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/5 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU5710236 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | NYKU5945837 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | SEGU5288795 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCLU8289829 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCLU9671230 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED CLOSED IN CELLO ON 08/07 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCNU2116525 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCNU4195164 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCNU6189659 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TCNU7453302 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | MOL MANEUVER | ONEYPKGA25158600 | NEDFPKGARP68875 | TRLU7532065 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-05 |  | DELIVERED CLOSED IN CELLO ON 08/06 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | FDCU0576819 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | MOTU0651985 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | MOTU0779132 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) (This container is targeted for off hire and has special empty return instructions) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | MOTU0781119 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) (This container is targeted for off hire and has special empty return instructions) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | NYKU5136998 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | NYKU5187640 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-13 |  | DELIVERED CLOSED IN CELLO 8/14 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | NYKU5813980 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-13 |  | DELIVERED CLOSED IN CELLO 8/14 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | ONEU0302033 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | TCNU4895553 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-12 |  | DELIVERED CLOSED IN CELLO 8/13 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MANEUVER | ONEYPKGA25161700 | NEDFPKGARP69730 | TCNU5309847 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-25 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-06 |  |  | 2020-08-13 |  | DELIVERED CLOSED IN CELLO 8/14 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | AXIU1628981 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-05 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | BEAU4413123 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-05 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | BMOU4112470 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | CAIU9370991 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | CXDU1667719 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | FFAU1429667 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | KKFU7994378 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | KKFU8107930 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | KKFU8163445 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | MOTU0627593 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | MOTU0668761 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | NYKU4233231 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-08 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | NYKU4246178 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-06 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCLU6246406 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCLU9689394 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCNU3283656 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCNU5186418 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCNU6203675 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TCNU7827932 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL GRANDEUR -> UNAYZAH | ONEYPKGA25154900 | NEDFPKGARR59942 | TGBU5116771 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-18 | 2020-08-01 |  |  | 2020-07-24 |  |  | 2020-08-07 |  |  | 2020-08-07 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA28296500 | NEDFPKGARX07560 | NYKU5964781 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-08 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA28296500 | NEDFPKGARX07560 | NYKU4939676 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA28296500 | NEDFPKGARX07560 | TCLU6497818 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA28296500 | NEDFPKGARX07560 | TCNU6070778 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA28296500 | NEDFPKGARX07560 | TCNU9899660 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | MOTU0737604 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-08 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4806272 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-11 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | ONEU0196899 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-11 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCNU5418365 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | BMOU6599990 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 580 | 20 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | BMOU6599990 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 58 | 2 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | BEAU4628585 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | CAIU9076760 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | GESU6834221 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | MOTU0648359 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | MOTU6711295 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU0729732 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4109431 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4304546 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4400690 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4700700 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4716477 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4757732 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-12 |  | DELIVERED CLOSED IN CELLO 8/13 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU4825689 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | NYKU5147457 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCLU5449116 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCLU6745909 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCLU8454857 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-12 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCLU9429571 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TCNU6428497 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-08 |  | DELIVERED CLOSED IN CELLO 8/10 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | NYK DEMETER -> YM WIDTH | ONEYPKGA25159700 | NEDFPKGARP99465 | TEMU7185529 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-06-29 | 2020-08-04 |  |  | 2020-07-28 |  |  | 2020-08-11 |  |  | 2020-08-10 |  | DELIVERED CLOSED IN CELLO 8/11 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | DRYU6044950 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-11 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | DRYU9484819 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-11 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | GESU5590922 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | KKFU7448572 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | MOTU0671220 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | NYKU0755768 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | NYKU4040166 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-13 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | NYKU4345761 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-13 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | NYKU5149737 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-13 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | SEGU5327490 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-13 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU4807399 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-14 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU4896586 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-14 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU5188663 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-14 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU9170019 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-14 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU9472533 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-15 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC (This container is targeted for off hire and has special empty return instructions) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TCNU9575383 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-15 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC (This container is targeted for off hire and has special empty return instructions) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TEMU7833874 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-15 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TEMU8714150 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-14 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TLLU5661463 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-15 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MOTIVATOR | ONEYPKGA25162800 | NEDFPKGARP71292 | TRLU7531407 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-02 | 2020-08-09 |  |  | 2020-08-04 |  |  | 2020-08-14 |  |  | 2020-08-17 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4807366 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 261 | 9 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/19 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4807366 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 348 | 12 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/19 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | DFSU6977047 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | FCIU9768920 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | KKFU7767775 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | KKFU7770491 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | MOTU6735189 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU0710845 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU0729250 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4209153 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4216147 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4291182 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4398020 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4424686 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4438993 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-14 |  | DELIVERED CLOSED IN CELLO ON 8/17 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4707650 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4892183 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU4991308 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU5254500 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | NYKU5908915 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCLU1735338 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/19 (PNCW20) (This container is targeted for off hire and has special empty return instructions) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCLU5500100 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/19 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCLU6620434 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCLU8527871 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCLU8759497 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU4107414 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU4372043 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO ON 08/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU5736577 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO 08/19 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU5947902 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO ON 08/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU8793797 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TCNU8963147 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO ON 08/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001033 | NYK DEMETER -> AL QIBLA | ONEYPKGA26777700 | NEDFPKGARX04115 | TEMU8724224 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-06-29 | 2020-08-11 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO ON 08/21 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | CAIU9168743 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | CRSU9367328 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | GESU6834915 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | KKFU7771749 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | KKFU7904409 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | MOTU0630529 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-19 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU0784196 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-20 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU0810232 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU0811964 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-20 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU0865430 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-20 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4049369 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4252606 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4445077 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4820455 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4852529 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-20 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | NYKU4909481 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCLU1559590 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCLU6403629 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU2076079 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU3075462 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU4800579 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU4895851 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU6917878 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TCNU9775020 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC (This container is targeted for off hire ) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28412900 | NEDFPKGARX78540 | TGCU0009692 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-22 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | TCLU8823364 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | NYKU4219090 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | TGHU6835920 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | NYKU0751931 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | CAIU9187147 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | BEAU4622587 | Q.PEAK DUO L-G7.2 405 | 12004283R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | FSCU6536089 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-24 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC (This container is targeted for off hire ) | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | NYKU0772404 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-24 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | NYKU4355841 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-21 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001034 | MOL MODERN | ONEYPKGA28413300 | NEDFPKGARX77836 | NYKU4327201 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-09 | 2020-08-17 |  |  | 2020-08-10 |  |  | 2020-08-24 |  |  | 2020-08-24 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | DFSU7426202 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | CRSU9361232 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | GESU6254645 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | KKFU7411547 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC (This container is targeted for off hire ) | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | KKFU7746366 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | KKFU7766070 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | NYKU4118304 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-25 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | NYKU4236267 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | NYKU4899022 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TCLU8540370 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TCNU4852741 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TCNU6024854 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TCNU9372241 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-26 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TEMU7203941 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-25 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | ONE MINATO | ONEYPKGA31947900 | NEDFPKGASF36641 | TEMU8640479 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-20 | 2020-08-24 |  |  | 2020-08-17 |  |  | 2020-08-31 |  |  | 2020-08-27 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | BEAU5318840 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | BSIU9370662 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | FDCU0350518 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED CLOSED IN CELLO 8/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | FDCU0621672 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED CLOSED IN CELLO 8/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | MOTU0636548 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU0849002 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU4189463 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU4295465 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-09-01 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU4753824 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU4831207 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU5159951 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | NYKU5162148 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | SEGU5051503 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED CLOSED IN CELLO 8/31 (PNCW20) | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU1638111 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-09-02 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU1790675 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU1866678 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU6372240 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-09-02 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU7823842 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-09-01 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU8942553 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCLU8959319 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCNU4125146 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCNU4874993 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-28 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TCNU7442205 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-28 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TLLU5519870 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-09-01 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | KYOTO EXPRESS | ONEYPKGA31427900 | NEDFPKGASE14756 | TRLU7511442 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-24 | 2020-08-27 |  |  | 2020-08-17 |  |  | 2020-09-03 |  |  | 2020-08-31 |  | DELIVERED DIRECT TO SUNENERGY - ROPER, NC | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | FSCU6511394 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY (This container is targeted for off hire ) | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | FSCU8629529 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | GESU5938453 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | GESU6777728 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | KKFU7979727 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | MOTU0612470 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU0721536 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4157960 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4164254 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-09 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4217879 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4250291 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4260387 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4311606 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4337956 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4405618 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4443855 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | NYKU4912654 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | SEGU4133633 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-10 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TCLU6683936 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TCLU7994151 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TCNU6752607 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TCNU9029741 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY (This container is targeted for off hire ) | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TEMU6841730 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TEMU8724097 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TGBU5203789 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-14 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | DALIAN EXPRESS | ONEYPKGA31430300 | NEDFPKGASG70503 | TLLU5459690 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-30 | 2020-09-06 |  |  | 2020-08-28 |  |  | 2020-09-14 |  |  | 2020-09-11 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | REPLACEMENT | DALIAN EXPRESS | ONEYPKGA35672800 | NEDFPKGASM56013 | NYKU4741417 | Q.PLUS DUO L-G5.2 360 | 12003547R | 20 | 386 | 14 | 2020-07-30 | 2020-09-06 |  |  | 2020-09-01 |  |  | 2020-09-14 |  |  | 2020-09-14 |  | RECEIVED CLOSED IN CELLO ON 9/15 (PNCW20) | REPLACEMENT FOR STRATA
NORFOLK, VA | REPLACEMENT | DALIAN EXPRESS | ONEYPKGA35672800 | NEDFPKGASM56013 | NYKU4741417 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 6 | 1 | 2020-07-30 | 2020-09-06 |  |  | 2020-09-01 |  |  | 2020-09-14 |  |  | 2020-09-14 |  | RECEIVED CLOSED IN CELLO ON 9/15 (PNCW20) | REPLACEMENT FOR STRATA
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | BEAU4616840 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | BEAU4617364 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | DRYU9534400 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | FDCU0518941 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | FDCU0557892 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | MOTU5806143 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-15 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | NYKU0769313 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | NYKU4350120 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | NYKU4394391 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | NYKU4745330 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | NYKU4838958 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU1496315 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU1783547 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU5794180 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU6631233 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU6992581 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-16 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU9279091 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU9556920 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCLU9878016 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCNU2453700 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCNU4562758 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCNU5922571 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCNU5947163 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-17 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TCNU8045630 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TEMU7305990 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TEMU7876650 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TGBU5327769 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TGHU6465851 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TGHU6470436 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001037 | YM UPSURGENCE | ONEYPKGA31432500 | NEDFPKGASG71785 | TRLU7573059 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-09 | 2020-09-13 |  |  | 2020-09-08 |  |  | 2020-09-18 |  |  | 2020-09-21 |  | DELIVERED --> DIRECT TO SUNENERGY | Sun Energy Project
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | BSIU9676210 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-09-29 |  | DELIVERED CLOSED IN CELLO ON 09/30 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | CAIU9039026 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | KKFU8041750 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-09-29 |  | DELIVERED CLOSED IN CELLO ON 09/30 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU0834002 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU4377809 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU4442843 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU4711259 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU4745140 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-02 |  | DELIVERED CLOSED IN CELLO ON 10/02 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU5782051 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/01 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | NYKU5902769 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-09-29 |  | DELIVERED CLOSE IN CELLO ON 09/30 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | SEGU4459229 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-02 |  | DELIVERED CLOSED IN CELLO ON 10/02 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | TCLU1663840 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-02 |  | DELIVERED CLOSED IN CELLO ON 10/02 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | TCLU8571703 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-09-29 |  | DELIVERED CLOSED IN CELLO ON 09/30 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | TCNU4961070 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-09-28 |  | DELIVERED CLOSE IN CELLO ON 09/29 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | TCNU5899189 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20)
NORFOLK, VA | 72001038 | MOL MAESTRO | ONEYPKGA37698400 | NEDFPKGASV46196 | TCNU8301496 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-02 |  | DELIVERED CLOSED IN CELLO ON 10/02 (PNCW20)
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | BEAU5262823 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | CAIU9135272 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | CAIU9372269 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | DFSU6311019 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | DFSU6665202 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | DRYU9410457 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | MOTU0770304 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) - Need to return empty to Off-Hire | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | NYKU0780821 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-02 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | NYKU5285306 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | TCLU1715060 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | TCLU5968298 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | TCNU5418046 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001037 | MOL MAESTRO | ONEYPKGA35058600 | NEDFPKGASL45671 | TGHU8556082 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-26 |  |  | 2020-09-17 |  |  | 2020-10-02 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | BEAU5268204 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | BMOU5388781 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | CAIU8637804 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | DRYU6046130 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | FDCU0481729 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU0806510 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU4210093 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU4357654 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU4770992 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU4840472 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-03 |  | DELIVERED CLOSED IN CELLO 10/5 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU5151210 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU5211005 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | NYKU5252452 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCLU6634145 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCLU6635917 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCLU9540498 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCLU9581286 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCNU5852659 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCNU6032850 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCNU6046088 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCNU7479312 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TCNU7873265 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-06 |  | DELIVERED (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TEMU8669636 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TEMU8733036 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MADRID BRIDGE | ONEYPKGA37704600 | NEDFPKGASV76893 | TGHU6200894 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-20 | 2020-09-28 |  |  | 2020-09-17 |  |  | 2020-10-05 |  |  | 2020-10-05 |  | DELIVERED CLOSED IN CELLO 10/06 (PNCW20) | Holocene
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | GESU5115877 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | NYKU5274791 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | SEGU4408854 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | TCLU6260195 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | TCLU6341677 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | TCLU6662635 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-14 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37700900 | NEDFPKGASV75563 | TCNU4887692 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | CRSU9147935 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | CAIU9537287 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | CXDU1106657 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | CXDU1752488 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | FDCU0531814 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | GESU5980896 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | GESU6004348 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | ONEU0214734 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | TCLU1641270 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | MEISHAN BRIDGE | ONEYPKGA37864600 | NEDFPKGASV79240 | TCLU7903758 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-31 | 2020-10-09 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CRSU9239517 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CRSU9278447 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU1842133 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2043297 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2050995 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2118734 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2118781 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2119725 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2120496 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2122009 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | CXDU2128861 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6153932 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6426404 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-17 |  | DELIVERED CLOSED IN CELLO 10/19 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6433050 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6519744 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6625664 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6906810 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | GESU6917028 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | HJMU1924819 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4096397 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4134270 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4269091 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4283973 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-23 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4409110 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4647946 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO 10/20 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4732626 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU4948636 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU5043067 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU5267940 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-23 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU6129041 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO 10/21 (PNCW20)
NORFOLK, VA | 72001038 | ONE MAGNIFICENCE | ONEYPKGA37707900 | NEDFPKGASV78201 | SEGU6136800 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-03 | 2020-10-15 |  |  | 2020-10-06 |  |  | 2020-10-22 |  |  | 2020-10-23 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | CRSU9214930 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | CXDU1106385 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | CXDU2053042 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | CXDU2124510 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | FFAU1458710 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | GESU5985429 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | GESU6015907 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | GESU6578900 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | GESU6737860 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | HJMU1939700 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-21 |  | DELIVERED CLOSED IN CELLO 10/22 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | NYKU4837041 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | NYKU5291654 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4404041 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4413064 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4447378 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4646615 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-23 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4820558 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU4952071 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU5266374 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | SEGU6129720 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | TCLU6661963 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-26 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | TCLU6713305 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | TRLU7609980 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001038 | MOL MANEUVER | ONEYPKGA37702400 | NEDFPKGASV74244 | TRLU8278227 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 638 | 22 | 2020-09-10 | 2020-10-18 |  |  | 2020-10-09 |  |  | 2020-10-23 |  |  | 2020-10-24 |  | DELIVERED CLOSED IN CELLO ON 10/26 (PNCW20)
NORFOLK, VA | 72001040 | CCNI ANGOL | MAEU205101452 | SDSMY20200914-01 | MRKU2332461 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-14 | 2020-10-20 |  |  | 2020-10-13 |  |  | 2020-10-26 |  |  | 2020-10-26 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001040 | CCNI ANGOL | MAEU205101452 | SDSMY20200914-01 | MRKU2595961 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-14 | 2020-10-20 |  |  | 2020-10-13 |  |  | 2020-10-26 |  |  | 2020-10-26 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CRSU9109581 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CRSU9111260 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CRSU9148952 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CRSU9314441 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU1749967 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU1750525 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2041020 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2054157 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2120578 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED CLOSED IN CELLO ON 11/3 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2120881 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2129791 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | CXDU2130880 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU5946187 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6004630 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6448595 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6579553 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-05 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6619677 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6701846 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | GESU6713180 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-05 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | HJMU1934226 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | KKFU7905642 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | NYKU4760700 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU4147771 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU4309445 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU4466070 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU4670226 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-03 |  | DELIVERED CLOSED IN CELLO ON 11/4 (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU4858091 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU6128739 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | SEGU6136570 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-04 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001038 | YM MANDATE | ONEYPKGA37705700 | NEDFPKGASV75040 | TCNU6857634 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-08-27 | 2020-10-30 |  |  | 2020-09-28 |  |  | 2020-11-06 |  |  | 2020-11-02 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | FCIU8603119 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | FCIU9078490 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | GESU5941312 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MIEU0019606 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRKU3147621 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRKU3540686 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRKU3827402 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRKU3874615 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRKU4353334 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRSU3120536 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MRSU4180484 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MSKU0180470 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MSKU0533010 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MSKU0561619 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/6 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MSKU1645503 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | MSKU1774922 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/6 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | TCLU5685868 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | TCNU2823507 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/6 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | TCNU4470625 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MAERSK SOFIA | MAEU205122773 | SDSMY20200921-01 | UETU5919580 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-21 | 2020-11-04 |  |  | 2020-10-27 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/9 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | FCIU8382316 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MRKU2386642 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-16 |  | DELIVERED CLOSED IN CELLO ON 11/17 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MRKU3619862 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO ON 11/19 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MRKU3843300 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MRKU4201012 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO ON 11/16 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MRKU5300914 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO ON 11/16 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU0006832 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO ON 11/16 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU0119628 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO ON 11/19 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU0299746 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU0948676 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU1484121 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-18 |  |  | 2020-11-20 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU1865935 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO ON 11/19 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU1992483 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-20 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU8567969 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-17 |  | DELIVERED CLOSED IN CELLO ON 11/18 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU8874190 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO ON 11/19 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | MSKU9904663 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-17 |  | DELIVERED CLOSED IN CELLO ON 11/18 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | PONU7515940 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | PONU8021556 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO ON 11/19 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | SUDU6542707 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-20 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | TCLU7478896 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001040 | MARCHEN MAERSK | MAEU205122859 | SDSMY20200928-01 | TCNU2618056 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-09-28 | 2020-11-11 |  |  | 2020-11-04 |  |  | 2020-11-17 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO ON 11/20 (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | ECMU9630950 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-17 |  | DELIVERED CLOSED IN CELLO 12/18 (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | GESU6132230 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-18 |  | DELIVERED (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | GLDU9887767 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-17 |  | DELIVERED CLOSED IN CELLO 12/18 (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | TCKU6249692 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-17 |  | DELIVERED CLOSED IN CELLO 12/18 (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | TCLU1876589 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-17 |  | DELIVERED CLOSED IN CELLO 12/18 (PNCW20)
NORFOLK, VA | 72001050 | CMA CGM CHILE | CMDUAYN0623950 | SDSMY20201114-01 | TCNU3510322 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-11-15 | 2020-12-15 |  |  | 2020-12-07 |  |  | 2020-12-18 |  |  | 2020-12-18 |  | DELIVERED (PNCW20)
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | CCLU7195159 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | CCLU7231066 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | CCLU7238440 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | CSLU6095536 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | FSCU8523033 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | OOCU6857671 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-13 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | OOLU6944047 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | TGHU6480286 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | TGHU6877587 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CMA CGM FIDELIO | COSU6173221570 | SDSMY20191212-01 | TRLU8169904 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CBHU8134498 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CBHU9477871 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CBHU9567147 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/14 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CBHU9581335 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CCLU7102095 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/14 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CCLU7710515 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CCLU7729697 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-09 |  | DELIVERED CLOSED IN CELLO ON 1/13 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CCLU7951702 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CSLU6007427 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CSLU6055045 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/14 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CSLU6075252 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | CSNU6423062 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | FCIU9649916 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | FSCU8483413 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED CLOSED IN CELLO ON 1/9 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | OOCU7481830 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-13 |  |  | 2020-01-08 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | TCNU2610815 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/14 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | TCNU4610326 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/14 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | TCNU6264937 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | TEMU6504663 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-14 |  |  | 2020-01-13 |  | DELIVERED CLOSED IN CELLO ON 1/15 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM FIDELIO | COSU6173221560 | SDSMY20191212-02 | TEMU7598029 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-12 | 2020-01-06 |  |  | 2019-12-31 |  |  | 2020-01-10 |  |  | 2020-01-08 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | TCLU9576227 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | NYKU0758330 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | TCLU5134551 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | NYKU0817371 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | GESU6124826 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | FDCU0349100 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | ONEU0318770 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | TGCU0206074 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | TCNU5234178 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | KKFU8128779 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | TEMU7412643 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | FDCU0606512 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | FFAU1426668 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | ONEU0233760 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN BREEZE | ONEYSELVD2999500 | SHTC19120126 | KKFU7809994 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2019-12-14 | 2020-01-09 |  |  | 2019-12-31 |  |  | 2020-01-15 |  |  | 2020-01-14 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | BMOU4398403 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | BMOU4788700 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | BMOU5131957 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED CLOSED IN CELLO ON 1/16 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU8657230 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU8883475 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU9001099 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU9014326 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU9123158 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CBHU9433111 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CCLU7388991 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CCLU7782177 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CSNU6658494 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | CSNU7152577 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED CLOSED IN CELLO ON 1/16 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | DFSU7681105 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | FCIU9555400 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | FCIU9639055 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | FCIU9992714 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | FSCU8600124 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | FSCU9311738 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | OOCU7257239 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | OOCU7388202 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | OOLU8614825 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | OOLU8883526 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | OOLU9911303 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | TCNU6702967 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | TEMU6289637 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | TGHU6873874 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | TGHU6882557 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | TGHU9306750 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED CLOSED IN CELLO ON 1/16 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | UETU5200512 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | UETU5314618 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | UETU5349018 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-16 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901035 | CMA CGM ORFEO | COSU6221795300 | SDSMY20191219-03 | UETU5385859 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-19 | 2020-01-13 |  |  | 2020-01-06 |  |  | 2020-01-17 |  |  | 2020-01-15 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | TCNU6098230 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | KKFU7522181 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | NYKU4841268 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | NYKU4424705 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | NYKU5256144 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | MOTU6702288 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN BRIGHTNESS | ONEYSELVD4498800 | SHTC19120204 | BEAU5250674 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-16 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-20 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TCNU1826100 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TCNU4236160 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TGBU7125005 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8211993 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8426800 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8605765 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8986614 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | BSIU9683266 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | CAAU5241463 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | CAIU4429551 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | CRSU9047474 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | DFSU6775621 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | DRYU9610727 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | FSCU8255223 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | GAOU6100306 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | SEGU5190601 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | SEGU5807381 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TCNU2721608 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TCNU4558790 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TCNU8534883 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TGBU7129084 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | TGBU7259529 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU6532612 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU7004991 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU7014290 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU7044989 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU7104049 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU7105894 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8437574 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED CLOSED IN CELLO ON 1/22 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8495903 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-22 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8510628 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8533650 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8717385 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8746038 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8813820 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8878311 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8888705 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | CLEMENTINE MAERSK | ZIMUSEL7010410 | SHTC19120207 | ZCSU8986297 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-22 | 2020-01-17 |  |  | 2020-01-07 |  |  | 2020-01-23 |  |  | 2020-01-21 |  | DELIVERED (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | BMOU4500388 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | BMOU4520321 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | DRYU9924116 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | FCIU8747369 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | GAOU6047710 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | SEGU5331150 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | SEGU5338725 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TCNU5338207 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TEMU6164537 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TGBU5416824 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU6537147 | Q.PEAK DUO L-G5.2 390 | 12002652 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | BSIU9707434 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | CAAU5286350 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | FSCU8227875 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | GAOU6460576 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | SEGU5777456 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TCNU2784530 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TCNU6906826 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | TGBU7166386 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | UETU5765340 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-23 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU7029705 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU8640874 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU8691212 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU8748529 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/27 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU8804155 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901034 | CAP ARNAUTI | SSPHPKL8059605 | SDSMY20191217-01 | ZCSU8941179 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-18 | 2020-01-22 |  |  | 2020-01-08 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MRKU3020257 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MRKU3080596 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MRSU3527521 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MRSU3663575 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MSKU0267179 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MSKU0317080 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MSKU0694627 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MSKU0997562 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | MSKU1172268 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | PONU7295721 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | SUDU6533259 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | SUDU6812063 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | TCKU6432804 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | TCKU7206083 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71900093 | GERD MAERSK | SUDUN9SOL0198451 | SHTC19120281 | TCNU8042414 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-29 | 2020-01-22 |  |  | 2020-01-16 |  |  | 2020-01-28 |  |  | 2020-01-24 |  | DELIVERED CLOSED IN CELLO ON 1/25 (PIONEERNBNEW25) | PIONEER - 2300 RT. 1
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | BMOU4389823 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | BMOU4637513 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | BSIU9382787 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CBHU8921087 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CCLU6793644 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CCLU6853213 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CCLU7022024 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CCLU7268888 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | CCLU7623827 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | DFSU6273876 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | FCIU9646476 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | FSCU8491595 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | OOCU6520910 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | OOLU8385360 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | OOLU8594101 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | OOLU8869488 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | OOLU9504015 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED CLOSED IN CELLO ON 1/30 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | SEGU5032674 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | TCNU8174236 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901039 | APL DUBLIN | COSU6173221550 | SDSMY20191226-05 | TGHU6650994 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | APHU6558742 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | APHU6824797 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | APHU7094190 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | APHU7136783 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | APHU7236000 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | BMOU4911115 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CAIU8039206 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CAIU9471889 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CMAU4357921 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CMAU4639627 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CMAU5237005 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CMAU7423040 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | CMAU7548710 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | ECMU9714310 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | ECMU9900757 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED CLOSED IN CELLO ON 01/28 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | FCIU8825728 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | FSCU9949698 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | HJMU1542077 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | SEGU5131954 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | SEGU6382379 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED CLOSED IN CELLO ON 01/28 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCKU9667567 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCLU6536766 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU2670394 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU2675014 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU3466024 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU3608812 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU3718255 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU6448106 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TCNU6737963 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TGHU6258480 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TLLU4373122 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TLLU4658589 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | APL DUBLIN | CMDUAYN0558237 | SDSMY20191226-06 | TRLU7333593 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | BMOU4446029 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | BMOU4449645 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | BMOU5324128 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CAIU8796149 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CBHU9575883 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CCLU6996153 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CCLU7229900 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CCLU7362960 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CCLU7735344 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CSLU6014370 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CSLU6300939 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | CSNU7252473 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FCIU9814965 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FCIU9933007 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FCIU9975635 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FSCU8490480 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FSCU8496278 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | FSCU8759712 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | MAGU5355034 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | OOCU7446850 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | OOLU6780323 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | OOLU8653837 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | OOLU9197536 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | TCNU9173358 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | TLLU4496472 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL DUBLIN | COSU6173221540 | SDSMY20191226-04 | UETU5113784 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-26 | 2020-01-24 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-31 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | CAIU7952695 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | GLDU7407004 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | TCKU6642930 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | TCNU2302936 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | TCNU2710178 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | TCNU2768930 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | TLLU4453737 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU7002638 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU7032313 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU8773590 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU8845616 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU8870120 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU8899037 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901039 | SEAMAX NORWALK | SSPHPKL8059803 | SDSMY20191224-02 | ZCSU8978706 | Q.PLUS L-G4.2.AF 345 | 12001227 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED CLOSED IN CELLO ON 1/29 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | SEAMAX NORWALK | SSPHPKL8059610 | SDSMY20191224-01 | ZCSU8648387 | Q.PEAK DUO L-G5.2 400 | 12002919 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | SEAMAX NORWALK | SSPHPKL8059610 | SDSMY20191224-01 | TGBU5484053 | Q.PEAK DUO L-G5.2 400 | 12002919 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | SEAMAX NORWALK | SSPHPKL8059610 | SDSMY20191224-01 | TCNU8769419 | Q.PEAK DUO L-G5.2 400 | 12002919 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71901035 | SEAMAX NORWALK | SSPHPKL8059610 | SDSMY20191224-01 | TCNU7368704 | Q.PEAK DUO L-G5.2 400 | 12002919 | 25 | 638 | 22 | 2019-12-25 | 2020-01-24 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | BEAU4698854 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | BMOU5051804 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | BSIU9359365 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CAIU9191595 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CAIU9205106 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CBHU7094256 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CBHU8647401 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CCLU7409667 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CCLU7745996 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CCLU7937812 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CSNU7029602 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CSNU7289493 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | CSNU7565210 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | DFSU7402480 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | FSCU8533242 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | SEGU4162225 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | SEGU4510399 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | TCNU3770377 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED CLOSED IN CELLO ON 1/31 (PIONEERNBNEW25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM T. ROOSEVELT | COSU6224613410 | SHTC19120284 | TCNU7032026 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2019-12-30 | 2020-01-25 |  |  | 2019-01-20 |  |  | 2020-01-30 |  |  | 2020-01-30 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | DRYU9414344 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | MOTU5818798 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | NYKU5127825 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | TCLU1840138 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | TCLU6504202 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900082 | SEASPAN ZAMBEZI | ONEYSELVD8037800 | SHTC19120268 | TCLU6732497 | Q.PEAK DUO L G5.2.1.V 395 | 30361455 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | DFSU6230642 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | FDCU0477565 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | KKFU7967475 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | NYKU0829536 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | NYKU4359446 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-01-31 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | NYKU4931470 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | CLOSED IN CELLO ON 02/05 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | ONEU0020831 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | ONEU0046585 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | TCLU7820890 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PSS-11C) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEASPAN ZAMBEZI | ONEYSELVD8848400 | SHTC19120269 | TCNU6421419 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-02 | 2020-01-29 |  |  | 2020-01-21 |  |  | 2020-02-04 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PSS-11C) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TCNU4756060 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TEMU7013577 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TEMU7056970 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TEMU7076976 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TEMU7669190 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | TGBU6274869 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | YMLU8544004 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | YMLU8723484 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | YMLU8727561 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-06 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | NAVIOS CONSTELLATION | YMLUE360774578 | SHTCS2001051 | YMLU8815410 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-05 | 2020-01-30 |  |  | 2020-01-21 |  |  | 2020-02-05 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | BSIU9703974 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | FCIU8319205 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | TCNU5416070 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED CLOSED IN CELLO ON 2/7 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | TCNU8941657 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | TGBU5767238 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU6521156 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED CLOSED IN CELLO ON 2/7 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU7051036 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU7125015 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8473904 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED CLOSED IN CELLO ON 2/7 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8549717 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8596597 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED CLOSED IN CELLO ON 2/7 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8601369 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED CLOSED IN CELLO ON 2/7 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8668167 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8714792 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8735141 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK KAWASAKI | SSPHPKL8059624 | SDSMY20191229-03 | ZCSU8917362 | Q.PEAK DUO L-G5.2 395 | 12002920 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TCNU5504653 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TCNU7258625 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TGBU5490396 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TGBU5760547 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TGBU5771670 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | TGBU7240354 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED CLOSED IN CELLO ON 02/04 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | ZCSU6532253 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | ZCSU8472446 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | ZCSU8479728 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | MAERSK KAWASAKI | SSPHPKL8059613 | SDSMY20191229-02 | ZCSU8492993 | Q.PEAK DUO L-G5.2 390 | 12002921 | 25 | 638 | 22 | 2019-12-29 | 2020-01-31 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED CLOSED IN CELLO ON 2/5 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | DFSU6150803 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | DFSU6273881 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | TCNU7895773 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | BMOU5125553 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | CBHU7081330 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | CBHU9573875 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | CCLU7270289 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | CSNU6755920 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | CXDU1370850 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | GLDU9348430 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | OOCU6948811 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | TCNU2154021 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED CLOSE IN CELLO 02/06 (PIONEERNB25) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM J. ADAMS | COSU6224624520 | SHTCS2001052 | TGBU5727132 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456 | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-28 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED (PIONEERNB25) | PIONEER-1665 JERSEY AVE
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | BMOU5813875 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-14 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/14 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | CRSU9071721 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | FCIU8331258 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-14 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/14 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | GAOU6093357 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | XINU8017891 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU6515894 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8507774 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8564814 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8698259 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8948893 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-12 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/12 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
PIONEER | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU7043051 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8679393 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901035 | MAERSK SALTORO | SSPHPKL8060115 | SDSMY20191229-04 | ZCSU8756838 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2019-12-29 | 2020-02-08 |  |  | 2020-02-03 |  |  | 2020-02-14 |  |  | 2020-02-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | BEAU5232644 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED CLOSED IN CELLO 02/14 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | BEAU5289085 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | BSIU9797232 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-18 |  |  | 2020-02-11 |  | DELIVERED CLOSED IN CELLO 02/12 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | CAIU8788499 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-18 |  |  | 2020-02-12 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | DRYU6056890 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | GCXU5201588 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-18 |  |  | 2020-02-11 |  | DELIVERED CLOSED IN CELLO 02/12 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | KKFU7889496 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | KKFU7965024 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | NYKU4260068 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TCLU6401082 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED CLOSED IN CELLO 02/14 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TCLU6405010 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-18 |  |  | 2020-02-11 |  | DELIVERED CLOSED IN CELLO 02/12 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TCLU8843817 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-18 |  |  | 2020-02-11 |  | DELIVERED CLOSED IN CELLO 02/12 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TCNU4274828 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TLLU5683797 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-13 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001001 | AL QIBLA | ONEYPKGA00706500 | SDSMY20200113-01 | TRLU6717763 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-12 | 2020-02-10 |  |  | 2020-02-04 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | BSIU9397093 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | RFCU5020263 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TCNU2767867 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TCNU4246908 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TCNU4346790 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TCNU4565736 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-19 |  | DELIVERED CLOSED CELLO 2/20 (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TCNU6908686 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TEMU6675481 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TGBU5414797 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | TGBU5492742 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | ZCSU6540984 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | ZCSU7076950 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-18 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | ZCSU8581827 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900098 | CPO BREMEN | ZIMUSEL7012952 | NEDFSEATSSE53286 | ZCSU8935999 | Q.PEAK DUO L G5.3.0.V 400 | 30361156R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-19 |  | DELIVERED CLOSED CELLO 2/20 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | CAAU5272802 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | CAIU4491917 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | TGBU5970348 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | TLLU5369240 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-14 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8557040 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8645602 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8648807 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8739738 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8886472 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900098 | CPO BREMEN | ZIMUSEL7012945 | NEDFSEATSSE53282 | ZCSU8912247 | Q.PEAK DUO L G5.3.0.V 390 | 30361119R | 20 | 638 | 22 | 2020-01-10 | 2020-02-12 |  |  | 2020-02-07 |  |  | 2020-02-19 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561074 | SDSMY20200115-05 | DFSU7821233 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-24 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561074 | SDSMY20200115-05 | CMAU4832385 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED CLOSED IN CELLO ON 2/18 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | APHU7130975 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSED CELLO 2/19 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | APHU7388342 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSED CELLO 2/19 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | BMOU4356584 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | CAIU8278258 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | CMAU4610156 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | CMAU5043648 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | CMAU7440048 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSED CELLO 2/19 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | ECMU9546108 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | ECMU9812810 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | ECMU9833216 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | ECMU9894422 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | FSCU8071648 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | GESU4127560 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | INKU6465861 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCKU9695851 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCLU5063720 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCLU6587634 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCLU9669886 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCNU5195750 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCNU5671326 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCNU7647139 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TCNU9621513 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TEMU6343954 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TEMU8232559 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TGBU5224708 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901037 | APL MIAMI | CMDUAYN0561071 | SDSMY20200115-04 | TGHU9845897 | Q.PEAK DUO-G7 325 | 12002484R | 20 | 832 | 26 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | CMAU4470202 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-24 |  |  | 2020-02-21 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/21 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | CMAU5887227 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/20 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | CMAU7113317 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-21 |  |  | 2020-02-24 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/24 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | CMAU7311919 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | FCIU8410439 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | GESU4898079 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | GESU6771308 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-24 |  |  | 2020-02-21 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/21 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | TCNU7220229 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/20 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | TGBU5066623 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-21 |  |  | 2020-02-24 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/24 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561065 | SDSMY20200115-02 | TGHU6723112 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | AMFU8883287 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | APHU6248618 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU4550801 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED CLOSED IN CELLO ON 2/18 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU4619744 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU5303745 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-24 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU1110667 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | APHU6338521 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | APHU6427779 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | APHU6761240 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | BMOU6406323 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | BSIU9178789 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CAIU9750369 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CAXU8219581 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU5782632 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU7227963 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CMAU7816475 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | CSOU4104563 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-24 |  |  | 2020-02-21 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/21 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | FSCU8989700 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | GESU5532021 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | MAGU5338037 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | SEGU4984295 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCKU6284754 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCLU1886083 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCLU6559376 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU1182142 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-20 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER (Monroe, NJ) 2/20 | S&D Transfer, Inc. (Navisun) - Monroe Twp, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU1467314 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU4316060 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU5362456 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TCNU9298400 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901034 | APL MIAMI | CMDUAYN0561055 | SDSMY20200115-01 | TLLU5109557 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/19 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | CAIU8617074 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | CLHU9073864 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | CMAU4362867 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | CMAU4930680 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | CMAU5123194 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | GESU5471754 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | TCKU6230001 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | TCLU9431964 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | TCNU1096609 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/18 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
CUSTOMER SITE | 71901035 | APL MIAMI | CMDUAYN0561069 | SDSMY20200115-03 | TCNU5298552 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-16 | 2020-02-13 |  |  | 2020-02-04 |  |  | 2020-02-20 |  |  | 2020-02-17 |  | PO# Hanwha-MA-01C; DIRECT DELIVERED TO CUSTOMER 2/17 | S&D Transfer, Inc. (Navisun) - Carnbury, NJ
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | CMAU4028320 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-19 |  | DELIVERED CLOSE IN CELLO ON 02/20 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | CMAU4881179 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED CLOSED CELLO 2/21 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | ECMU9767808 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED CLOSED CELLO 2/21 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | FCIU8765125 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | GESU5243029 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | GESU6105554 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | GESU6928655 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TCLU1506917 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TCNU6382056 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TCNU9666020 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TEMU6437354 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TGHU9584685 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TLLU4350739 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TLLU4443718 | Q.PEAK DUO BLK G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000008 | CMA CGM MAGELLAN | CMDUSEL0933413 | NEDFSEATSSE53534 | TCNU5037477 | Q.PEAK DUO BLK G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED CLOSED CELLO 2/21 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | APHU6623513 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED CLOSED CELLO 2/21 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | APHU7249820 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-20 |  | DELIVERED CLOSED CELLO 2/21 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | BMOU5342820 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | CMAU5564712 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | CMAU6297610 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | CMAU6489320 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | CMAU7388459 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | DFSU6327000 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | SEGU4626711 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | SEGU4632592 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | TEMU7784661 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | TLLU4920195 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-25 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | TRLU5922526 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933308 | NEDFSEATSSE53517 | TRLU6707889 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933299 | NEDFSEATSSE53520 | CMAU4754132 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-19 |  | DELIVERED CLOSE IN CELLO ON 02/20 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM MAGELLAN | CMDUSEL0933299 | NEDFSEATSSE53520 | TCNU2671317 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-24 | 2020-02-17 |  |  | 2020-02-11 |  |  | 2020-02-21 |  |  | 2020-02-19 |  | DELIVERED CLOSE IN CELLO ON 02/20 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | SEGU5778405 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | TCNU8775140 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | TEMU6753218 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | TLLU4777103 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU7046127 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU8738578 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU8763415 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU8906558 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU8976067 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | SEAMAX NEW HAVEN | ZlMUSEL7013075 | NEDFSEATSSE53387 | ZCSU8994250 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | CRSU9052399 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | GAOU6443178 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | RFCU5106520 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | TCNU5781724 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | TCNU8546565 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | TEMU6756304 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | TGBU5413229 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | ZCSU7073210 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | ZCSU8452413 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | ZCSU8493433 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7012944 | NEDFSEATSSE53393 | ZCSU8697545 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7013073 | NEDFSEATSSE53390 | CAIU4251156 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7013073 | NEDFSEATSSE53390 | ZCSU8651225 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | SEAMAX NEW HAVEN | ZIMUSEL7013073 | NEDFSEATSSE53390 | ZCSU8697360 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | BMOU4069985 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | CAIU9224282 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | CRSU9066638 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | DFSU6326554 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | DRYU9321241 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | FCIU8691629 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | FSCU8090437 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | FSCU8254818 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | GAOU6440693 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | GAOU6451039 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | SEGU5682793 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | SEGU5763977 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU4341947 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU4562697 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU5334686 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU5368768 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU5407210 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU6222145 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU6909701 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU8239105 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU8549939 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TCNU8704320 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TEMU6772075 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | TGBU7163047 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU7031451 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU7058175 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8469993 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8473252 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-25 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8617030 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8683562 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8739023 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8817070 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8859292 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8889701 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-21 |  | DELIVERED CLOSED IN CELLO ON 2/24 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8915272 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | SEAMAX NEW HAVEN | ZIMUSEL7013306 | NEDFSEATSSE53392 | ZCSU8955974 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-17 | 2020-02-19 |  |  | 2020-02-13 |  |  | 2020-02-26 |  |  | 2020-02-24 |  | DELIVERED CLOSED IN CELLO ON 02/25 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | TCKU6889494 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | HASU4816811 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | SUDU8642990 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | SUDU6603150 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | MRKU2743950 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK SHENZHEN | MAEU591202371 | TWSC20010505 | MSKU1802480 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | FSCU8314199 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | HASU4905204 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRKU4422034 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRKU4748530 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRKU5659191 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED CLOSED IN CELLO 2/28 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRKU5665569 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRSU3173578 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRSU3632960 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MRSU3806022 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU0346447 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU0591552 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU0646249 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU1535907 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU1978335 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED CLOSED IN CELLO 2/28 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU8557390 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 03/02 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | MSKU9241323 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | PONU8111813 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | PONU8176780 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED CLOSE IN CELLO 02/27 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | SUDU6794102 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED CLOSED IN CELLO 2/28 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | TCKU6625911 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 03/02 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | TCKU6820456 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 03/02 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | TCLU5291735 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | TCNU1494602 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK SHENZHEN | MAEU590960893 | TWSC20010471 | TLLU5354451 | Q.PEAK DUO L-G7.2.1.V395 | 30367455R | 20 | 638 | 22 | 2020-01-26 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | CAIU9353530 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | DRYU9489786 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | FDCU0550964 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | GCXU5239557 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED CLOSED IN CELLO 2/28 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | GESU6733186 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | MOTU0649062 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU0707754 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU4339964 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED CLOSED IN CELLO 2/28 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU4445971 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU4774982 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU4872079 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU4932579 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU5675222 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU5935269 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | NYKU5960153 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | ONEU0179839 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | TCLU6243768 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | TCLU6628498 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | TCNU5797700 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001001 | ANTWERPEN EXPRESS | ONEYPKGA00307900 | SDSMY20200118-01 | TRLU7393859 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-01-19 | 2020-02-23 |  |  | 2020-02-19 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | CAIU7411509 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | CMAU4614022 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | CMAU4852714 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | CMAU5238547 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | ECMU9531427 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | ECMU9750580 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | FCIU8832542 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | FCIU9285115 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | GESU5814581 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | GESU6452511 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | MAGU5751755 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | MAGU5754409 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | SEGU4989830 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | SEGU6361355 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TCLU1724945 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TCLU5047307 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TGHU6357142 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TGHU9655156 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TLLU4257420 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0561778 | SDSMY20200130-02 | TLLU5103862 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | APHU7076750 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | BEAU4088661 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | BSIU9281225 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | CMAU4254395 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | CMAU4790356 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | CMAU5161759 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-25 |  | DELIVERED CLOSED IN CELLO 2/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | CMAU5709380 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | ECMU9764270 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | TEMU7753655 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED CLOSED IN CELLO 2/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562944 | SDSMY20200130-03 | TGHU6124095 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | APHU6911356 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | CMAU4303205 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | CAIU8929299 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | CMAU4464010 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | SEGU6060264 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72001002 | CMA CGM THALASSA | CMDUAYN0562937 | SDSMY20200130-04 | TGBU5289930 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | APHU6682985 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | APHU6841095 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | CAIU9436790 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | CMAU7453997 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | CMAU7629860 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | CMAU7969324 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | GESU5732328 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TCLU8467535 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TCNU4147187 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TCNU7337283 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TEMU8242053 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TEMU8437008 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TGHU6292720 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0562898 | SDSMY20200130-05 | TGHU9300900 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | APHU6699951 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | APHU6783255 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | APHU7165837 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | APHU7184251 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | APHU7233090 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | BEAU4132846 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CAIU9077221 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CAIU9604791 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4034512 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4220013 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4284867 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4474430 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4719050 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU4855441 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU5259642 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU7019527 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | CMAU7201378 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | ECMU9829047 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | GESU5582568 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | GESU6933815 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCLU9635572 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU3077552 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU3601309 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU4585007 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU6761039 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU7052038 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TCNU9926003 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | TGBU6983334 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-28 |  | DELIVERED CLOSED IN CELLO 2/29 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THALASSA | CMDUAYN0561885 | SDSMY20200130-01 | XINU8190192 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-02-24 |  |  | 2020-02-21 |  |  | 2020-02-28 |  |  | 2020-02-27 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | BSIU9709904 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | TCNU5784298 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | FCIU9040154 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | ZCSU8238401 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | CRSU9019554 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | JXLU8932829 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | ZCSU8681750 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | ZCSU7031744 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | ZCSU8769671 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | GUTHORM MAERSK | ZlMUSEL7014173 | NEDFSEATSSE53693 | ZCSU7027786 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-02 | 2020-02-27 |  |  | 2020-02-24 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | BEAU4986399 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | CAIU8533841 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | CAIU9282930 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | FSCU7167787 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | GESU5925029 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | HLBU1993447 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | HLBU2194430 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | HLXU6469384 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | RFCU5092725 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | TCNU8788872 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | UACU5296757 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | UACU5550291 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | UACU5917200 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | EXPRESS ROME | HLCUKUL200111300 | SDSMY20200123-01 | UACU6038187 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-26 | 2020-02-28 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | MOTU0610883 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | NYKU4399120 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | NYKU5151082 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCLU8514072 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCLU9373678 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCLU9703830 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCNU4423710 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCNU7307191 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TCNU7886576 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01467300 | SDSMY20200120-02 | TLLU5596347 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | FDCU0443396 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | KKFU7865576 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU0777371 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU0818948 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU4332677 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU4788311 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU4901979 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU5170760 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | NYKU5707593 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | ONEU0331094 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TCLU7874650 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TCLU9458878 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TCNU3036147 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TCNU3943472 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TGCU0208591 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA01228500 | SDSMY20200120-03 | TLLU5569737 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | BEAU5247412 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | CAIU8056203 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | CAIU8702073 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | CAIU9505232 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | DRYU9532352 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | FDCU0474838 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | KKFU7611041 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | KKFU7809905 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | KKFU7948161 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | MOTU0601834 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | MOTU0742067 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | NYKU4382467 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | NYKU5105770 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | NYKU5176624 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | NYKU5827855 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | ONEU0001847 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-02 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | ONEU0158332 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | SEGU5050997 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-03 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCLU5316010 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCLU8290645 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCLU8300830 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-06 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU4446167 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU4815732 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU5417076 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU5733069 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU5977574 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU6481547 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TCNU9420334 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TLLU5636429 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | MOL PARADISE | ONEYPKGA00584900 | SDSMY20200120-01 | TRLU5816993 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-20 | 2020-02-29 |  |  | 2020-02-25 |  |  | 2020-03-05 |  |  | 2020-03-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | BMOU5649150 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU4582429 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU4973845 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU5488973 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU5520226 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED CLOSED OUT IN CELLO ON 03/06 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | DFSU6660221 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | FCIU8108898 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | HJCU1653379 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCKU6264491 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCKU9769173 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCLU5027260 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCNU1185028 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCNU6110361 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-09 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TEMU8581313 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TGBU5577963 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TGHU6325891 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TRLU7025965 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TRLU7575977 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-09 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | APHU6591566 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | APHU7344880 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | BMOU4421674 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CARU9949640 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU4268948 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU4809955 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | CMAU5874261 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | FCIU9326045 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | FCIU9423765 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED CLOSED OUT IN CELLO ON 03/06 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | GESU5592226 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCKU6232241 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED CLOSED OUT IN CELLO ON 03/06 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCNU2832047 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TCNU2951215 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED CLOSED OUT IN CELLO ON 03/06 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VESPUCCI | CMDUSEL0934593 | NEDFSEATSSE53798 | TLLU4334152 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-09 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | APHU6557561 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | APHU7399481 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | CLHU8906605 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | CMAU4329771 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | CMAU5057235 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | CMAU6105277 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | CMAU7930003 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | ECMU9909610 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | GESU5775187 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | TCKU6390334 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | TCNU5174905 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | TCNU7312747 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0935052 | NEDFSEATSSE53797 | TLLU4643758 | Q.PEAK DUO L-G7.2.1.V 395W | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | FCIU8469904 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | AMFU8856152 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU6653333 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU6866299 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU6888019 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU6890470 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU7111722 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | APHU7215286 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BEAU4084096 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BEAU4089945 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BEAU4129992 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BMOU5288653 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BMOU5609970 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BMOU5664935 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | BMOU5865586 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CAIU8303480 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CAIU9617119 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CLHU9109062 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU4010320 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU4897600 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU4906981 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU5273614 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU5403913 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU5461606 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU5634065 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU5735733 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU6156947 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU6181580 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU6332901 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU7538498 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CMAU7769326 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CRSU9160388 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | CRXU9893279 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | FSCU9170244 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | FSCU9396951 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | SEGU6421794 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCLU5060612 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCLU6772329 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCLU8462683 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCLU9602882 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCNU2198945 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCNU2946944 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCNU3075225 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-09 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCNU3932138 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-13 |  |  | 2020-03-12 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TCNU3940540 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TEMU6389180 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TEMU8386528 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO 3/9 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TEMU8440866 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TGHU9455380 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED CLOSED IN CELLO 03/04 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | TLLU4265811 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000002 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0934479 | NEDFSEATSSE53799 | UETU5559014 | Q.PEAK DUO L-G7.2.1.V400 | 30367456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | APHU6629764 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | CMAU4261429 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | FCIU9354670 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | GESU6875787 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-04 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | GLDU7455580 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | TCNU4033970 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-09 |  |  | 2020-03-04 |  | DELIVERED CLOSED IN CELLO 3/5 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 71900093 | CMA CGM AMERIGO VES PUCCI | CMDUSEL0936968 | NEDFSEATSSE53825 | TGHU9509697 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-26 |  |  | 2020-03-06 |  |  | 2020-03-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | APHU6634668 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | APHU7054387 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | CAIU9731414 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | CMAU4205580 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | CMAU4628113 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | CMAU5379226 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | CMAU6009484 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | FCIU9090900 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | FCIU9216027 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | FSCU8989572 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | GESU5692570 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | GESU5903360 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | GESU6089221 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | GESU6089920 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | GESU6806220 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | TCNU5097922 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-10 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | TCNU6544199 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | CMA CGM THAMES | CMDUAYN0564686 | SDSMY20200206-01 | TGBU5198553 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-07 | 2020-03-02 |  |  | 2020-02-28 |  |  | 2020-03-06 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PSS | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01474800 | SDSMY20200130-08 | BSIU9809396 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01474800 | SDSMY20200130-08 | DRYU9932430 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01474800 | SDSMY20200130-08 | NYKU0799030 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01474800 | SDSMY20200130-08 | NYKU4996953 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01474800 | SDSMY20200130-08 | TCNU4872835 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001003 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01473700 | SDSMY20200130-06 | KKFU7750957 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001003 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01473700 | SDSMY20200130-06 | KKFU8158325 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001003 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01473700 | SDSMY20200130-06 | NYKU0843663 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001003 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01473700 | SDSMY20200130-06 | TCLU1534631 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001003 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01473700 | SDSMY20200130-06 | TCLU9658177 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | BEAU4599131 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | DRYU6013327 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | DRYU9206567 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | FCIU9959969 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | FDCU0394136 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | FDCU0526192 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | GESU6222000 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | GESU6518408 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | KKFU7648708 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | KKFU8148625 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | MOTU0795540 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | MOTU5813008 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4000097 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4200080 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4230280 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4295737 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4371077 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4397364 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4763165 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4813796 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4889955 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSE IN CELLO 03/11 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU4957480 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSE IN CELLO 03/11 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU5885661 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | NYKU5932450 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCLU7811271 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCLU7982248 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCLU8572248 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCLU9214779 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCLU9465630 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-11 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCNU5155799 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSE IN CELLO 03/11 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCNU9383400 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSE IN CELLO 03/11 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TCNU9498712 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSE IN CELLO 03/11 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TEMU6523914 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TGBU5189510 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TGCU0198282 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TLLU4601367 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TLLU5601802 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TRLU7602732 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | TRLU8200825 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | GEORGE WASHINGTON BRIDGE | ONEYPKGA00589700 | SDSMY20200130-07 | UETU5335499 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 03/13 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | GCXU5240455 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED CLOSED IN CELLO ON 3/6 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | KKFU8079062 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO ON 3/10 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | NYKU4359106 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | NYKU4721107 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED CLOSED IN CELLO ON 3/9 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | ONEU0198124 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | TCLU9641467 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | TCNU8006715 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | TCNU9419462 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-06 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001006 | GEORGE WASHINGTON BRIDGE | ONEYPKGA01475900 | SDSMY20200130-09 | TLLU4020700 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-01-30 | 2020-03-03 |  |  | 2020-02-28 |  |  | 2020-03-09 |  |  | 2020-03-05 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | BMOU5178213 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | BSIU9212543 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | CAIU7199067 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | CAIU7366441 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | CAIU7641728 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | CAIU8917662 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | HMMU6265542 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000002 | MAERSK YUKON | HDMUBUWB4974788 | NEDFSEATSSE53919 | TCNU5707007 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | BMOU5199469 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | CAIU7133162 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | CAIU7489385 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | CAIU9975597 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | HDMU6852351 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-13 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | HDMU6853337 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | HMMU6153049 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | HMMU6153603 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | HMMU6285981 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | KOCU4284940 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-12 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | TCNU7604266 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | TCNU7899038 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | TEMU7540048 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED CLOSED IN CELLO 3/11 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | TGBU6226270 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974502 | NEDFSEATSSE53974 | TRLU8052538 | Q.PEAK DUO BLK G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | CAIU7440390 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | CAIU7467806 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | HDMU6802200 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | KOCU4281849 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | SEGU5844744 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000011 | MAERSK YUKON | HDMUBUWB4974239 | NEDFSEATSSE53948 | TCNU7671243 | Q.PEAK DUO BLK G6+ 335 | 30375108R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | BMOU4662500 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU4350842 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU7155114 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU7366842 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU7481445 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU7504710 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CAIU9962603 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | DFSU6671972 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | GAOU6192160 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | GCXU5020912 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | HDMU6546691 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | HDMU6566466 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | HMMU6043313 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | HMMU6126594 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | TGBU6165575 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | CLKU5018181 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | DRYU9375382 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | HMMU6069787 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000003 | MAERSK YUKON | HDMUBUWB4974545 | NEDFSEATSSE53920 | TGBU5885375 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED CLOSED IN CELLO 3/10 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | DFSU6216114 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | DFSU6245806 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | DFSU6480934 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HDMU6495402 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HDMU6579946 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TGBU6356170 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BHCU4990796 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BMOU4008193 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BMOU4124531 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BMOU4150844 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BMOU4690987 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BSIU9192684 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BSIU9201889 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BSIU9286931 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | BSIU9954100 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAAU5039468 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAIU7402148 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-19 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAIU7451116 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAIU7663579 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAIU9961124 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | CAIU9963467 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | GAOU6212184 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | GAOU6228663 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | GAOU6346007 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HDMU6657592 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HDMU6847083 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HDMU6865750 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6128133 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6167910 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 3/16 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6180640 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6195635 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-18 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6298485 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | HMMU6316275 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4018853 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4034577 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-18 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4066872 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-18 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4096542 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4193440 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-19 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4198164 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4223499 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4257903 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | KOCU4290780 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | SEGU6010345 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-18 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TCNU5101745 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TCNU6874945 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TCNU6929159 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TCNU7627596 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TGBU6341247 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TGBU6342454 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | TGBU6476026 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/18 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72000002 | MAERSK YUKON | HDMUBUWB4974407 | NEDFSEATSSE53921 | WFHU5170204 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | CAIU4332828 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | TCKU7152372 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | TGBU7245675 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | XINU8095600 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | ZCSU6504312 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | ZCSU6544830 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | ZCSU8964580 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | CAIU4429464 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | GAOU6438823 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | SLSU8049712 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | TCNU1041714 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | ZCSU8764999 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK YUKON | ZIMUSEL7016344 | NEDFSEATSSE54000 | ZCSU8835330 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | BSIU9950001 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | CAIU7132696 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | CAIU7691143 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | CAIU8671049 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | DFSU6752185 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | GAOU6172440 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | GCXU5013507 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | GLDU9984427 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | HDMU6511340 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | KOCU4036836 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | KOCU4299093 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | TCNU5084632 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | TGBU6468587 | Q.PEAK DUO BLK-G6+ 340 | 30375109R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | CAIU7198878 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | CAIU8116935 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | HDMU6637003 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | HDMU6858690 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-11 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | KOCU4251422 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED CLOSED IN CELLO 3/17 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000011 | MAERSK YUKON | HDMUBUWB4974679 | NEDFSEATSSE53980 | KOCU4300595 | Q.PEAK DUO BLK-G6+ 345 | 30375110R | 20 | 768 | 24 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-16 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
PSS | 71900082 | MAERSK YUKON | ZIMUSEL7015969 | NEDFSEATSSE53947 | FCIU8744837 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED CLOSED IN CELLO 3/12 (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900082 | MAERSK YUKON | ZIMUSEL7015969 | NEDFSEATSSE53947 | TGBU7159659 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED CLOSED IN CELLO 3/12 (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900082 | MAERSK YUKON | ZIMUSEL7015969 | NEDFSEATSSE53947 | ZCSU7110099 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900082 | MAERSK YUKON | ZIMUSEL7015969 | NEDFSEATSSE53947 | ZCSU8733072 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 71900082 | MAERSK YUKON | ZIMUSEL7015969 | NEDFSEATSSE53947 | ZCSU8815669 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-09 | 2020-03-04 |  |  | 2020-02-28 |  |  | 2020-03-10 |  |  | 2020-03-12 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 71900082 | MAERSK SYDNEY | ZIMUSEL7013461 | NEDFSEATSSE53649 | TCLU5138109 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-01-27 | 2020-03-08 |  |  | 2020-03-03 |  |  | 2020-03-12 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 3/13 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900082 | MAERSK SYDNEY | ZIMUSEL7013461 | NEDFSEATSSE53649 | TCNU4765307 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-01-27 | 2020-03-08 |  |  | 2020-03-03 |  |  | 2020-03-12 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 3/13 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900082 | MAERSK SYDNEY | ZIMUSEL7013461 | NEDFSEATSSE53649 | TCNU5832950 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-01-27 | 2020-03-08 |  |  | 2020-03-03 |  |  | 2020-03-12 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 3/13 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 71900082 | MAERSK SYDNEY | ZIMUSEL7013461 | NEDFSEATSSE53649 | ZCSU6553111 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-01-27 | 2020-03-08 |  |  | 2020-03-03 |  |  | 2020-03-12 |  |  | 2020-03-12 |  | DELIVERED CLOSED IN CELLO 3/13 (PIONEERNB20) | PIONEER-1665 JERSEY AVE
PIONEER | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | HDMU6849682 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 03/14 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TCLU5932309 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 03/14 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TCNU7602010 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 03/14 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TGBU6472057 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED CLOSED IN CELLO 03/14 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU4892000 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU7197552 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU7406842 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU7440554 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CLKU5002550 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | DRYU9182613 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | GAOU6183996 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | GAOU6206941 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | GAOU6373867 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | HMMU6213596 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TCNU9460553 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TGBU5887320 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | BMOU5217156 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | BSIU9229628 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAAU5134568 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU4458800 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU7319096 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | CAIU9980063 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | FCIU8825538 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | GAOU6227538 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | HDMU6808343 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | HDMU6875510 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | HMMU6229782 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | KOCU4056540 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | KOCU4279712 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | SEGU5845083 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TCNU6591971 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TEMU7255380 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TEMU7291177 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TLLU5768235 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000015 | MAERSK SHAMS | HDMUBUWB4976404 | NEDFSEATSSE54138 | TLLU5784576 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | BSIU9699534 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | DFSU6965750 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | TCNU2303470 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | TCNU2757128 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | TCNU5091251 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | TCNU5386503 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8460126 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8482043 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8536915 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8657584 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED CLOSED IN CELLO 3/19 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8677750 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8871889 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000002 | MAERSK SHAMS | ZIMUSEL7016799 | NEDFSEATSSE54137 | ZCSU8959162 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 638 | 22 | 2020-02-16 | 2020-03-11 |  |  | 2020-03-09 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | BEAU5032420 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 03/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | CAAU5458757 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 03/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | CAIU4418876 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | CAIU4423888 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 03/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | FSCU8254438 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 03/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | TCNU2752168 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | TCNU5642776 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 03/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | TLLU4460588 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED OUT IN CELLO ON 3/24 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7038630 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7141103 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7141130 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7141150 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7141947 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7142753 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7145412 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7146466 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU7152896 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU8578401 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU8610566 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062233 | SDSMY20200211-02 | ZCSU8911092 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | BMOU4519059 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | CAAU5453586 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | CAIU4419698 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | CAXU9131005 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | DFSU6027907 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | FCIU8928583 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-22 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | GCXU5079335 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | TCNU4247083 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | TCNU8188712 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | TCNU8754527 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | TEMU6675326 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7043088 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7108050 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7141377 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7153824 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7154435 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-22 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU7154570 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | AXEL MAERSK | SSPHPKL8062236 | SDSMY20200218-01 | ZCSU8590114 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-17 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
GTG | 72001010 | AXEL MAERSK | SSPHPKL8062295 | SDSMY20200218-03 | BMOU4503469 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED CELLO IN 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001010 | AXEL MAERSK | SSPHPKL8062295 | SDSMY20200218-03 | GAOU6116581 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001010 | AXEL MAERSK | SSPHPKL8062295 | SDSMY20200218-03 | TCNU2724649 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED CELLO IN 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001010 | AXEL MAERSK | SSPHPKL8062295 | SDSMY20200218-03 | ZCSU8767600 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED CELLO IN 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001010 | AXEL MAERSK | SSPHPKL8062295 | SDSMY20200218-03 | ZCSU8902911 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | BEAU5047477 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | BSIU9705555 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | CAAU5448722 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | FSCU8170086 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | RFCU5013813 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | SEGU5754933 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TCNU2313329 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TCNU4767130 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TCNU5406699 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TCNU5547505 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TEMU6772650 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TGBU5497446 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | TLLU5297639 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | UETU5275511 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | ZCSU7133031 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001013 | AXEL MAERSK | SSPHPKL8062235 | SDSMY20200218-02 | ZCSU8733811 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-19 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED (ROMARK145TR20) | ROMARK - 145A Talmadge Road
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | CAAU5239548 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | CAAU5243379 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED CELLO IN 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | CAXU8110230 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | DRYU9134908 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | FCIU8345159 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | FCIU8748175 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED CLOSED CELLO IN 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | FSCU8255141 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | GAOU6093589 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | GLDU7420217 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TCNU2302427 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TCNU2765777 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TCNU5542817 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | IMF DELIVERED ON 3/19; GTG UNLOADED ON 3/20; CLOSED IN CELLO ON 3/24 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TCNU5938449 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO ON 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TCNU6340050 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TEMU6802478 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TGBU5414462 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-19 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TGBU7068590 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TLLU4303784 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/24 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | TLLU4307413 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-20 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO 3/23 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | WFHU5196277 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO ON 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | ZCSU7145602 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-20 |  | DELIVERED CLOSED IN CELLO ON 3/23 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | ZCSU7154517 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001009 | AXEL MAERSK | SSPHPKL8062224 | SDSMY20200211-01 | ZCSU8724152 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-02-11 | 2020-03-15 |  |  | 2020-03-12 |  |  | 2020-03-19 |  |  | 2020-03-19 |  | DELIVERED CLOSED IN CELLO 3/20 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | APHU7076940 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | APHU7313981 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | BEAU4035229 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CAIU9408401 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU4380325 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU4531571 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU5536644 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-25 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU5581366 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU6187573 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU7053476 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU7681071 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | CMAU7926873 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | FCIU8755908 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | SEGU4981130 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | SEGU5241186 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | SEGU6192609 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | SEGU6317619 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | SEGU6474264 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | TCLU8633261 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | TCNU5530570 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | TGBU6541522 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | CMA CGM AQUILA | CMDUAYN0565863 | SDSMY20200220-02 | TLLU4807867 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/24 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | BMOU5089097 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | BSIU9634024 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CBHU8608046 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CCLU7271177 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CSNU6017103 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CSNU6332358 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CSNU7054884 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | CSNU7083877 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | DFSU7464624 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | DRYU9751920 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | FCIU9700113 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | FCIU9909037 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | OOLU9876429 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | OOLU9934227 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | TCNU3385278 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | TCNU3385365 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | TCNU3642967 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | TCNU7204085 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | TCNU8877820 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-23 |  | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001010 | CMA CGM AQUILA | COSU6173235660 | SDSMY20200220-01 | UETU5181578 | Q.PEAK DUO-G7 330 | 12002483R | 20 | 832 | 26 | 2020-02-21 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-24 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | BMOU4507715 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | DFSU6326003 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | DRYU9065108 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | FCIU8920725 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | FSCU8224500 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU2606570 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU4207558 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU4428081 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU6825426 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU8779000 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU8779593 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TCNU8897831 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TEMU6798378 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TGBU7130300 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TLLU4859834 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU6531745 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU7071583 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8465560 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8584770 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8598120 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8717488 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8814148 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8862188 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8909243 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8940151 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | CAAU5242670 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | CAIU9226500 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | GAOU6272096 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | JXLU8945744 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | SEGU5199260 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | TLLU4309993 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | UETU5271455 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8632550 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-24 |  | DELIVERED CLOSED IN CELLO 03/25 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GEROG MAERSK | ZIMUSEL7017200 | NEDFSEATSSE54261 | ZCSU8644545 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (11C20) | PSS-11C NICHOLAS COURT
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | BMOU4586571 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-27 |  | IMF DELIVERED ON 3/25; GTG UNLOADED, CLOSED 3/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | BMOU5165730 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | BSIU9942583 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | BSIU9951815 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | CAIU7140963 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | CAIU7449757 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | CAIU7474575 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | CAIU7517492 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | DFSU6622561 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | DFSU6671273 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | GAOU6161847 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HDMU6495526 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HDMU6497730 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HDMU6524856 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HDMU6532316 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HDMU6652878 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HMMU6005123 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HMMU6168990 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | HMMU6246774 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | KOCU4073790 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | SEGU6045110 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72000013 | GEROG MAERSK | HDMUBUWB4979294 | NEDFSEATSSE54345 | TCNU6875520 | Q.PEAK DUO L-G8.3.1.V420 | 30382860R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | GAOU6447527 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | TCNU8935654 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | TGBU5480865 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20) | GTG - 201 BAY AVE
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | ZCSU6512468 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | ZCSU6531621 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 3/30 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | ZCSU6533692 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 71900096 | GEROG MAERSK | ZIMUSEL7017828 | NEDFSEATSSE54317 | ZCSU7087002 | Q.PEAK DUO L G5.2.1.V 395 | 30361455R | 20 | 638 | 22 | 2020-02-23 | 2020-03-20 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | BMOU4509282 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | BSIU9216831 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | CAAU5458090 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | FSCU8153469 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | FSCU8218805 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | HCIU8012606 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TCNU1832530 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TCNU2302005 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TCNU2311943 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TCNU2758633 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TGBU7088560 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TGBU7238017 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | TGBU7262348 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU6529413 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7109143 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7146342 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7146363 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7146390 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7148200 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU7150379 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU8589411 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-27 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 3/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU8603280 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU8652540 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU8667319 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-25 |  | DELIVERED CLOSED IN CELLO 03/26 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001012 | ARNOLD MAERSK | SSPHPKL8062330 | SDSMY20200218-04 | ZCSU8729750 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-19 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | BSIU9010080 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | CAXU9109887 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | CAXU9219312 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | DAYU6102034 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | GESU5204280 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | HASU4413020 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | HASU4603760 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU2548893 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU2582460 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU2798172 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU3873286 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU4016708 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU4139805 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU4279345 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU5294257 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU6281505 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MRKU6314492 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU0326815 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU0475130 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU0605764 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU0879908 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU1375270 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU1867624 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU1880924 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU8907020 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU9161660 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU9226798 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU9313758 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU9870938 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | MSKU9893770 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | PONU7422873 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | SEGU4221360 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | TCKU9597310 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-26 |  | DELIVERED CLOSED IN CELLO 03/27 (GTGNAE20) | GTG - 10 NORTH AVE. EAST
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | TCLU7225959 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001012 | ARNOLD MAERSK | MAEU591521087 | SDSMY20200223-01 | TRLU8064673 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-02-22 | 2020-03-21 |  |  | 2020-03-17 |  |  | 2020-03-26 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | BMOU5038525 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | BMOU5124080 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CBHU8561519 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CBHU8835672 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CBHU9073102 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CBHU9175022 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/31 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CBHU9489888 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED CLOSED IN CELLO 04/01 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CSLU6017929 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | CSLU6081759 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | DFSU7416230 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/31 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | DFSU7422110 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | FCIU9552696 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-27 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | FCIU9593170 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | FCIU9735212 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | FSCU8931462 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | OOLU8116210 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | OOLU8583318 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | OOLU9583565 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/31 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | SEGU5093324 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/31 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | TCLU5120732 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | TCNU2294086 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | TCNU6319177 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | TEMU7104363 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
GTG | 72001015 | CMA CGM T.JEFFERSON | COSU6173238960 | SDSMY20200226-01 | UETU5179020 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-27 | 2020-03-23 |  |  | 2020-03-19 |  |  | 2020-03-31 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (GTGBA20) | GTG - 201 BAY AVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CCLU7471663 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CCLU7428501 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CSLU6025251 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CSLU6072649 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | DELIVERED CLOSED IN CELLO 03/31 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CSLU6087654 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | DELIVERED CLOSED IN CELLO 03/31 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CSNU6646580 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | CSNU7051484 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | FCIU9730632 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | IMF delivered on 3/27; ROMARK RCVD on 3/30, CLOSED IN CELLO 03/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | FCIU9836100 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | IMF delivered on 3/27; ROMARK RCVD on 3/30, CLOSED IN CELLO 03/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | FCIU9998538 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARK145TR20) | ROMARK - 145A Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | FSCU8643065 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | DELIVERED CLOSED IN CELLO 03/31 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | FSCU8739104 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | SEGU4882694 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-30 |  | DELIVERED CLOSED IN CELLO 03/31 (ROMARK44TR20) | ROMARK - 44 Talmadge Road
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | SEGU6330987 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PIONEER | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | TCNU2188968 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | TCNU3692464 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | TEMU6112066 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | TLLU4165751 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
ROMARK | 72001002 | COSCO HOPE | COSU6173235690 | SDSMY20200207-01 | TLLU4476856 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-08 | 2020-03-24 |  |  | 2020-03-19 |  |  | 2020-03-30 |  |  | 2020-03-27 |  | DELIVERED CLOSED IN CELLO 03/30 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | APHU6933925 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | BMOU4927770 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | BMOU6407398 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | BMOU6415428 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CAIU8091225 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CAIU8974404 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CAIU9480068 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CMAU5105652 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CMAU5128658 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | CMAU7119640 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | GLDU9887068 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | MAGU5335568 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TCLU1852648 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TCNU5300032 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TCNU9466227 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-03-31 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TEMU6169122 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TGHU6241260 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000013 | COSCO SHIPPING ORCHID | CMDUSEL0942515 | NEDFSEATSSE54487 | TTNU9042664 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000015 | COSCO SHIPPING ORCHID | CMDUSEL0943007 | NEDFSEATSSE54486 | APHU6537610 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000015 | COSCO SHIPPING ORCHID | CMDUSEL0943007 | NEDFSEATSSE54486 | TCLU6619855 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000015 | COSCO SHIPPING ORCHID | CMDUSEL0943007 | NEDFSEATSSE54486 | UETU5147526 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-03-02 | 2020-03-27 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | DFSU7000290 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | GAOU6043103 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | GAOU6089721 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | TCKU7153980 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | TCNU8550858 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001015 | MAERSK SEVILLE | SSPHPKL8062345 | SDSMY20200225-04 | TCNU8937554 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001013 | MAERSK SEVILLE | SSPHPKL8062346 | SDSMY20200225-03 | TEMU6797793 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001013 | MAERSK SEVILLE | SSPHPKL8062346 | SDSMY20200225-03 | ZCSU7010248 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001013 | MAERSK SEVILLE | SSPHPKL8062346 | SDSMY20200225-03 | ZCSU8252035 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001013 | MAERSK SEVILLE | SSPHPKL8062346 | SDSMY20200225-03 | ZCSU8731953 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-02-25 | 2020-03-28 |  |  | 2020-03-23 |  |  | 2020-04-02 |  |  | 2020-04-01 |  | DELIVERED CLOSED IN CELLO 04/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | BMOU5493283 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/03(11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | FSCU9725790 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | GESU6780233 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | HLXU8310257 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | TCNU8259502 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | UACU5363958 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/03(11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200121931 | SDSMY20200225-01 | UACU5615427 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | CLHU9128062 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | HLXU8034020 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/03(11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | HLXU8426062 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/03(11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | IKSU8611960 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | TCNU8376751 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | TEMU7269764 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/06 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | NYK SWAN | HLCUKUL200216897 | SDSMY20200225-02 | UACU5568921 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-02-25 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED CLOSED IN CELLO 04/03(11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | BEAU5124228 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | BMOU4505477 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | BMOU4510827 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | BMOU4516050 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | CAIU4337985 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | DRYU9281961 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | GAOU6041482 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | GAOU6089547 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | GAOU6442865 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | SEGU5685468 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TCNU2476938 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TCNU2506122 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TCNU2969960 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TCNU8539864 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TEMU6752382 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TGBU7202673 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TGBU7236781 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TLLU4308810 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | TLLU5914598 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU6508914 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU6528490 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU7052705 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU7122295 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8594547 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8677549 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8707411 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8831150 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8928541 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8953884 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7017935 | NEDFSEATSSE54665 | ZCSU8995180 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-03 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | BSIU9752433 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | CAIU4334944 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | FCIU8690772 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | FCIU8928794 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | FSCU8163214 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | TGHU9578975 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | TLLU4591145 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | ZCSU7119202 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-08 |  |  | 2020-04-08 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | ZCSU8660382 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000013 | CLEMENTINE MAERSK | ZIMUSEL7018989 | NEDFSEATSSE54664 | ZCSU8772000 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-09 | 2020-04-01 |  |  | 2020-03-26 |  |  | 2020-04-07 |  |  | 2020-04-06 |  | DELIVERED CLOSED IN CELLO 04/07 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PSS | 72001015 | CAP ARNAUTI | MAEU591959764 | SDSMY20200302-01 | MSKU8975301 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-03 | 2020-04-03 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED CLOSED IN CELLO 04/09 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001015 | CAP ARNAUTI | MAEU591959764 | SDSMY20200302-01 | MSKU8991745 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-03 | 2020-04-03 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED CLOSED IN CELLO 04/09 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | CAIU8535016 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | CAXU9356716 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | HLXU6244217 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | HLXU6465563 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | HLXU6590966 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | HLXU8150312 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | TCLU8089728 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | TCNU8703181 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | TGBU5749424 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | UACU5199612 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001012 | MEISHAN BRIDGE | HLCUKUL200122978 | SDSMY20200303-01 | UACU5841640 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | DFSU7483938 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | GESU4283650 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | HLBU1087524 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | HLXU6425323 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | HLXU8551594 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED CLOSED IN CELLO 04/09 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | UACU5373046 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-07 |  | DELIVERED CLOSED IN CELLO 04/08 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001013 | MEISHAN BRIDGE | HLCUKUL200218245 | SDSMY20200303-02 | UACU5753262 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-08 | 2020-04-04 |  |  | 2020-03-31 |  |  | 2020-04-09 |  |  | 2020-04-08 |  | DELIVERED CLOSED IN CELLO 04/09 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | BMOU4493308 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED CLOSE IN CELLO 04/16 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | CAIU8033300 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | FSCU9569131 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | GESU6384905 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | GLDU7539016 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | GVCU5269155 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLBU1066291 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLBU2479704 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLXU6405287 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLXU6564313 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLXU8444981 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | HLXU8563553 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED CLOSE IN CELLO 04/16 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TCLU5338128 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TCLU5589910 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TCNU8252576 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TCNU9842751 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TEMU7627678 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TGHU8141893 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TGHU8883906 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TGHU8909852 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TGHU9623740 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TLLU5267700 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | TRLU6997474 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200122989 | SDSMY20200310-01 | UACU5252126 | Q.PLUS L-G4.2.AF 345 | 12001227R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | BEAU4185759 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | HLXU8041820 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | HLXU8235092 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | TCLU8118493 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-15 |  | DELIVERED CLOSE IN CELLO 04/16 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | TGHU8915346 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | TGHU9009602 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-21 |  |  | 2020-04-17 |  | DELIVERED (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | UACU5260395 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | UACU5554907 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72001019 | NYK FALCON | HLCUKUL200300290 | SDSMY20200310-02 | UACU5573240 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-10 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7288363 | Q.PEAK DUO L-G8.3.1.V 415 | 30382859R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7550597 | Q.PEAK DUO L-G8.3.1.V 415 | 30382859R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7285214 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7288717 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7509166 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-21 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7541846 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-21 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7610628 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-21 |  |  | 2020-04-17 |  | DELIVERED CLOSED IN CELLO 04/20 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7753193 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-14 |  |  | 2020-04-07 |  |  | 2020-04-20 |  |  | 2020-04-16 |  | DELIVERED CLOSED IN CELLO 4/17 (PIONEERNBNEW20) | PIONEER-2300 RT 1 North
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | BSIU9629028 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | CAIU4343632 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | DRYU9708713 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | GLDU9938801 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | GLDU9973680 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | KOCU4101720 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | SEGU5008549 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | SEGU5040263 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | SEGU5148788 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7049435 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7252587 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7278914 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7312921 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7314740 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7315010 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-04 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | HDMUBUWB4985847 | NEDFSEATSSE54869 | TEMU7416905 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 290 | 10 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/06 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | BSIU9118938 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | DFSU6300143 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | FSCU8146080 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | GAOU6100564 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | GAOU6448246 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TCNU8393701 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TGBU7081930 | Q.PEAK DUO L-G7.2.0.V 395 | 30367555R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TCNU5547953 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TGBU5415263 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TGBU7213209 | Q.PEAK DUO L-G7.2.1.V 395 | 30367455R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | GERD MAERSK | ZIMUSEL7020078 | NEDFSEATSSE54813 | TGBU5972042 | Q.PEAK DUO L-G7.2.1.V 400 | 30367456R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000025 | GERD MAERSK | ZIMUSEL7019711 | NEDFSEATSSE54814 | TCNU8543680 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | ZIMUSEL7019711 | NEDFSEATSSE54814 | TCNU5545565 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000025 | GERD MAERSK | ZIMUSEL7019711 | NEDFSEATSSE54814 | TCNU8605550 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-18 | 2020-04-29 |  |  | 2020-04-07 |  |  | 2020-05-05 |  |  | 2020-05-05 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | BMOU4723442 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | BMOU4724979 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | BMOU5532461 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | BMOU6631978 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | CAIU4975824 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | DFSU7318213 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | DFSU7378932 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | HLXU6494828 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | HLXU6560597 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | HLXU6578385 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | HLXU8005485 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | HLXU8211721 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | TCNU8259020 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-21 |  | DELIVERED CLOSED IN CELLO 04/22 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | TCNU8467260 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | TCNU9797890 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | TGHU9250287 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5132619 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5157999 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5387749 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5416106 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5571782 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5614457 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5690668 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5834770 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5891261 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72001019 | UNAYZAH | HLCUKUL200122990 | SDSMY20200317-01 | UACU5922697 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-17 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-23 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | BMOU5181897 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | CAIU7366586 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | HDMU6703975 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | HDMU6742755 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | HDMU6747171 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | HDMU6815980 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | HMMU6173277 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | KOCU4154680 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-22 |  | DELIVERED CLOSED IN CELLO 04/23 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | KOCU4223375 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
GTG | 72000025 | GUNDE MAERSK | HDMUBUWB4987611 | NEDFSEATSSE55121 | TCNU8504385 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-03-23 | 2020-04-20 |  |  | 2020-04-10 |  |  | 2020-04-24 |  |  | 2020-04-23 |  | DELIVERED CLOSED IN CELLO 04/24 (GTGSS20) | GTG - 340 South Stiles St
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | BMOU6428533 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-04-30 |  | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | CAXU9875347 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | FCIU8009128 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-30 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | FCIU8038321 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-04-30 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | GATU8586540 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLBU1204549 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-30 |  | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLBU1315500 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-29 |  | DELIVERED CLOSED IN CELLO 04/30 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLBU1555733 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-04-29 |  | DELIVERED CLOSED IN CELLO 04/30 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLBU2538788 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLXU8383280 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-30 |  | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLXU8389694 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-29 |  | DELIVERED CLOSED IN CELLO 04/30 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | HLXU8501274 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | TCLU6621446 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | TCLU9223220 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-04-29 |  | DELIVERED CLOSED IN CELLO 04/30 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | TCNU8440721 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-29 |  | DELIVERED CLOSED IN CELLO 04/30 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | UACU5060859 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-04 |  |  | 2020-05-01 |  | DELIVERED CLOSED IN CELLO 05/04 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001019 | MONACO BRIDGE | HLCUKUL200123005 | SDSMY20200323-02 | UACU5806906 | Q.PLUS L-G4.2.AF 345 | 12001434R | 20 | 638 | 22 | 2020-03-25 | 2020-04-27 |  |  | 2020-04-21 |  |  | 2020-05-01 |  |  | 2020-04-30 |  | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | BEAU5031629 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | CAIU4253483 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | FCIU8917779 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | TCNU2763476 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | TCNU4268105 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | TCNU5356582 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | TCNU8773316 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | XINU8012333 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | ZCSU7006232 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | CORNELIA MAERSK | SSPHPKL8063959 | SDSMY20200329-01 | ZCSU8622340 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-03-30 | 2020-05-02 |  |  | 2020-04-27 |  |  | 2020-05-07 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000031 | GUSTAV MAERSK | HDMUBUWB4992295 | NEDFSEATSSE55506 | HDMU6768024 | Q.PEAK DUO BLK-G5/S C.V 310W | 30359203R | 20 | 676 | 26 | 2020-04-05 | 2020-05-04 |  |  | 2020-04-27 |  |  | 2020-05-11 |  |  | 2020-05-06 |  | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063856 | SDSMY20200315-02 | ZCSU8502221 | Q.PEAK DUO L-G5.2 385 | 12002922R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063856 | SDSMY20200315-02 | TGBU7158349 | Q.PEAK DUO L-G5.2 385 | 12002922R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/12 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | CAAU5242900 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 24 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 05/11 (11C20); Total 24 pallet IDs (100000001346529 - 9 pcs, 100000001346530 - 20 pcs, 100000001346531 - 1 pc, 100000001347232 28 pcs. | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | FSCU8152014 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | HCIU8012653 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | RFCU4054926 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | TCLU8599790 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/12 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | TCNU4576772 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | TGBU5489918 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001016 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063858 | SDSMY20200315-01 | ZCSU7072949 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/12 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU5322221 | Q.PEAK DUO L-G5.2 390 | 12002652R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/12 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU5322411 | Q.PEAK DUO L-G5.2 390 | 12002652R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/13 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | ZCSU7146867 | Q.PEAK DUO L-G5.2 390 | 12002652R | 20 | 381 | 15 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED CLOSED IN CELLO 05/12 (PIONEERNB20); 1 PLT CONTAINS 2 DIFFERENT PLT IDS - 100000001345346 (3PCS) & 100000001345350 (1PC) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | GAOU6107229 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU2475654 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU2765463 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU4262299 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 610 | 26 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20); 1 PLT CONTAINS 17 PCS; 1 PLT CONTAINS 5 DIFFERENT PLT IDS TOTAL 13 PCS | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU5551927 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU7261070 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TCNU8547324 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | TEMU6801297 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-08 |  | DELIVERED CLOSED IN CELLO 5/11 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | WFHU5176563 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | ZCSU7183243 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001017 | GUSTAV MAERSK -> Seamax New Haven | SSPHPKL8063859 | SDSMY20200315-03 | ZCSU8594486 | Q.PEAK DUO L-G5.2 390 | 12002921R | 20 | 638 | 22 | 2020-03-15 | 2020-05-06 |  |  | 2020-04-30 |  |  | 2020-05-12 |  |  | 2020-05-11 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72001017 | AL QIBLA | HDMUMYWB0856652 | SDSMY20200330-05 | GCXU5029530 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-03-30 | 2020-05-07 |  |  | 2020-05-01 |  |  | 2020-05-14 |  |  | 2020-05-12 |  | DELIVERED CLOSED IN CELLO 05/15 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001017 | AL QIBLA | HDMUMYWB0856652 | SDSMY20200330-05 | CAIU7403910 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 24 | 2020-03-30 | 2020-05-07 |  |  | 2020-05-01 |  |  | 2020-05-14 |  |  | 2020-05-12 |  | DELIVERED CLOSED IN CELLO 05/12 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72001020 | MOL MOTIVATOR | HDMUMYWB0855948 | SDSMY20200330-01 | BMOU4762752 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-14 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | MOL MOTIVATOR | HDMUMYWB0855948 | SDSMY20200330-01 | HMMU6183660 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-14 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | MOL MOTIVATOR | HDMUMYWB0855948 | SDSMY20200330-01 | BSIU9266811 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-14 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4126529 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-14 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4139296 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-14 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4146823 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4150994 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4278096 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU4915893 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BMOU5168386 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | BSIU9200835 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | CAIU9981368 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | HMMU6217462 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | KOCU4027768 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | SEGU6018773 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | TCNU6790700 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001018 | MOL MOTIVATOR | HDMUMYWB0856506 | SDSMY20200330-02 | TCNU7318299 | Q.PLUS DUO L-G5.2 365 | 12002139R | 20 | 638 | 22 | 2020-03-30 | 2020-05-12 |  |  | 2020-05-05 |  |  | 2020-05-18 |  |  | 2020-05-15 |  | DELIVERED CLOSED IN CELLO ON 5/18 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | BSIU9114470 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO 05/19 (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | CAIU4305062 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | CAIU4423804 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | GAOU6133697 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | GAOU6445020 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TCNU2758926 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TCNU4251376 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TCNU8670895 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TCNU8672347 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TLLU4735793 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | TLLU4859789 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU6511965 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU6523689 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU7084981 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED CLOSED IN CELLO ON 5/20 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU7158359 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU8589258 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU8730392 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU8758738 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU8822312 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023690 | NEDFSEATSSE55816 | ZCSU8890256 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED CLOSED IN CELLO ON 5/20 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023972 | NEDFSEATSSE55818 | ZCSU7022594 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-18 |  | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | DFSU6535600 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | FSCU9216999 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | SEGU5811273 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | TCNU4250955 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | TEMU6768521 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | GUTHORM MAERSK | ZIMUSEL7023971 | NEDFSEATSSE55842 | ZCSU8685400 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-04-20 | 2020-05-13 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855951 | SDSMY20200330-04 | CAIU9822469 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855951 | SDSMY20200330-04 | TGBU6146929 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-19 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | CAIU4437705 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | CAIU7371598 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | HMMU6138065 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | HMMU6250624 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | KOCU4017630 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | KOCU4063030 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | TGBU6226201 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | TLLU5770253 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72001020 | YM WARMTH | HDMUMYWB0855949 | SDSMY20200330-03 | TLLU5772385 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-03-30 | 2020-05-14 |  |  | 2020-05-07 |  |  | 2020-05-20 |  |  | 2020-05-20 |  | DELIVERED (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | CAIU7404243 | Q.PEAK DUO BLK G5.0.3.V 310 | 30359303R | 20 | 832 | 26 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | CAIU7440620 | Q.PEAK DUO BLK G5.0.3.V 310 | 30359303R | 20 | 192 | 6 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | CAIU7440620 | Q.PEAK DUO BLK G5.0.3.V 320 | 30359305R | 20 | 640 | 20 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | TCNU7269960 | Q.PEAK DUO BLK G5.0.3.V 310 | 30359303R | 20 | 192 | 6 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | TCNU7269960 | Q.PEAK DUO BLK G5.0.3.V 315 | 30359304R | 20 | 640 | 20 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000031 | HYUNDAI HOPE | HDMUBUWB4995400 | NEDFSEATSSE55848 | TGBU6480113 | Q.PEAK DUO BLK G5.0.3.V 310 | 30359303R | 20 | 832 | 26 | 2020-04-19 | 2020-05-16 |  |  | 2020-05-11 |  |  | 2020-05-21 |  |  | 2020-05-19 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000015 | EXPRESS BERLIN | HDMUBUWB4996909 | NEDFSEATSSE56020 | BMOU4426022 | Q.PEAK DUO L-G7.2.0.V 400 | 30367556R | 20 | 638 | 22 | 2020-04-28 | 2020-05-25 |  |  | 2020-05-21 |  |  | 2020-05-29 |  |  | 2020-05-27 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | CAIU4418834 | Q.PEAK DUO BLK-G6+340 | 30375109R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | FCIU8921819 | Q.PEAK DUO BLK-G6+340 | 30375109R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | ZCSU6515451 | Q.PEAK DUO BLK-G6+340 | 30375109R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | ZCSU8982835 | Q.PEAK DUO BLK-G6+340 | 30375109R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | TEMU6797345 | Q.PEAK DUO BLK-G6+340 | 30375109R | 20 | 448 | 14 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | TEMU6797345 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 320 | 10 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-05-29 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | BMOU4502987 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | DFSU6049188 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | DFSU6496972 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | TCNU5334990 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | TCNU5406533 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | TGBU5769349 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | ZCSU8478085 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
PIONEER | 72000034 | MAERSK SHAMS | ZIMUSEL7023689 | NEDFSEATSSE56002 | ZCSU8991230 | Q.PEAK DUO BLK-G6+.0.1.V 340 | 30375209R | 20 | 768 | 24 | 2020-05-03 | 2020-05-27 |  |  | 2020-05-21 |  |  | 2020-06-02 |  |  | 2020-06-01 |  | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNB20) | PIONEER - 1665 JERSEY AVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | GCXU5015388 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4088444 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4308657 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4336915 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4339961 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4474853 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4476537 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4476619 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4644780 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | KOCU4645473 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859518 | SDSMY20200508-02 | TGBU6156758 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (ROMARKMD20); One of the pallets has 2 different IDs on the actual pallet, one side with 150000000689954 which is not on the FTD and one side with 150000000689953 which is on FTD. Advised Romark to scan with 150000000689953. | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | BMOU4144630 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | BMOU4704083 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | BMOU5160235 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | BSIU9316825 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | CAIU7298157 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | CAIU7330114 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | DFSU6195691 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | HDMU6827430 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-04 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | HMMU6196170 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | TCNU1698340 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-03 |  | DELIVERED CLOSED IN CELLO 6/4 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001026 | DALIAN EXPRESS | HDMUMYWB0859520 | SDSMY20200508-03 | TCNU5353768 | Q.PLUS DUO L-G5.2 365 | 12003546R | 20 | 638 | 22 | 2020-05-07 | 2020-06-02 |  |  | 2020-05-27 |  |  | 2020-06-08 |  |  | 2020-06-05 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DRIVE
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | HASU4051907 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MAEU8395049 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MRKU2250403 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MRKU3135831 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MRKU5386374 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MSKU1527408 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MSKU8147591 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | MSKU9458788 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | PONU7352457 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | SUDU6593290 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | TCNU9863184 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000040 | GUDRUN MAERSK | MAEU598310243 | PTIK20S05603 | TGHU6434296 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-05-17 | 2020-06-11 |  |  | 2020-06-05 |  |  | 2020-06-17 |  |  | 2020-06-15 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
ROMARK | 72001025 | MOL MARVEL | ONEYPKGA20353500 | NEDFPKGARC31226 | BSIU9659418 | Q.PLUS BFR-G4.1.AF 290 | 12000809R | 20 | 832 | 26 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001025 | MOL MARVEL | ONEYPKGA20353500 | NEDFPKGARC31226 | KKFU8145077 | Q.PLUS BFR-G4.1.AF 290 | 12000809R | 20 | 832 | 26 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | BSIU9691810 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | FDCU0635085 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | GCXU5271950 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | GESU6329791 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NYKU0734750 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NYKU4092977 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NYKU4319016 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NYKU4323309 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NYKU4736940 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | ONEU0172710 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | ONEU0279843 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | TCLU9840685 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | TCNU5950526 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-23 |  |  | 2020-06-19 |  | DELIVERED CLOSED IN CELLO 06/22 (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | TRLU7557084 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
ROMARK | 72001027 | MOL MARVEL | ONEYPKGA20354600 | NEDFPKGARC31484 | UETU5841368 | Q.PEAK DUO L-G5.2 395 | 12002920R | 20 | 638 | 22 | 2020-05-21 | 2020-06-16 |  |  | 2020-06-09 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (ROMARKMD20) / TU LABEL (NOT ok to ship) | ROMARK - 23 MACK DRIVE
PSS | 72001030 | YANTIAN EXPRESS | ONEYPKGA21985300 | NEDFPKGARF80865 | NYKU4078813 | Q.PEAK DUO L-G5.2 405 | 12002918R | 20 | 464 | 19 | 2020-05-28 | 2020-06-22 |  |  | 2020-06-16 |  |  | 2020-06-26 |  |  | 2020-06-24 |  | DELIVERED (11C20) - 16 PALLETS WITH 19 pallet IDS / TU LABEL (NOT ok to ship) | PSS-11C NICHOLAS COURT
PSS | 72001030 | YANTIAN EXPRESS | ONEYPKGA21985300 | NEDFPKGARF80865 | NYKU4292321 | Q.PEAK DUO L-G5.2 405 | 12002918R | 20 | 638 | 22 | 2020-05-28 | 2020-06-22 |  |  | 2020-06-16 |  |  | 2020-06-26 |  |  | 2020-06-24 |  | DELIVERED (11C20) / TU LABEL (NOT ok to ship) | PSS-11C NICHOLAS COURT
ROMARK | RETURN-TUV LABEL | RETURN-TUV LABEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NJ1PT3062404R | Q.PEAK DUO L G5.2 395 | 12002920R | 20 | 754 | 26 |  | 2020-06-30 | [8 empty] | 2020-06-30 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DR
ROMARK | RETURN-TUV LABEL | RETURN-TUV LABEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NJ1PT3062401R | Q.PEAK DUO L G5.2 395 | 12002920R | 20 | 754 | 26 |  | 2020-06-26 | [8 empty] | 2020-06-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DR
ROMARK | RETURN-TUV LABEL | RETURN-TUV LABEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NJ1PT3062402R | Q.PEAK DUO L G5.2 395 | 12002920R | 20 | 754 | 26 |  | 2020-06-26 | [8 empty] | 2020-06-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DR
ROMARK | RETURN-TUV LABEL | RETURN-TUV LABEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NJ7243062502R | Q.PEAK DUO L G5.2 395 | 12002920R | 20 | 696 | 24 |  | 2020-06-26 | [8 empty] | 2020-06-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DR
ROMARK | RETURN-TUV LABEL | RETURN-TUV LABEL | ONEYPKGA20354600 | NEDFPKGARC31484 | NJ7243062503R | Q.PEAK DUO L G5.2 395 | 12002920R | 20 | 696 | 24 |  | 2020-06-26 | [8 empty] | 2020-06-26 |  | DELIVERED (ROMARKMD20) | ROMARK - 23 MACK DR
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | BMOU4474946 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | BMOU4483212 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | BMOU4774080 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | DRYU9494740 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | DRYU9833124 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | DRYU9875095 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EGHU9213988 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EISU9211452 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EISU9246720 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EISU9316324 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1040969 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1159475 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1186980 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1198722 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1212564 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1259031 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1677068 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1779033 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EITU1977297 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9447574 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9731657 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9747530 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9770904 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9787785 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | EMCU9826963 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | FCIU9431098 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | HMCU9162358 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | OCGU8078157 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TCKU6447471 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TCLU6313741 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-01 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TCLU7842210 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TCNU2178738 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TCNU3753425 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001031 | CMA CGM LIBRA | EGLV091030237886 | NEDFPKGARH07156 | TLLU4870896 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-16 |  |  | 2020-07-02 |  |  | 2020-07-02 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | AXIU1607227 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | DFSU6978932 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | DRYU6025992 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | FDCU0496800 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | FSCU8556443 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | FSCU8569857 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | GESU6188862 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | KKFU7817433 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | NYKU0708391 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | NYKU0753174 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | SEGU4331412 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCLU1796694 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCLU9440483 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCLU9620042 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCNU3274905 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-29 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCNU6105703 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TCNU7086486 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TEMU7641742 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TEMU8572944 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PIONEER | 72001029 | YM UTILITY | ONEYPKGA21369600 | NEDFPKGARE84195 | TGCU0203331 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2020-05-28 | 2020-06-25 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-06-30 |  | DELIVERED (PIONEERNB20) TUV LABEL (NOT ok to ship) | Sun Energy1 Project
PSS | 72000025 | HYUNDAI DREAM | YMLUE360777119 | PTIK20S05008 | TCNU2322038 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-05-31 | 2020-06-28 |  |  | 2020-06-22 |  |  | 2020-07-01 |  |  | 2020-07-01 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | DFSU6895123 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED (11C20) | VESSEL / Good to ship; PSS-11C NICHOLAS COURT
PSS | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EGHU9183029 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED (11C20) | VESSEL / Good to ship; PSS-11C NICHOLAS COURT
PSS | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EMCU9478467 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (11C20) | VESSEL / Good to ship; PSS-11C NICHOLAS COURT
PSS | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | HMCU9162018 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED (11C20) | VESSEL / Good to ship; PSS-11C NICHOLAS COURT
PSS | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | TRLU6646084 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (11C20) | VESSEL / Good to ship; PSS-11C NICHOLAS COURT
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | BEAU5026978 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | BSIU9252398 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | BSIU9469779 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | DRYU9254987 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EGHU9265430 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EGHU9678162 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EGSU9031230 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EGSU9153096 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EISU9195454 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EISU9297501 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-01 |  | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EISU9408518 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EITU1371490 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-03 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EMCU9569119 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EMCU9648500 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | EMCU9889302 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | TCNU1659261 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | TGBU5813009 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
ROMARK | 72001032 | APL MIAMI | EGLV091030251498 | NEDFPKGARK25170 | TRLU7224123 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-04 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (ROMARKMD20) - TUV LABEL (NOT OK TO SHIP) | Sun Energy1 Project
PSS | 72001032 | APL MIAMI | EGLV091030251480 | NEDFPKGARK12776 | OCGU8003796 | Q.PEAK DUO L-G7.2 395 | 12002680R | 20 | 580 | 20 | 2020-06-05 | 2020-06-29 |  |  | 2020-06-22 |  |  | 2020-07-06 |  |  | 2020-07-02 |  | DELIVERED (11C20) - TUV LABEL (NOT ok to ship) | 18 cntrs - TUV label (no good to ship, need to be on-hold)
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | DRYU9275974 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | DRYU9827482 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | FCIU7182397 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | GAOU6221946 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | OCGU8086492 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | TCNU3119112 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72001032 | CMA CGM ELBE | EGLV091030268943 | NEDFPKGARN57825 | TGBU6112370 | Q.PEAK DUO L G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-06-11 | 2020-07-07 |  |  | 2020-06-30 |  |  | 2020-07-14 |  |  | 2020-07-10 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000037 | HYUNDAI AMBITION | HDMUBUWB5012115 | PTIK20S06607 | BSIU9334773 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000037 | HYUNDAI AMBITION | HDMUBUWB5012115 | PTIK20S06607 | CAIU7184107 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000037 | HYUNDAI AMBITION | HDMUBUWB5012115 | PTIK20S06607 | HMMU6195466 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000037 | HYUNDAI AMBITION | HDMUBUWB5012115 | PTIK20S06607 | KOCU4311687 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED CLOSED IN CELLO ON 7/29 (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000037 | HYUNDAI AMBITION | HDMUBUWB5012115 | PTIK20S06607 | DFSU6714272 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (11C20) | PSS-11C NICHOLAS COURT
PSS | 72000046 | HYUNDAI AMBITION | HDMUBUWB5013727 | PTIK20S06017 | KOCU4082317 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI AMBITION | HDMUBUWB5013727 | PTIK20S06017 | CAIU7409986 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI AMBITION | HDMUBUWB5013727 | PTIK20S06017 | HDMU6826096 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI AMBITION | HDMUBUWB5013727 | PTIK20S06017 | TCNU7096329 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI AMBITION | HDMUBUWB5013727 | PTIK20S06017 | GAOU6342742 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-21 | 2020-07-21 |  |  | 2020-07-13 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | CAIU4732716 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | HASU4457049 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | HASU5152893 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU2503543 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU2625109 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU3143014 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU3529943 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU3978230 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU4078248 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU5410906 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU5761979 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRKU6251286 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MRSU3430784 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MSKU0834009 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MSKU0995385 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MSKU1504850 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | MSKU8371744 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-27 |  | CLOSED IN CELLO 7/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | PONU8173841 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | TCLU5346838 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | GERDA MAERSK | MAEU203537977 | PUNY20060033 | TCNU5315027 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-06-28 | 2020-07-23 |  |  | 2020-07-17 |  |  | 2020-07-29 |  |  | 2020-07-28 |  | DELIVERED CLOSED IN CELLO ON 07/29 (11CZEROT) ; BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
ROMARK | 72000025 | ARTHUR MAERSK | ZIMUSEL7030284 | PUNY20060027 | SEGU5283577 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 638 | 22 | 2020-06-26 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-05 |  |  | 2020-08-04 |  | DELIVERED (ROMARKMD20)
ROMARK | 72000037 | ARTHUR MAERSK | ZIMUSEL7030285 | PUNY20060028 | TCNU5781998 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-26 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-05 |  |  | 2020-08-04 |  | DELIVERED (ROMARKMD20)
ROMARK | 72000037 | ARTHUR MAERSK | ZIMUSEL7030285 | PUNY20060028 | ZCSU8590916 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 638 | 22 | 2020-06-26 | 2020-07-30 |  |  | 2020-07-24 |  |  | 2020-08-05 |  |  | 2020-08-04 |  | DELIVERED (ROMARKMD20)
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | BSIU9200305 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/7 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | BSIU9211130 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/7 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | BSIU9934783 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | CLKU5016091 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | DFSU6876885 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | GAOU6345171 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-10 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | GCXU5015475 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED CLOSED IN CELLO ON 08/07 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | HDMU6838991 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | HMMU6141881 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | HMMU6220152 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/7 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4081687 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4228211 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4259228 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-06 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4260039 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/13 (11CZEROT); BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4303505 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | KOCU4353208 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | SEGU5829673 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | TCNU7408411 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED CLOSED IN CELLO ON 08/14 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | TCNU7606675 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-06 |  |  | 2020-08-04 |  | DELIVERED CLOSED IN CELLO ON 8/7 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI HOPE | HDMUBUWB5019460 | PTIK20S07601 | TGBU6468289 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-06 | 2020-08-01 |  |  | 2020-07-28 |  |  | 2020-08-14 |  |  | 2020-08-07 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI SPEED | HDMUBUWB5020230 | PTIK20S07604 | SEGU6036437 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-12 | 2020-08-08 |  |  | 2020-08-03 |  |  | 2020-08-13 |  |  | 2020-08-13 |  | DELIVERED CLOSED IN CELLO ON 08/14 (11CZEROT); BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI SPEED | HDMUBUWB5020230 | PTIK20S07604 | KOCU4182105 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-12 | 2020-08-08 |  |  | 2020-08-03 |  |  | 2020-08-13 |  |  | 2020-08-13 |  | DELIVERED CLOSED IN CELLO ON 08/14 (11CZEROT); BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI SPEED | HDMUBUWB5020230 | PTIK20S07604 | TCLU8441886 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-12 | 2020-08-08 |  |  | 2020-08-03 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/13 (11CZEROT); BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS | 72000046 | HYUNDAI SPEED | HDMUBUWB5020230 | PTIK20S07604 | HMMU6226994 | Q.PEAK DUO LG8P.3/BGT 405W | 30368257 | 0 | 638 | 22 | 2020-07-12 | 2020-08-08 |  |  | 2020-08-03 |  |  | 2020-08-14 |  |  | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/13 (11CZEROT); BIFACIAL SOLAR MODULES NO TARIFF | Horizontal Packaging
PSS |  | RETURN-2 DAMAGED PLT | SSPHPKL8063858 | SDSMY20200315-01 | NJ2203071501R | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 58 | 2 | [10 empty] | 2020-08-07 |  | DELIVERED CLOSED IN CELLO ON 08/11 (11C20) // Pallet ID: 150000000663552 & 150000000663520
ROMARK |  | RETURN-NJAMI1081101 | 327042303 | 327042303 | NJAMI1081101 | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 174 | 6 | [10 empty] | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/14 (ROMARKMD) // driver was not comfortable with driving up the hill at the delivery location. Driver will return to shipper and re-deliver
ROMARK |  | RETURN-NJAMI1081101 | 327042317 | 327042317 | NJAMI1081101 | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 319 | 11 | [10 empty] | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/14 (ROMARKMD) // driver was not comfortable with driving up the hill at the delivery location. Driver will return to shipper and re-deliver
ROMARK |  | RETURN-NJAMI1081101 | 327042325 | 327042325 | NJAMI1081101 | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 261 | 9 | [10 empty] | 2020-08-12 |  | DELIVERED CLOSED IN CELLO ON 08/14 (ROMARKMD) // driver was not comfortable with driving up the hill at the delivery location. Driver will return to shipper and re-deliver
PSS | Accident | RETURN-NJREEK080605R | HDMUBUWB4976404 | NEDFSEATSSE54138 | NJREEK080605R | Q.PEAK DUO L-G7.2 400 | 30367556R | 20 | 754 | 26 |  | 2020-08-17 | [8 empty] | 2020-08-17 |  | PAPERWORK CLOSED IN CELLO 08/20 Non-Value Inventory / Cell# (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | BEAU4621770 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | CXDU1673938 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | CXDU2266095 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | DRYU9291363 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | FDCU0435180 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | GESU5781929 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | GESU6230448 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | GESU6925790 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | KKFU7926100 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | MOTU0732686 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4059372 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4216701 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4398078 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4404139 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4747740 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4858168 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU4899362 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU5841236 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU5925018 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | NYKU5995653 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCKU9328120 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCLU5242812 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCLU7829075 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCLU8525328 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU4446450 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU5529311 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU5556390 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU5796030 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU6162350 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU8029120 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU8248998 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-18 |  | DELIVERED CLOSED IN CELLO ON 8/19 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TCNU9498311 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-17 |  | DELIVERED CLOSED IN CELLO 08/18 (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TEMU6837670 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TRLU5871331 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-18 |  |  | 2020-08-20 |  | DELIVERED (11C20)
PSS | 72001036 | MOL MISSION | ONEYPKGA31425700 | NEDFPKGASD58410 | TRLU7040785 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-13 |  |  | 2020-08-04 |  |  | 2020-08-19 |  |  | 2020-08-19 |  | DELIVERED (11C20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | BMOU4148683 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | BMOU5185022 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-19 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | BSIU9617900 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-19 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU4840829 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-19 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU7407788 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-19 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU7456400 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-19 |  | DELIVERED CLOSED IN CELLO 08/20 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU7477173 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU7485008 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | CAIU9937787 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | DFSU6219258 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | DFSU6480370 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | DRYU9190250 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | GAOU6173051 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO 8/21 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | GAOU6227646 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO 8/21 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | GCXU5010811 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | HDMU6641960 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | HDMU6897037 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-20 |  | DELIVERED CLOSED IN CELLO 8/21 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | HMMU6147832 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | HMMU6148778 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | HMMU6179845 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | KOCU4085960 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | KOCU4156913 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | KOCU4293979 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-24 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | TCNU7402096 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PIONEERNB20)
PIONEER | 72000054 | HYUNDAI VICTORY | HDMUBUWB5022325 | PTIK20S07608 | TEMU7315073 | Q.PEAK DUO BLK-G6P+/SC 340W | 30375309R | 20 | 676 | 26 | 2020-07-19 | 2020-08-15 |  |  | 2020-08-10 |  |  | 2020-08-20 |  |  | 2020-08-21 |  | DELIVERED CLOSED IN CELLO ON 08/24 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | KKFU7779230 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | KKFU7881047 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU0785037 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU0857158 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU4316980 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-25 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU4334010 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU4384290 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | NYKU5149871 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCLU1543802 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-25 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCLU1553544 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCLU6629410 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCLU8926824 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCLU9616042 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TCNU8273012 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001036 | YM WARMTH | ONEYPKGA31630500 | NEDFPKGASD58686 | TGHU8963410 | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | DRYU6038496 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | DRYU9360206 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | KKFU7949152 | Q.PEAK DUO L-G7.2 395 | 12004285R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | MOAU6758927 | Q.PEAK DUO L-G5.2 400 | 12002919R | 20 | 58 | 6 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED CLOSED IN CELLO on 08/28 (PIONEERNB20)- (12GP CONTAINER); 6 partial pallet IDs
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | NYKU4093572 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 116 | 8 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | NYKU4093572 | Q.PEAK DUO L-G5.2 390 | 12002652R | 20 | 522 | 20 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | NYKU4418282 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 23 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-27 |  | DELIVERED CLOSED IN CELLO ON 08/28 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | ONEU0133587 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCLU4610268 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-25 |  |  | 2020-08-26 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCLU9300901 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCNU6601200 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-25 |  | DELIVERED CLOSED IN CELLO ON 08/26 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCNU7840024 | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 522 | 24 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED CLOSED IN CELLO ON 08/31 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCNU7840024 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 29 | 1 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED CLOSED IN CELLO ON 08/31 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TCNU7840024 | Q.PEAK DUO L-G7.2 395 | 12004285R | 20 | 87 | 3 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED CLOSED IN CELLO ON 08/31 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | TEMU6838911 | Q.PEAK DUO L-G7.2 395 | 12004285R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED CLOSED IN CELLO ON 08/31 (PIONEERNB20)
PIONEER | 72001035 | YM WARMTH | ONEYPKGA31284300 | NEDFPKGASD14494 | UETU5735983 | Q.PEAK DUO L-G5.2 395 | 12002651R | 20 | 638 | 22 | 2020-07-16 | 2020-08-19 |  |  | 2020-08-06 |  |  | 2020-08-26 |  |  | 2020-08-28 |  | DELIVERED (PIONEERNB20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | BMOU4578339 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | BSIU9918308 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | DFSU6185380 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED CLOSED IN CELLO ON 09/09 (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | DFSU6192049 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | DFSU6232497 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | GCXU5013913 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED CLOSED IN CELLO ON 09/09 (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | HMMU6144622 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED CLOSED IN CELLO ON 09/09 (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | KOCU4051893 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | KOCU4281134 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | TCNU5351003 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000056 | HYUNDAI RESPECT | HDMUBUWB5026065 | PTIK20S08601 | TGBU6332991 | Q.PEAK DUO G5.0.2.V 325 | 30350206R | 20 | 832 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | BMOU4122143 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | BMOU5166803 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | CAIU7469239 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED CLOSED IN CELLO 09/11 (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | CAIU7492970 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | DFSU6882661 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | GCXU5013847 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | GCXU5034644 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6663229 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6666070 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6683781 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6704117 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6709783 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HDMU6798841 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HMMU6146287 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HMMU6280974 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | HMMU6312990 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4006235 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4132017 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4209910 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-04 |  |  | 2020-09-08 |  | DELIVERED CLOSED IN CELLO ON 09/09 (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4236074 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4311115 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | KOCU4366801 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-08 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | SEGU6011357 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | TCNU8025947 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-04 |  | DELIVERED (11C20)
PSS | 72000052 | HYUNDAI RESPECT | HDMUBUWB5026919 | PTIK20S08602 | TEMU7253238 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-02 | 2020-08-29 |  |  | 2020-08-25 |  |  | 2020-09-03 |  |  | 2020-09-03 |  | DELIVERED (11C20)
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | BSIU9344513 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-23 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU7486180 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-25 |  |  | 2020-09-24 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU7518591 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-25 |  |  | 2020-09-24 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU7707018 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-23 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU8746364 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-25 |  |  | 2020-09-24 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU9836610 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-23 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | CAIU9967020 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-23 |  | DELIVERED CLOSED ON 09/24 - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | DFSU6946832 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-23 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | GAOU6152927 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | GAOU6293587 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | HDMU6764008 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | HMMU6313553 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | KOCU4122127 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | KOCU4290711 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | KOCU4603204 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | SEGU5848708 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-25 |  |  | 2020-09-24 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | TCKU6097795 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | TGBU6149147 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-25 |  |  | 2020-09-24 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | TLLU5303876 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI DREAM | HDMUBUWB5029354 | PTIK20S08607 | TLLU5842219 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-16 | 2020-09-20 |  |  | 2020-09-08 |  |  | 2020-09-24 |  |  | 2020-09-22 |  | DELIVERED CLOSED IN CELLO ON 9/23 (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | KOCU4456660 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | KOCU4488754 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | KOCU4660821 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | TLLU5287610 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-05 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | BMOU4141333 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-01 |  |  | 2020-10-01 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | CAIU7690640 | Q.PEAK DUO BLK-G5/SC.V 315 | 30359204R | 20 | 98 | 4 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-09-30 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | CAIU7690640 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 209 | 9 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-09-30 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | HMMU6188317 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-09-29 |  | CLOSED IN CELLO 9/30 (11C20)
PSS | 72000062 | HYUNDAI SMART | HDMUBUWB5031204 | PTIK20S08618 | KOCU4478680 | Q.PEAK DUO BLK-G5/SC.V 320 | 30359205R | 20 | 676 | 26 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-09-30 |  | DELIVERED CLOSED IN CELLO ON 10/02 (11C20)
PSS | 72000058 | HYUNDAI SMART | HDMUBUWB5031939 | PTIK20S08621 | BMOU5178785 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI SMART | HDMUBUWB5031939 | PTIK20S08621 | KOCU4480305 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI SMART | HDMUBUWB5031939 | PTIK20S08621 | SEGU5150281 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI SMART | HDMUBUWB5031939 | PTIK20S08621 | TCNU7649620 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-08-23 | 2020-09-27 |  |  | 2020-09-15 |  |  | 2020-10-02 |  |  | 2020-10-01 |  | DELIVERED (11CZEROT) - BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000062 | HYUNDAI HONOUR | HDMUBUWB5032642 | PTIK20S08625 | CAAU5143277 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-08-31 | 2020-10-03 |  |  | 2020-09-23 |  |  | 2020-10-09 |  |  | 2020-10-07 |  | DELIVERED CLOSED IN CELLO ON 10/08 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI HONOUR | HDMUBUWB5032642 | PTIK20S08625 | DFSU6246090 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-08-31 | 2020-10-03 |  |  | 2020-09-23 |  |  | 2020-10-09 |  |  | 2020-10-07 |  | DELIVERED CLOSED IN CELLO ON 10/08 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI HONOUR | HDMUBUWB5032642 | PTIK20S08625 | KOCU4476012 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-08-31 | 2020-10-03 |  |  | 2020-09-23 |  |  | 2020-10-09 |  |  | 2020-10-07 |  | DELIVERED CLOSED IN CELLO ON 10/08 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI HONOUR | HDMUBUWB5032642 | PTIK20S08625 | SEGU6018860 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-08-31 | 2020-10-03 |  |  | 2020-09-23 |  |  | 2020-10-08 |  |  | 2020-10-07 |  | DELIVERED CLOSED IN CELLO ON 10/08 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI HONOUR | HDMUBUWB5032642 | PTIK20S08625 | TEMU7258097 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-08-31 | 2020-10-03 |  |  | 2020-09-23 |  |  | 2020-10-08 |  |  | 2020-10-07 |  | DELIVERED CLOSED IN CELLO ON 10/08 (PIONEERNB20)
PSS | 72000069 | SEAMAX NEW HAVEN | ZIMUSEL7034531 | PTIK20S09611 | ZCSU8781825 | Q.PEAK DUO L-G8.2.2.V 420 | 30382960R | 20 | 290 | 10 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED CLOSED ON 10/16 (11C20)
PSS | 72000069 | SEAMAX NEW HAVEN | ZIMUSEL7034531 | PTIK20S09611 | ZCSU8781825 | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 87 | 3 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED CLOSED ON 10/16 (11C20)
PSS | 72000069 | SEAMAX NEW HAVEN | ZIMUSEL7034531 | PTIK20S09611 | ZCSU8781825 | Q.PEAK DUO L-G8.3.2.V 420 | 30383060R | 20 | 116 | 4 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED CLOSED ON 10/16 (11C20)
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL200212932 | PTIK20S09608 | BMOU4294501 | Q.PEAK DUO LG8P.3.1/BGT 405 | 30368357 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO on 10/14 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4526401 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4691577 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO on 10/14 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4706722 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4741810 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-20 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4742674 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4754973 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU4910886 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | BMOU6975778 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | DRYU9627231 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | FCIU8511624 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | GAOU6140464 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | RFCU4043388 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | SEGU5336717 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | TLLU5925170 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | ZCSU7120271 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | ZCSU8435252 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-14 |  | DELIVERED CLOSED IN CELLO 10/15 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | ZCSU8498420 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO on 10/14 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | ZCSU8767149 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | SEAMAX NEW HAVEN | ZIMUSEL7034530 | PTIK20S09606 | ZCSU8918374 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO on 10/14 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000062 | SEAMAX NEW HAVEN | ZIMUSEL7034534 | PTIK20S09607 | TGHU6497484 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 676 | 26 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO ON 10/14 (11C20)
PSS | 72000062 | SEAMAX NEW HAVEN | ZIMUSEL7034534 | PTIK20S09607 | TCNU2728433 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 676 | 26 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO ON 10/14 (11C20)
PSS | 72000062 | SEAMAX NEW HAVEN | ZIMUSEL7034534 | PTIK20S09607 | TGHU6080783 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 676 | 26 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED CLOSED IN CELLO ON 10/14 (11C20)
PSS | 72000062 | SEAMAX NEW HAVEN | ZIMUSEL7034534 | PTIK20S09607 | ZCSU8776670 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 676 | 26 | 2020-09-04 | 2020-10-10 |  |  | 2020-10-02 |  |  | 2020-10-15 |  |  | 2020-10-13 |  | DELIVERED (11C20)
PSS | 72000058 | HYUNDAI AMBITION | HDMUBUWB5035205 | PTIK20S09613 | BSIU9629100 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI AMBITION | HDMUBUWB5035205 | PTIK20S09613 | CAIU4431878 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | HYUNDAI AMBITION | HDMUBUWB5035205 | PTIK20S09613 | KOCU4047682 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | CAIU4412728 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | CAIU4466405 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | CAIU7165600 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-21 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | CAIU7448730 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | CAIU7659959 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | DFSU6652020 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | DFSU6655035 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | DRYU9204517 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | GAOU6207655 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | GAOU6212688 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | GCXU5017800 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HDMU6649730 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HDMU6776061 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HDMU6799724 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-15 |  | DELIVERED CLOSED IN CELLO ON 10/16 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HDMU6856418 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HMMU6157949 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HMMU6242399 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | HMMU6261254 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4046095 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4196602 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-19 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4331847 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4337758 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4450532 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | KOCU4482170 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | SEGU5830761 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-20 |  |  | 2020-10-20 |  | DELIVERED CLOSED IN CELLO ON 10/21 (PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | TGBU6236827 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PIONEER | 72000062 | HYUNDAI AMBITION | HDMUBUWB5034046 | PTIK20S09604 | TGBU6487714 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-09 | 2020-10-13 |  |  | 2020-10-02 |  |  | 2020-10-19 |  |  | 2020-10-16 |  | DELIVERED CLOSED IN CELLO 10/19(PIONEERNB20)
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | CAIU4384210 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-22 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | CAIU7479279 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-22 |  | DELIVERED CLOSED IN CELLO 10/23 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | CAIU8146565 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-22 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | CLKU5016050 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-22 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | GAOU6367756 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-28 |  |  | 2020-10-27 |  | DELIVERED CLOSED IN CELLO 10/28 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | HDMU6718002 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-28 |  |  | 2020-10-27 |  | DELIVERED CLOSED IN CELLO 10/28 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | HDMU6737342 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-23 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | HDMU6746806 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-27 |  |  | 2020-10-27 |  | DELIVERED CLOSED IN CELLO 10/28 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | HMMU6271859 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-26 |  |  | 2020-10-23 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000058 | YM WARRANTY | HDMUBUWB5035235 | PTIK20S09614 | KOCU4156831 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-15 | 2020-10-20 |  |  | 2020-10-12 |  |  | 2020-10-28 |  |  | 2020-10-27 |  | DELIVERED CLOSED IN CELLO 10/28 (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000078 | GRETE MAERSK | MAEU204923738 | PTIK20S09627 | MRKU4772860 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204923738 | PTIK20S09627 | MRKU2540737 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204923738 | PTIK20S09627 | TCNU6287953 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204923738 | PTIK20S09627 | TGHU8412275 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | GVCU5075397 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | HASU4486387 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | INKU6355951 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | MRKU2444970 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | MRKU3873310 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | MRKU6210380 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | MSKU0786805 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | TCKU6801707 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | TCLU8283902 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | TCNU1455400 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | TLLU5863145 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204951035 | PTIK20S09625 | UETU5924185 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | GESU5941652 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | HASU4716730 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MRKU2588520 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MRKU4113647 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MRKU4624441 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MRKU4649645 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MSKU8776378 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | MSKU9368107 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | PONU7777322 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | SUDU5841658 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | TCNU7566720 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000076 | GRETE MAERSK | MAEU204950910 | PTIK20S09626 | TLLU5979304 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB) BIFACIAL SOLAR MODULES NO TARIFF
CUSTOMER SITE | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | CAIU8277185 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-03 |  | DIRECT DRAYAGE - DELIVERED TO TESLA / ELKRIDGE MD
CUSTOMER SITE | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | FESU5124137 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DIRECT DRAYAGE - DELIVERED TO TESLA / ELKRIDGE MD
CUSTOMER SITE | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MRKU2223985 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DIRECT DRAYAGE - DELIVERED TO TESLA / ELKRIDGE MD
CUSTOMER SITE | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MRSU3110991 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DIRECT DRAYAGE - DELIVERED TO TESLA / ELKRIDGE MD
CUSTOMER SITE | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MRSU3999739 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DIRECT DRAYAGE - DELIVERED TO TESLA / ELKRIDGE MD
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MSKU0008901 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MSKU0045187 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MSKU0931858 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MSKU8946828 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | MSKU9205516 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PIONEER | 72000078 | GRETE MAERSK | MAEU204952238 | PTIK20S09623 | TCKU6585233 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-29 |  | DELIVERED CLOSED IN CELLO 10/30 (PIONEERNB20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | BEAU5097631 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MRKU3269933 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MRKU4288265 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MRSU3614570 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-03 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MRSU3656719 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MSKU0047451 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MSKU0361544 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MSKU9380735 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-11-02 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | MSKU9775524 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | SUDU6524616 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000078 | GRETE MAERSK | MAEU204952120 | PTIK20S09622 | TRLU8057951 | Q.PEAK DUO BLK-G6P+/SC 340 | 30375309R | 20 | 676 | 26 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11C20)
PSS | 72000076 | GRETE MAERSK | MAEU204925054 | PTIK20S09628 | HASU4882710 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | 72000076 | GRETE MAERSK | MAEU204925054 | PTIK20S09628 | MRKU2905563 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | 2020-10-19 |  |  | 2020-11-02 |  |  | 2020-10-30 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PSS | P0213PPRC-22 | GRETE MAERSK | MAEU205031978 | PICJPTIK20S09624 | TCNU7270750 | Q.PEAK DUO L-G8P.2.1 420 | 30383260EPC | ?? | 638 | 22 | 2020-09-23 | 2020-10-27 |  |  | NA | [5 empty] | 2020-10-30 |  | DELIVERED (PSSEPC); FTD UPLOADED IN CELLO
PSS | 72000071 | MAERSK SANA | MAEU204923268 | PTIK20S09618 | MRKU5430097 | Q.PEAK DUO L-G6P.2 415 | 30380659R | 20 | 638 | 22 | 2020-09-13 | 2020-11-01 |  |  | 2020-10-23 |  |  | 2020-11-05 |  |  | 2020-11-03 |  | DELIVERED (11C20)
PSS | 72000071 | MAERSK SANA | MAEU204923268 | PTIK20S09618 | FCIU9086113 | Q.PEAK DUO L-G6P.2 415 | 30380659R | 20 | 638 | 22 | 2020-09-13 | 2020-11-01 |  |  | 2020-10-23 |  |  | 2020-11-05 |  |  | 2020-11-04 |  | DELIVERED (11C20)
PSS | 72000071 | MAERSK SANA | MAEU204923268 | PTIK20S09618 | MRKU5983446 | Q.PEAK DUO L-G6P.2 415 | 30380659R | 20 | 638 | 22 | 2020-09-13 | 2020-11-01 |  |  | 2020-10-23 |  |  | 2020-11-05 |  |  | 2020-11-03 |  | DELIVERED (11C20)
PSS | 72000058 | MAERSK SANA | MAEU204970161 | PTIK20S09616 | MSKU1161181 | Q.PEAK DUO L-G8P.3.1/BGT 405 | 30368357 | 0 | 638 | 22 | 2020-09-13 | 2020-11-01 |  |  | 2020-10-23 |  |  | 2020-11-05 |  |  | 2020-11-03 |  | DELIVERED (11CZEROT) BIFACIAL SOLAR MODULES NO TARIFF
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | CAIU7153087 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | CAXU9222363 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | GESU5502602 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | HASU4810916 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED CLOSED IN CELLO ON 11/09 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MRKU2332029 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MRKU3145233 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MRKU5931740 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED CLOSED IN CELLO 11/11 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MRKU6116054 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED CLOSED IN CELLO 11/11 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MRSU3239530 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/06 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MSKU0859007 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/06 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MSKU1128711 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-11 |  | DELIVERED CLOSED IN CELLO ON 11/12 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MSKU9772438 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | MSKU9840363 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/06 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | SEAU8642150 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED CLOSED IN CELLO 11/11 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | TCKU6563403 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | TCNU2486387 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | TGHU7069520 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/06 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | TLLU4773330 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | CLOSED IN CELLO 11/10 (PIONEERNB20)
PIONEER | 72000083 | MAERSK EDINBURGH | MAEU205117040 | PTIK20S09643 | TRLU7614878 | Q.PEAK DUO-G6P+.0.1 350 | 30370711R | 20 | 832 | 26 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-10 |  | DELIVERED CLOSED IN CELLO 11/11 (PIONEERNB20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | ZCSU8973474 | Q.PEAK DUO L-G7.3.1.V 400 | 30367656R | 20 | 638 | 22 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | ZCSU8953396 | Q.PEAK DUO L-G7.3.1.V 400 | 30367656R | 20 | 638 | 22 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | TGBU7225787 | Q.PEAK DUO L-G7.3 405 | 30367257R | 20 | 638 | 22 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | DFSU6602713 | Q.PEAK DUO L-G7.3 400 | 30367256R | 20 | 203 | 7 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED (11C20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | DFSU6602713 | Q.PEAK DUO L-G7.3 405 | 30367257R | 20 | 203 | 7 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED (11C20)
PSS | 72000084 | MAERSK EDINBURGH | ZIMUSEL7040042 | PTIK20S10648 | DFSU6602713 | Q.PEAK DUO L-G7.3.1.V 400 | 30367656R | 20 | 116 | 4 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED (11C20)
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | BEAU5553346 | Q.PEAK DUO BLK G5.0.3.2.V 315 | 30356104R | 20 | 608 | 20 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20) TOTAL 20 PALLET IDS
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | BEAU5553346 | Q.PEAK DUO BLK-G5/SC.V 310 | 30359203R | 20 | 182 | 7 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20)
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | ZCSU8783411 | Q.PEAK DUO BLK G5.0.3.1.V 315 | 3035604R | 20 | 128 | 4 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20)
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | ZCSU8783411 | Q.PEAK DUO BLK G5.0.3.V 315 | 30359304R | 20 | 352 | 11 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20)
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | ZCSU8783411 | Q.PEAK DUO BLK-G5/SC.V 305 | 30359202R | 20 | 104 | 4 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20)
PSS | 72000066 | MAERSK EDINBURGH | ZIMUSEL7040095 | PTIK20S10645 | ZCSU8783411 | Q.PEAK DUO BLK-G5/SC.V 310 | 30359203R | 20 | 52 | 2 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-06 |  | CLOSED IN CELLO 11/11 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | HASU4896653 | Q.PEAK DUO L-G8P.2.1 420 | 30383260R | 20 | 581 | 21 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-06 |  | DELIVERED (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | MRSU3522448 | Q.PEAK DUO L-G7.3.1.V 395 | 30367655R | 20 | 203 | 7 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/11 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | MRSU3522448 | Q.PEAK DUO L-G7.3 395 | 30367255R | 20 | 435 | 15 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED CLOSED IN CELLO ON 11/11 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | MSKU8429677 | Q.PEAK DUO L-G8P.2.1 420 | 30383260R | 20 | 638 | 22 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | MSKU8572121 | Q.PEAK DUO L-G8P.2.1 420 | 30383260R | 20 | 638 | 22 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-09 |  |  | 2020-11-05 |  | DELIVERED (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | TCNU5480206 | Q.PEAK DUO L-G7.3.1.V 410 | 30367658R | 20 | 435 | 15 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (11C20)
PSS | 72000084 | MAERSK EDINBURGH | MAEU205127024 | PTIK20S10647 | TCNU5480206 | Q.PEAK DUO L-G7.3.1.V 395 | 30367655R | 20 | 58 | 2 | 2020-10-10 | 2020-11-03 |  |  | 2020-10-28 |  |  | 2020-11-10 |  |  | 2020-11-09 |  | DELIVERED CLOSED IN CELLO ON 11/10 (11C20)
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | KOCU4214455 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | CLOSED IN CELLO 11/13 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | KOCU4221161 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-18 |  |  | 2020-11-18 |  | DELIVERED (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | KOCU4263228 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | CLOSED IN CELLO 11/13 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | KOCU4805524 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | CLOSED IN CELLO 11/13 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TCLU8313340 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | CLOSED IN CELLO 11/13 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TEMU7536731 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO 11/16 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TGBU6490261 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-11 |  | DELIVERED CLOSED IN CELLO ON 11/12 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TGHU6711214 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | CLOSED IN CELLO 11/13 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TLLU5768087 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-10 |  | DELIVERED CLOSED IN CELLO 11/11(PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PIONEER | 72000058 | HYUNDAI HOPE | HDMUBUWB5038258 | PTIK20S09629 | TLLU5772220 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-10-08 | 2020-11-05 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO 11/16 (PIONEERNB) BIFACIAL SOLAR MODULES ZERO TARIFF
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | HASU4271898 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | HASU5009970 | Q.PEAK DUO L-G5.2.1.V 400 | 30361456R | 20 | 638 | 24 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20); TOTAL 24 PALLET IDS
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | MRSU3153231 | Q.PEAK DUO L-G5.2.2.V 395 | 30361555R | 20 | 261 | 9 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | MRSU3153231 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 377 | 13 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | MRSU3887960 | Q.PEAK DUO L-G5.2.1.V 400 | 30361456R | 20 | 348 | 12 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | MSKU8717950 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | TCNU7198613 | Q.PEAK DUO L-G5.2.0.V 400 | 30361056R | 20 | 58 | 2 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | TCNU7198613 | Q.PEAK DUO L-G5.2.1.V 395 | 30361455R | 20 | 493 | 19 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20); TOTAL 19 PALLET IDS
PSS | 72000070 | ALEXANDER BAY | MAEU205117065 | PTIK20S09638 | TCNU7198613 | Q.PEAK DUO L-G5.2.1.V 405 | 30361457R | 20 | 87 | 3 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-12 |  | DELIVERED CLOSED IN CELLO 11/13 (11C20)
PSS | 72000058 | ALEXANDER BAY | MAEU205125274 | PTIK20S09640 | MSKU8364792 | Q.PEAK DUO LG8P.3.1/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO 11/16 (11CZEROT); BIFACIAL SOLAR MODULES ZERO TARIFF
PSS | 72000078 | ALEXANDER BAY | MAEU205122969 | PTIK20S09637 | TCNU8001117 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 676 | 26 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO 11/16 (11C20)
PSS | 72000076 | ALEXANDER BAY | MAEU205271318 | PTIK20S09639 | MSKU1810824 | Q.PEAK DUO L-G8P.3.1/BGT 420 | 30368360 | 0 | 638 | 22 | 2020-09-28 | 2020-11-09 |  |  | 2020-10-28 |  |  | 2020-11-13 |  |  | 2020-11-13 |  | DELIVERED CLOSED IN CELLO 11/16 (11CZEROT); BIFACIAL SOLAR MODULES ZERO TARIFF
PSS | 72000071 | NORTHERN JADE | ZIMUSEL7040316 | PTIK20S10646 | ZCSU8677111 | Q.PEAK DUO L-G6P.2 430 | 30380662R | 20 | 638 | 22 | 2020-10-02 | 2020-11-12 |  |  | 2020-11-02 |  |  | 2020-11-19 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO 11/20 (11C20)
PSS | 72000071 | NORTHERN JADE | ZIMUSEL7040316 | PTIK20S10646 | TGBU7091034 | Q.PEAK DUO L-G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-10-02 | 2020-11-12 |  |  | 2020-11-02 |  |  | 2020-11-19 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO 11/19 (11C20)
PSS | 72000071 | NORTHERN JADE | ZIMUSEL7040316 | PTIK20S10646 | BSIU9682300 | Q.PEAK DUO L-G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-10-02 | 2020-11-12 |  |  | 2020-11-02 |  |  | 2020-11-19 |  |  | 2020-11-19 |  | DELIVERED CLOSED IN CELLO 11/20 (11C20)
PSS | 72000071 | NORTHERN JADE | ZIMUSEL7040316 | PTIK20S10646 | TLLU5386280 | Q.PEAK DUO L-G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-10-02 | 2020-11-12 |  |  | 2020-11-02 |  |  | 2020-11-19 |  |  | 2020-11-18 |  | DELIVERED CLOSED IN CELLO 11/19 (11C20)
PSS | TSS-4634 | XPO - (damaged pallet) | ZIMUSEL784875 | NPNESEATSSE47686 | VA4634082903A | Q.PLUS L G4.2.5.A.F 345 | 30340710A | 25 | 29 | 1 | 2020-11-17 | 2020-11-18 | [8 empty] | 2020-11-19 |  | CLOSED IN CELLO 12/01 DAMAGED PALLET ID 190418_K2_PEVF42_345A_740 (cell# DAMAGE-PSS)
PSS | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU8564316 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-02 |  |  | 2020-11-30 |  | DELIVERED (11C20)
PSS | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | TCKU9150131 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-11-30 |  | DELIVERED (11C20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | CRSU9105903 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-02 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | HASU4162623 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MRKU3118032 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU0466530 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-02 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU0741903 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-02 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU1888165 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-02 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU8280372 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU8661070 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | MSKU9843911 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | PONU8237904 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-02 |  | DELIVERED CLOSED IN CELLO 12/03 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | SUDU6567114 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | SUDU6982244 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK EUPHRATES | MAEU205579591 | SDSMY20201014-02 | TLLU5871367 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-15 | 2020-11-25 |  |  | 2020-11-16 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72000089 | GJERTRUD MAERSK | ZIMUSEL7041710 | PTIK20S11657 | AXIU1627861 | Q.PEAK DUO BLK-G6P+.0.2 335 | 30375708R | 20 | 832 | 26 | 2020-11-01 | 2020-11-28 |  |  | 2020-11-24 |  |  | 2020-12-03 |  |  | 2020-11-30 |  | DELIVERED (PIONEERNB20) | HORIZONTAL PACKAGING
PIONEER | 72000089 | GJERTRUD MAERSK | ZIMUSEL7041710 | PTIK20S11657 | TCNU4576577 | Q.PEAK DUO BLK-G6P+.0.1 335 | 30375508R | 20 | 832 | 26 | 2020-11-01 | 2020-11-28 |  |  | 2020-11-24 |  |  | 2020-12-03 |  |  | 2020-11-30 |  | CLOSED IN CELLO 12/01 (PIONEERNB20) | HORIZONTAL PACKAGING
PIONEER | 72000089 | GJERTRUD MAERSK | ZIMUSEL7041710 | PTIK20S11657 | TLLU4307476 | Q.PEAK DUO BLK-G6P+.0.1 340 | 30375509R | 20 | 832 | 26 | 2020-11-01 | 2020-11-28 |  |  | 2020-11-24 |  |  | 2020-12-03 |  |  | 2020-12-01 |  | DELIVERED CLOSED IN CELLO 12/02 (PIONEERNB20) | HORIZONTAL PACKAGING
PIONEER | 72000089 | GJERTRUD MAERSK | ZIMUSEL7041710 | PTIK20S11657 | ZCSU8754882 | Q.PEAK DUO BLK-G6P+.0.1 340 | 30375509R | 20 | 832 | 26 | 2020-11-01 | 2020-11-28 |  |  | 2020-11-24 |  |  | 2020-12-03 |  |  | 2020-11-30 |  | CLOSED IN CELLO 12/01 (PIONEERNB20) | HORIZONTAL PACKAGING
PSS | PO-92691 |  | 119372884 | 119372884 | 119372884 | Q.PEAK DUO BLK G5.V 320 | 43207124 | 0 | 96 | 3 | 2020-11-24 | 2020-12-11 | [8 empty] | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/15 (11CZEROT) | PU from Boxborough, MA
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | BMOU4506489 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | BMOU4512286 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | BMOU4562965 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | BSIU9547758 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-02 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | CAIU4352531 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-02 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | GAOU6437149 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-07 |  | DELIVERED CLOSED IN CELLO 12/08 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | GAOU6440604 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | GCXU5068515 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-07 |  | DELIVERED CLOSED IN CELLO 12/08 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | SEGU5286494 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-07 |  | DELIVERED CLOSED IN CELLO 12/08 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TCKU7154586 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-04 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TCNU2501985 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-07 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TCNU8947932 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-07 |  | DELIVERED CLOSED IN CELLO 12/08 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TGBU5484095 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TGBU7062606 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TGCU5079326 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TGHU9644824 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | TLLU5221248 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8546488 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8646297 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-03 |  | DELIVERED CLOSED IN CELLO 12/04 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8753103 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8761984 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-04 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8779263 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-07 |  |  | 2020-12-07 |  | DELIVERED CLOSED IN CELLO 12/08 (PIONEERNBNEW20)
PIONEER | 72001041 | MAERSK SALTORO | SSPHPKL8072710 | SDSMY20201026-01 | ZCSU8940022 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-26 | 2020-12-01 |  |  | 2020-11-24 |  |  | 2020-12-08 |  |  | 2020-12-04 |  | DELIVERED CLOSED IN CELLO ON 12/07 (PIONEERNBNEW20)
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | HDMU6699730 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | HDMU6725948 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | HDMU6785490 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | HMMU6232575 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | KOCU4243962 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | KOCU4262350 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | KOCU4309036 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | KOCU4468531 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | KOCU4679257 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | TCKU6107126 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-11 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | TCLU7949609 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | HYUNDAI PRIDE | HDMUBUWB5049901 | PTIK20S11658 | TCNU5708810 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-05 | 2020-12-04 |  |  | 2020-11-25 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | GUNDE MAERSK | ZIMUSEL7041703 | PTIK20S11662 | TCNU2475401 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-08 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | GUNDE MAERSK | ZIMUSEL7041703 | PTIK20S11662 | ZCSU6510927 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-08 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | GUNDE MAERSK | ZIMUSEL7041703 | PTIK20S11662 | ZCSU7116517 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-08 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED CLOSED IN CELLO 12/10 (11C20) | BIFACIAL SOLAR MODULES
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU2152259 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED CLOSED IN CELLO 12/10 (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU2215547 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU2433132 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU2790021 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU2933565 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU3211464 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU4390050 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU4424551 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRKU5550786 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRSU3024424 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MRSU3392030 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU0691016 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU1091470 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU1162399 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU1678256 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU1968126 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | MSKU9477427 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED CLOSED IN CELLO 12/09 (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | PONU7789175 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | SUDU8569712 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 590 | 20 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED CLOSED IN CELLO 12/09 (PIONEERNBNEW20) | 1 PALLET 100000001438695 WITH 20 PCS
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | SUDU8575891 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | TEXU5631440 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PIONEER | 72001041 | ADRIAN MAERSK | MAEU205751356 | SDSMY20201031-01 | TLLU8065679 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-12-03 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (PIONEERNBNEW20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | FCIU9081955 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | INKU2547128 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MAGU5423740 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MRKU2510286 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MRKU3894910 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MRSU3766640 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MSKU0311543 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MSKU1626355 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-08 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | MSKU9665698 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-10 |  | DELIVERED (11C20)
PSS | 72001046 | ADRIAN MAERSK | MAEU205816935 | SDSMY20201030-01 | SUDU6623584 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-31 | 2020-12-05 |  |  | 2020-11-30 |  |  | 2020-12-10 |  |  | 2020-12-09 |  | DELIVERED (11C20)
PSS | 72000085 | MAERSK PUELO | MAEU205875365 | PTIK20S10656 | MRKU4858075 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-11-30 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | MAERSK PUELO | MAEU205875365 | PTIK20S10656 | MSKU0413099 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-11-30 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | MAERSK PUELO | MAEU205875365 | PTIK20S10656 | SUDU6834904 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-11-30 |  |  | 2020-12-16 |  |  | 2020-12-15 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | MAERSK PUELO | MAEU205875365 | PTIK20S10656 | TCKU6982966 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-11-30 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000085 | MAERSK PUELO | MAEU205875365 | PTIK20S10656 | TGHU9263582 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-11-30 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (11C20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MIEU3062015 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MRKU3099380 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-10 |  | DELIVERED CLOSED IN CELLO 12/11 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MRKU5149562 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MSKU0247130 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MSKU8758688 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | MSKU9532247 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | TCKU6711624 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | TCKU6951815 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | TCNU3187288 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875074 | PTIK20S10653 | TCNU4447456 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | FBXU5010450 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | HASU4921231 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-15 |  | DELIVERED CLOSED IN CELLO 12/15 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MRKU3714999 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MSKU0355285 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MSKU1255167 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MSKU1438419 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-10 |  | DELIVERED CLOSED IN CELLO 12/11 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MSKU8597006 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-15 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | MSKU9043436 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | PONU7643154 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-10 |  | DELIVERED CLOSED IN CELLO 12/11 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875167 | PTIK20S10654 | PONU8205580 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-16 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU2268892 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU2367998 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU2647520 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU3398186 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU4069159 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED CLOSED IN CELLO 12/14 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRKU4443340 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MRSU3860743 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-11 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | MSKU9424670 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-15 |  |  | 2020-12-10 |  | DELIVERED (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PIONEER | 72000085 | MAERSK PUELO | MAEU205875274 | PTIK20S10655 | TCNU6788214 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-09 | 2020-12-09 |  |  | 2020-12-03 |  |  | 2020-12-16 |  |  | 2020-12-14 |  | DELIVERED CLOSED IN CELLO 12/15 (PIONEERNBNEW20) | BIFACIAL SOLAR MODULES
PSS | 72000093 | HYUNDAI DREAM | YMLUE360780363 | PTIK20S11664 | SEGU6404312 | Q.PEAK DUO BLK-G6P+/SC 335 | 30375308R | 20 | 416 | 16 | 2020-11-09 | 2020-12-14 |  |  | 2020-11-30 |  |  | 2020-12-18 |  |  | 2020-12-16 |  | DELIVERED (11C20)
PSS | 72000093 | HYUNDAI DREAM | YMLUE360780363 | PTIK20S11664 | SEGU6404312 | Q.PEAK DUO BLK-G6P+/SC 350 | 30375311R | 20 | 260 | 10 | 2020-11-09 | 2020-12-14 |  |  | 2020-11-30 |  |  | 2020-12-18 |  |  | 2020-12-16 |  | DELIVERED (11C20)
PSS | 72000093 | HYUNDAI DREAM | YMLUE360780363 | PTIK20S11664 | TEMU8614124 | Q.PEAK DUO BLK-G6P+/SC 330 | 30375307R | 20 | 364 | 14 | 2020-11-09 | 2020-12-14 |  |  | 2020-11-30 |  |  | 2020-12-18 |  |  | 2020-12-16 |  | DELIVERED (11C20)
PSS | 72000093 | HYUNDAI DREAM | YMLUE360780363 | PTIK20S11664 | TEMU8614124 | Q.PEAK DUO BLK-G6P+/SC 350 | 30375311R | 20 | 156 | 6 | 2020-11-09 | 2020-12-14 |  |  | 2020-11-30 |  |  | 2020-12-18 |  |  | 2020-12-16 |  | DELIVERED (11C20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MRKU2739035 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MRKU3645100 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-30 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MRKU5541763 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-30 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MRKU5552691 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/06 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MRKU5913860 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MSKU0524169 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MSKU0714528 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/06 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MSKU1635296 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/12 (GTGNAE20) | PLT# 150000000764730 (need to set aside for DUKE TESTING)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MSKU8837811 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MSKU9061609 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | MVIU0019275 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | SUDU8654286 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20)
GTG | 72001046 | MAERSK DETROIT --> MAERSK SKARSTIND | MAEU206119451 | SDSMY20201109-01 | SUDU8971296 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-10 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | MAERSK SKARSTIND | MAEU206415873 | SDSMY20201116-01 | CAIU8401573 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-16 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/12 (GTGNAE20)
GTG | 72001049 | MAERSK SKARSTIND | MAEU206415873 | SDSMY20201116-01 | MRKU3999886 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-16 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2021-01-04 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/04 (GTGNAE20)
GTG | 72001049 | MAERSK SKARSTIND | MAEU206415873 | SDSMY20201116-01 | HASU4206784 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-16 | 2020-12-19 |  |  | 2020-12-11 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/12 (GTGNAE20)
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | BSIU9233654 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | CAIU7666290 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | HMMU6079682 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | KOCU4561238 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | TCNU7454994 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | HDMU6724514 | Q.PEAK DUO L-G8P.3.1/BFG 410 | 30368158R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED CLOSED IN CELLO 12/28 (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | HMMU6008380 | Q.PEAK DUO L-G8P.3.1/BFG 410 | 30368158R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (11C20) | BIFACIAL SOLAR MODULES
PSS | 72000092 | HYUNDAI SMART | HDMUBUWB5050871 | PTIK20S11661 | KOCU4671180 | Q.PEAK DUO L-G8P.3.0 420 | 30383360R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-23 |  | DELIVERED CLOSED IN CELLO 12/28 (11C20) | HORIZONTAL PACKAGING
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | HDMU6653880 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/06 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4338625 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/05 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4385078 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/11 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4642047 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4793378 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4811105 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | KOCU4815008 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | TCNU5081232 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | TCNU6924970 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/04 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | TGBU5889766 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-30 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/05 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | TGBU6161728 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5052054 | PTIK20S11665 | TLLU5299293 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5051593 | PTIK20S11663 | KOCU4539574 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/06 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | CAIU7409121 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 01/06 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | CAIU9981727 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | HMMU6122074 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | HMMU6218237 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-31 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | HMMU6240210 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-24 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | KOCU4026545 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-28 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | KOCU4202665 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | KOCU4513841 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-29 |  |  | 2020-12-30 |  | DELIVERED CLOSED IN CELLO 01/08 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72000085 | HYUNDAI SMART | HDMUBUWB5050842 | PTIK20S11660 | KOCU4723431 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-18 | 2020-12-20 |  |  | 2020-12-09 |  |  | 2020-12-28 |  |  | 2020-12-29 |  | DELIVERED CLOSED IN CELLO 12/30 (GTGNAE20) | BIFACIAL SOLAR MODULES
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0626215 | SDSMY20201119-02 | APHU7021784 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0626215 | SDSMY20201119-02 | TCNU5432105 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0626215 | SDSMY20201119-02 | CMAU4596398 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 25 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/13 (GTGNAE20); TOTAL 25 PALLET IDS
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | APHU6369287 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | APHU7250374 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | APHU7282561 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/12 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | BEAU4145015 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | BMOU6424013 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/12 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CAIU8240843 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CAIU9474954 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CAIU9729335 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU4503590 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU4663834 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU4721606 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU5644572 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU7033232 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU7050060 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU7248375 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | CMAU7439638 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | GESU6347347 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/12 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | GESU6909001 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | GLDU7459081 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | SEGU4963899 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | SEGU5045060 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU1033133 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU1173557 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU1771137 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU3348593 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU5153630 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU9526305 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TCNU9777255 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/11 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TGBU6112997 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TGCU0057453 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | TGHU6361137 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/12 (GTGNAE20)
GTG | 72001049 | CMA CGM T.JEFFERSON | CMDUAYN0624849 | SDSMY20201119-01 | UETU5563267 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-22 | 2020-12-22 |  |  | 2020-12-14 |  |  | 2021-01-04 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/10 (GTGNAE20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | CAIU7086564 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9083570 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9185973 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9570943 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-04 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9744264 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9775012 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EGHU9860243 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-04 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | EISU8269510 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | OCGU8090131 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-04 |  | DELIVERED | (11C20)
PSS | 72000096 | COSCO SHIPPING LOTUS | EGLV040000381399 | PTIK20S12677 | TLLU5385895 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-11-30 | 2020-12-28 |  |  | 2020-12-17 |  |  | 2021-01-07 |  |  | 2021-01-04 |  | DELIVERED | (11C20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | BMOU4137903 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-03 |  | DELIVERED | CLOSED IN CELLO 01/05 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | BSIU9263448 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | CAAU5125479 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | CAIU9845818 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | HDMU6863844 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | HMMU6320423 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/05 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4152369 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4160791 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4166188 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4239690 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4257781 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4347632 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4608309 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-07 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | KOCU4691910 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | TCLU5081934 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | TCNU5085407 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5054559 | PTIK20S11669 | TGBU6353227 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | GAOU6164445 | Q.PEAK DUO L-G8P.2.1 410 | 30383258R | 20 | 609 | 21 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | HDMU6713037 | Q.PEAK DUO L-G8P.2.1 415 | 30383259R | 20 | 145 | 5 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | HDMU6713037 | Q.PEAK DUO L-G8P.3.1/BGT 405 | 30368357R | 20 | 261 | 9 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | CAIU7442860 | Q.PEAK DUO L-G8P.3.0 420 | 30383360R | 20 | 58 | 2 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | CAIU7442860 | Q.PEAK DUO L-G8P.3.1/BFG 410 | 30368158R | 20 | 290 | 10 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | CAIU7442860 | Q.PEAK DUO L-G8P.3.1/BFG 425 | 30368161R | 20 | 58 | 2 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000092 | HYUNDAI HONOUR | HDMUBUWB5054597 | PTIK20S11670 | HDMU6726944 | Q.PEAK DUO L-G8P.3/BGT 405 | 30368257R | 20 | 609 | 21 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/08 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI HONOUR | HDMUBUWB5054631 | PTIK20S11671 | KOCU4206660 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI HONOUR | HDMUBUWB5054631 | PTIK20S11671 | KOCU4670202 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-07 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI HONOUR | HDMUBUWB5054631 | PTIK20S11671 | SEGU6017524 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI HONOUR | HDMUBUWB5054631 | PTIK20S11671 | TGBU6163736 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5052064 | PTIK20S11666 | FSCU8511135 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5052064 | PTIK20S11666 | GAOU6338629 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-07 |  | DELIVERED | IN CELLO 01/08 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5052064 | PTIK20S11666 | KOCU4710305 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5052064 | PTIK20S11666 | TCNU7407987 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72000085 | HYUNDAI HONOUR | HDMUBUWB5052064 | PTIK20S11666 | TEMU7284516 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-11-30 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-07 |  |  | 2021-01-07 |  | DELIVERED | IN CELLO 01/08 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | CAIU8482390 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU2131390 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU2304243 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/05 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU4188688 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/05 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU4395664 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU4551221 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU5563572 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-04 |  | DELIVERED | CLOSED IN CELLO 01/05 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU5890960 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2020-12-30 |  | DELIVERED | CLOSED IN CELLO 12/31 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRKU5937461 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRSU3135011 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MRSU3439159 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MSKU1050362 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2020-12-30 |  | DELIVERED | CLOSED IN CELLO 12/31 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MSKU1363747 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/11 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | MSKU1429103 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | SUDU6891611 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | TCKU6961449 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-06 |  | DELIVERED | CLOSED IN CELLO 01/07 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | TCKU6971220 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | TCNU6721988 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | TEMU6352766 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PIONEER | 72001051 | MAERSK SANTANA | MAEU206447819 | SDSMY20201123-04 | TEMU6929020 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2020-12-29 |  |  | 2020-12-22 |  |  | 2021-01-06 |  |  | 2021-01-05 |  | DELIVERED | CLOSED IN CELLO 01/06 (PIONEERNB20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | BSIU9538648 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-11 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | FCIU9041382 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-11 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TCNU2501007 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-08 |  |  | 2021-01-07 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TLLU4576881 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-08 |  |  | 2021-01-07 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | ZCSU8210786 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | ZCSU8887484 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TGBU5522699 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 522 | 18 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TGBU5522699 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 120 | 4 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | BMOU4745190 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-08 |  |  | 2021-01-07 |  | DELIVERED | CLOSED IN CELLO 01/08 (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TCNU4346743 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-08 |  |  | 2021-01-07 |  | DELIVERED | CLOSED IN CELLO 01/08 (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TCNU7255307 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TCNU8548450 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-11 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TEMU6801039 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TEMU7334664 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-11 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | TEMU7601591 | Q.PEAK DUO L-G8.2 425 | 12004246_29R | 20 | 638 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PSS | 72001041 | SEROJA LIMA | SSPHPKL8072592 | SDSMY20201014-01 | ZCSU8564814 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-10-20 | 2021-01-04 |  |  | 2020-11-16 |  |  | 2021-01-11 |  |  | 2021-01-08 |  | DELIVERED | (11C20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | BMOU4511422 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | BMOU5917334 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | FSCU8505765 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | HMMU6120908 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | KOCU4139541 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | KOCU4186585 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | KOCU4327488 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | KOCU4778706 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | SEGU6028391 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TCLU4842134 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TCNU6056553 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TCNU9429199 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TEMU6921543 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TEMU7308881 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TEMU7312027 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TEMU7319166 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000100 | HYUNDAI AMBITION | HDMUBUWB5062705 | PTIK20S12679 | TGBU6489907 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-08 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | BSIU9937102 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | CAIU4427076 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-08 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | CAIU7178589 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | HMMU6028854 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-09 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | KOCU4167970 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | KOCU4243345 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | KOCU4576069 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054643 | PTIK20S11672 | KOCU4696655 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-12 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054659 | PTIK20S11673 | GAOU6227332 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054659 | PTIK20S11673 | HDMU6841700 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054659 | PTIK20S11673 | KOCU4219251 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054659 | PTIK20S11673 | KOCU4428441 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | HYUNDAI AMBITION | HDMUBUWB5054659 | PTIK20S11673 | KOCU4536889 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-10 | 2021-01-06 |  |  | 2020-12-28 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | BEAU5041910 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | BMOU4583839 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | BSIU9712066 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | DRYU9096330 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | FCIU8752581 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | JTMU6005257 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | MAGU5625269 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TCLU6379883 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TCNU1044781 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TCNU5414380 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TCNU5778783 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TEMU6186475 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TGBU7159617 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | TLLU5199798 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU6505690 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU7106484 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU8586942 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU8640339 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-11 |  | DELIVERED | CLOSED IN CELLO 01/12 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU8956667 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72000100 | GERDA MAERSK | ZIMUSEL7046873 | PUNY20110034 | ZCSU8981103 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-05 | 2021-01-07 |  |  | 2021-01-04 |  |  | 2021-01-13 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | APHU6580371 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | BEAU4115540 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | CMAU4910657 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | CMAU5502217 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | CMAU5609740 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | CMAU5812927 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | FCGU1671011 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | FCIU8167078 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | CLOSED IN CELLO 01/13 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | FCIU8749510 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | FJKU6011297 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | GLDU7643674 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | SEGU4263175 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | TCLU1771459 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | TCNU5862071 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | APL SOUTHAMPTON | CMDUAYN0629135 | SDSMY20201210-02 | TGBU5815017 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-12 | 2021-01-09 |  |  | 2021-01-04 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | CAIU7025933 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | CBHU9142754 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | CSNU6531072 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | CSNU7547366 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | OOCU7984897 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | OOLU6789418 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | OOLU8785129 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | OOLU8802191 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | OOLU9274571 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72000096 | CMA CGM ARGENTINA | OOLU2652130760 | PTIK20S12680 | TGBU5334080 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-29 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PSS | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | BMOU5304538 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | (11C20)
PSS | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | TLLU5201494 | Q.PEAK DUO L-G8P.3.1/BGT 415 | 30368359R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (11C20)
PSS | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | BMOU4766655 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | (11C20)
PSS | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | EITU1783814 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | (11C20)
PSS | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | TCLU6257078 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-12 |  | DELIVERED | (11C20)
GTG | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | EGSU9132961 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-15 |  |  | 2021-01-13 |  | DELIVERED | (GTGNAE20)
GTG | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | EISU9172700 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-15 |  |  | 2021-01-13 |  | DELIVERED | (GTGNAE20)
GTG | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | EITU1531350 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-15 |  |  | 2021-01-13 |  | DELIVERED | (GTGNAE20)
GTG | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | EITU1683651 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | (GTGNAE20)
GTG | 72000096 | CMA CGM ARGENTINA | EGLV040000377588 | PTIK20S12678 | TLLU4014884 | Q.PEAK DUO L-G8P.3.1/BGT 410 | 30368358R | 20 | 638 | 22 | 2020-12-09 | 2021-01-09 |  |  | 2020-12-28 |  |  | 2021-01-15 |  |  | 2021-01-13 |  | DELIVERED | (GTGNAE20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MRKU3136756 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MRKU3569925 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MRKU5540200 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MRKU5878754 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MRSU3823550 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU1158953 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU1549578 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-18 |  | DELIVERED | CLOSED IN CELLO 01/19 (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU1764360 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU8890842 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU9427257 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | MSKU9846660 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-13 |  | DELIVERED | CLOSED IN CELLO 01/14 (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | SUDU6965864 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001047 | DUMMY AE55 -> ROBIN 2 | MAEU206350093 | SDSMY20201123-01 | SUDU8917401 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | CAIU8963890 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | CAXU9154269 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | CNIU2453900 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU2589850 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU3583179 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-18 |  | DELIVERED | CLOSED IN CELLO 01/19 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU3592587 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU4693930 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU4764398 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRKU5314836 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRSU3778770 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MRSU3919796 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/19 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MSKU8433110 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MSKU8895295 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MSKU8904801 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | MSKU9227855 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | PONU7683481 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | PONU7907658 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | PONU7943613 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | PONU7949720 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | SUDU5904695 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | SUDU6836933 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | SUDU8729750 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | TCKU6895141 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-18 |  | DELIVERED | CLOSED IN CELLO 01/19 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | TCKU7043812 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-16 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001051 | DUMMY AE55 -> ROBIN 2 | MAEU206347491 | SDSMY20201123-03 | TCLU5068188 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | CRSU9028258 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU2135890 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU2159232 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU2256741 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU2798146 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU3193910 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU3540731 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU3547232 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU4929625 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-15 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU4953365 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU4955305 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU0674390 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU0697502 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU0780664 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU8378482 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU9165199 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU9193950 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU9954788 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | PONU7543900 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | PONU7801835 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MRKU5397907 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | CLOSED IN CELLO 01/15 (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU8493697 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-15 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | MSKU9997310 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | TCNU7897009 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001049 | DUMMY AE55 -> ROBIN 2 | MAEU206347173 | SDSMY20201123-02 | TGBU6017367 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-11-24 | 2021-01-10 |  |  | 2021-01-05 |  |  | 2021-01-14 |  |  | 2021-01-14 |  | DELIVERED | (PIONEERNB20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | BEAU4570713 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | CLOSED IN CELLO 1/20 (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | BEAU5172798 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | CLOSED IN CELLO 1/20 (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | DRYU9856217 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | EGHU9096768 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | EISU8228830 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | CLOSED IN CELLO 1/20 (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | EMCU8286412 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | EMCU9704625 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-20 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | EMCU9743508 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | TCNU4350954 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72000100 | EVER LADEN | EGLV040000381411 | PTIK20S12682 | TGBU8041526 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-09 | 2021-01-14 |  |  | 2021-01-06 |  |  | 2021-01-20 |  |  | 2021-01-15 |  | DELIVERED | CLOSED IN CELLO 01/18 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | BSIU9423839 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | HASU4487085 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MRKU3028690 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MRKU3214653 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-25 |  | DELIVERED | (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MRKU3918159 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MRKU4133303 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU1508326 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU8589783 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU8621150 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9017078 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9458216 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9474794 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9546301 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9755596 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 1/26 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | MSKU9846361 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | SUDU6571346 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | SUDU8558317 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72001051 | MAERSK SOFIA | MAEU206760488 | SDSMY20201207-01 | TCLU5653480 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001049 | MAERSK SOFIA | MAEU206760686 | SDSMY20201207-02 | MRKU6188060 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72001049 | MAERSK SOFIA | MAEU206760686 | SDSMY20201207-02 | SUDU5802522 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001049 | MAERSK SOFIA | MAEU206760686 | SDSMY20201207-02 | TCKU6779774 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001049 | MAERSK SOFIA | MAEU206760686 | SDSMY20201207-02 | TCNU9173039 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001049 | MAERSK SOFIA | MAEU206760686 | SDSMY20201207-02 | TGHU7875320 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-10 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-19 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | MONACO BRIDGE | HDMUMYWB0883907 | SDSMY20201213-01 | GAOU6182048 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-15 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72001054 | MONACO BRIDGE | HDMUMYWB0883907 | SDSMY20201213-01 | DFSU6708726 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-15 | 2021-01-14 |  |  | 2021-01-08 |  |  | 2021-01-21 |  |  | 2021-01-21 |  | DELIVERED | (GTGNAE20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | BMOU5441588 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | DFSU6866850 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | EGHU9217849 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | EITU1007913 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | EITU9021013 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | FSCU8637210 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | HMCU9219279 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | TCKU6148491 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | TCNU3879500 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (PIONEERNBNEW20)
PIONEER | 72000096 | COSCO SHIPPING SAKURA | EGLV040000377596 | PTIK20S12685 | TGBU8030711 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-05 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (PIONEERNBNEW20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | CSNU6142532 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | DFSU7284073 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | GCXU5294847 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | CLOSED IN CELLO 01/21 (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOCU7310945 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOCU7569480 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-20 |  | DELIVERED | (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOCU7777164 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOLU8803367 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOLU9534370 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 1/25 (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | OOLU9746277 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | (GTGNAE20)
GTG | 72000110 | COSCO SHIPPING SAKURA | OOLU2652188540 | PTIK20S12684 | TCNU7398381 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-14 | 2021-01-16 |  |  | 2021-01-11 |  |  | 2021-01-22 |  |  | 2021-01-21 |  | DELIVERED | CLOSED IN CELLO 01/22 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | CMAU4218994 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | CMAU4400566 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-25 |  |  | 2021-01-25 |  | DELIVERED | CLOSED IN CELLO 1/26 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | CMAU7489388 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | SEGU4631575 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TCLU6674261 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TCNU5389797 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-25 |  |  | 2021-01-25 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TCNU6556440 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TCNU7529711 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-25 |  |  | 2021-01-25 |  | DELIVERED | CLOSED IN CELLO 1/28 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TCNU8193724 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TEMU7896532 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-25 |  |  | 2021-01-25 |  | DELIVERED | CLOSED IN CELLO 1/26 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | TRLU8187580 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (GTGNAE20)
GTG | 72001054 | APL SENTOSA | CMDUAYN0629745 | SDSMY20201218-02 | UETU5279986 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-20 | 2021-01-18 |  |  | 2021-01-08 |  |  | 2021-01-22 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (GTGNAE20)
PIONEER | 72001054 | YM WIDTH | ONEYPKGA71200900 | NEDFPKGAWL86361 | BSIU9810041 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | ONEYPKGA71200900 | NEDFPKGAWL86361 | KKFU7678111 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-27 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | ONEYPKGA71200900 | NEDFPKGAWL86361 | NYKU4314842 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-26 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | ONEYPKGA71200900 | NEDFPKGAWL86361 | NYKU4332595 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-26 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | ONEYPKGA71200900 | NEDFPKGAWL86361 | TCLU8370714 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-26 |  |  | 2021-01-22 |  | DELIVERED | CLOSED IN CELLO 1/25 (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | HDMUMYNW0883936 | SDSMY20201213-02 | CLKU5010663 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-19 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-26 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72001054 | YM WIDTH | HDMUMYNW0883936 | SDSMY20201213-02 | KOCU4688855 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-19 | 2021-01-20 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | TEMU6449993 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | EITU9021836 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-25 |  | DELIVERED | (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | EITU1924928 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-25 |  | DELIVERED | (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | TCNU3906870 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | FCIU9187459 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 1/27 (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | EITU9160235 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-25 |  | DELIVERED | CLOSED IN CELLO 1/26 (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | GAOU6322216 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-25 |  | DELIVERED | CLOSED IN CELLO 1/26 (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | CARU9451847 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-25 |  | DELIVERED | (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | HMCU9129339 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 1/27 (GTGNAE20)
GTG | 72000109 | EVER LENIENT | EGLV040000381429 | PTIK20S12686 | OCGU8083940 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-16 | 2021-01-21 |  |  | 2021-01-07 |  |  | 2021-01-27 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 1/27 (GTGNAE20)
PIONEER | 72000096 | CMA CGM LAPEROUSE | EGLV040000377600 | PTIK20S12689 | BMOU4629420 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-24 | 2021-01-22 |  |  | 2021-01-07 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 1/27 (PIONEERNBNEW20)
PIONEER | 72000096 | CMA CGM LAPEROUSE | EGLV040000377600 | PTIK20S12689 | DRYU9200738 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-24 | 2021-01-22 |  |  | 2021-01-07 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 1/27 (PIONEERNBNEW20)
PIONEER | 72000096 | CMA CGM LAPEROUSE | EGLV040000377600 | PTIK20S12689 | EITU9108181 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-24 | 2021-01-22 |  |  | 2021-01-07 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | CMA CGM LAPEROUSE | EGLV040000377600 | PTIK20S12689 | FCIU9303728 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-24 | 2021-01-22 |  |  | 2021-01-07 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000096 | CMA CGM LAPEROUSE | EGLV040000377600 | PTIK20S12689 | TGBU5817318 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-24 | 2021-01-22 |  |  | 2021-01-07 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | (PIONEERNBNEW20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | BMOU4515834 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | CAAU5477470 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | CAIU8015040 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | CRSU9070643 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | DRYU9636146 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | DRYU9640700 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | GAOU6082820 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | GCXU5061491 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | SEGU5809342 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCKU7357536 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCLU6353195 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCNU1818569 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCNU4869488 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCNU5645060 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TCNU8187383 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TDRU4121424 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TGBU5493672 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TGBU7177190 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | TLLU4455642 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU7030558 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU7061395 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU7150091 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU7175530 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU7177908 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-26 |  | DELIVERED | CLOSED IN CELLO 01/27 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8629617 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8773537 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8838089 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8876896 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8904977 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-27 |  | DELIVERED | CLOSED IN CELLO 1/28 (PIONEERNB20)
PIONEER | 72000110 | NORTHERN JADE | ZIMUSEL7046531 | PTIK20S12688 | ZCSU8954983 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-19 | 2021-01-24 |  |  | 2021-01-12 |  |  | 2021-01-28 |  |  | 2021-01-28 |  | DELIVERED | CLOSED IN CELLO 1/29 (PIONEERNB20)
PIONEER | 72000107 | YM WARRANTY | HDMUBUWB5066654 | PTIK20S12690 | KOCU4297589 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72000107 | YM WARRANTY | HDMUBUWB5066654 | PTIK20S12690 | TCNU7900289 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-03 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/04 (PIONEERNB20)
PIONEER | 72000108 | YM WARRANTY | HDMUBUWB5066686 | PTIK20S12691 | CAIU7311217 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72000108 | YM WARRANTY | HDMUBUWB5066686 | PTIK20S12691 | HMMU6160198 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-08 |  |  | 2021-02-06 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | DFSU6945292 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-02 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/01 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | GCXU5054173 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-03 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/01 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | HDMU6652970 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-02 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/01 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | KOCU4267671 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-03 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/01 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | TGBU6231126 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-02 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/01 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | KOCU4272678 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 638 | 22 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72000100 | YM WARRANTY | HDMUBUWB5066834 | PTIK20S12692 | KOCU4821700 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260R | 20 | 376 | 13 | 2020-12-27 | 2021-01-26 |  |  | 2021-01-19 |  |  | 2021-02-02 |  |  | 2021-01-29 |  | DELIVERED | CLOSED IN CELLO 02/03 (PIONEERNB20)
PIONEER | 72001054 | MOL MISSION | ONEYPKGA71194700 | NEDFPKGAWL86416 | KKFU7527060 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-28 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (PIONEERNB20)
PIONEER | 72001054 | MOL MISSION | ONEYPKGA71194700 | NEDFPKGAWL86416 | MOTU0679107 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-28 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (PIONEERNB20)
PIONEER | 72001054 | MOL MISSION | ONEYPKGA71194700 | NEDFPKGAWL86416 | TCNU6856664 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-28 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (PIONEERNB20)
PIONEER | 72001054 | MOL MISSION | ONEYPKGA71194700 | NEDFPKGAWL86416 | TEMU8575769 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-28 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72001054 | MOL MISSION | ONEYPKGA71194700 | NEDFPKGAWL86416 | UETU5839170 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-16 | 2021-01-28 |  |  | 2021-01-19 |  |  | 2021-02-05 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (PIONEERNB20)
PIONEER | 72001053 | MOL MISSION | HDMUKULM86930700 | SDSMY20201218-03 | KOCU4232818 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-12-18 | 2021-01-28 |  |  | 2021-01-26 |  |  | 2021-02-05 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72001053 | MOL MISSION | HDMUKULM86930700 | SDSMY20201218-03 | DRYU9210551 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-12-18 | 2021-01-28 |  |  | 2021-01-26 |  |  | 2021-02-05 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
PIONEER | 72001053 | AL QIBLA | HDMUKULM29436900 | PLIMY4B01879 | CAIU7296642 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-12-28 | 2021-01-30 |  |  | 2021-01-20 |  |  | 2021-02-09 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (PIONEERNB20)
PIONEER | 72001053 | AL QIBLA | HDMUKULM29436900 | PLIMY4B01879 | KOCU4223518 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-12-28 | 2021-01-30 |  |  | 2021-01-20 |  |  | 2021-02-08 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001053 | AL QIBLA | HDMUKULM29436900 | PLIMY4B01879 | TCNU7733828 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2020-12-28 | 2021-01-30 |  |  | 2021-01-20 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (PIONEERNB20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | BEAU4099054 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | CAIU9360041 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | CMAU6151400 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | CMAU6313007 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | CMAU7061023 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | CXDU1846756 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | FCIU8755934 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | FFAU1602094 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 27 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | TCNU2632326 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0641654 | SDSMY20201230-05 | TRLU7283023 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001050 | CMA CGM BRAZIL | CMDUAYN0632477 | SDSMY20201230-03 | BMOU5348135 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001050 | CMA CGM BRAZIL | CMDUAYN0632477 | SDSMY20201230-03 | CAIU7631680 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001050 | CMA CGM BRAZIL | CMDUAYN0632477 | SDSMY20201230-03 | TCLU8138313 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001050 | CMA CGM BRAZIL | CMDUAYN0632477 | SDSMY20201230-03 | TCNU3102300 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001050 | CMA CGM BRAZIL | CMDUAYN0632477 | SDSMY20201230-03 | TCNU5731600 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | APHU6958899 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | APHU7255150 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | APHU7362944 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | BEAU4127120 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | BMOU6709778 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | CAIU9766489 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | CMAU6103211 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | CMAU6311236 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | CNCU5503495 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | CSOU4105359 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | SEGU4653553 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | SEGU5022681 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | TCKU6366195 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | TCNU1224382 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0629740 | SDSMY20201230-04 | TGBU5424706 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0645531 | SDSMY20201230-10 | CMAU4669914 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0645531 | SDSMY20201230-10 | CMAU6263570 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0645531 | SDSMY20201230-10 | CMAU6314322 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0645531 | SDSMY20201230-10 | CMAU7246032 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | CLOSED IN CELLO 02/10 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0645531 | SDSMY20201230-10 | CMAU7783181 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-09 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | CMAU4225910 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | CMAU4772835 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | CMAU7818117 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | SEGU4354423 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | TCKU6360978 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | TCLU6459443 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | TCNU5669421 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | TEMU8332202 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0645529 | SDSMY20201230-08 | TGHU6320673 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-09 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | BEAU4016532 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/10 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | BEAU4788407 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | BHCU4962264 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | BHCU4978975 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | CMAU4141573 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | CMAU6465611 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | FDCU0251726 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | GESU6724517 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | SEGU5221805 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | TCLU6587742 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | UETU5533160 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642300 | SDSMY20201230-09 | XINU8230470 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0642296A | SDSMY20201230-11 | APHU6731204 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0642296A | SDSMY20201230-11 | SEGU4984382 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0642296A | SDSMY20201230-11 | TCNU7976263 | Q.PEAK DUO L-G8.2 420 | 12004247R | 20 | 660 | 32 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA20); 32 PALLET IDS
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | APHU7296204 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | BEAU4069867 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | BMOU4056571 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | BMOU4342852 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | BMOU5664827 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | BMOU6579421 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | CAIU9218680 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | CAIU9402980 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | CMAU4760259 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | CMAU4839292 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | CMAU4928553 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | GLDU7425902 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | GVTU5016527 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | SEGU4698476 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | SEGU5190068 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | SEGU6198551 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | SEGU6365725 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCKU6361043 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCLU6545460 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCLU8267711 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCNU3224099 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCNU3408985 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCNU4044152 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TCNU5275937 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TGBU6803685 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TLLU4276689 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | CMA CGM BRAZIL | CMDUAYN0642296B | SDSMY20201230-12 | TLLU4566728 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | BMOU5301009 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | CMAU4925702 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | CMAU5338417 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | CMAU7271143 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | TCNU7488757 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001053 | CMA CGM BRAZIL | CMDUAYN0644026 | SDSMY20201230-07 | TEMU7397301 | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 638 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-10 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | APHU6506923 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | BEAU4036776 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | BMOU5570029 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CAIU9128838 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CAIU9310170 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CAIU9608293 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CAIU9669663 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CMAU4538200 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 25 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/10 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CMAU7082941 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CMAU7335593 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CMAU7651035 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/05 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | CXDU1842940 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-04 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | DFSU6314379 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | FCIU9368544 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | GESU6565328 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | MAGU5758169 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | SEGU6358583 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCKU6289099 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCLU6358290 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU2838641 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU3451261 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU4061503 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU4532861 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU5106156 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-05 |  | DELIVERED | CLOSED IN CELLO 02/08 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU6153240 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU6391588 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TCNU7674094 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TGHU9842922 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TRLU5932519 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (GTGBA20)
GTG | 72001055 | CMA CGM BRAZIL | CMDUAYN0642298 | SDSMY20201230-06 | TRLU7262308 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-03 | 2021-01-31 |  |  | 2021-01-22 |  |  | 2021-02-08 |  |  | 2021-02-08 |  | DELIVERED | (GTGBA20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BEAU4369490 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BEAU4382819 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BEAU4469077 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BMOU4779879 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BMOU4827278 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | BMOU5459587 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | DRYU9428461 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EGHU9193367 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EGHU9409137 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EGHU9454624 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EGHU9655260 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EISU9212968 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EITU1398572 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EITU1585090 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EITU1920250 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EMCU9642631 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | EMCU9839148 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | FFAU2102869 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | FSCU7104710 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | GAOU6156748 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | TCLU9320106 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | TCNU1662115 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | TCNU7766400 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | TEMU8948409 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770452 | PLIMY4B01869 | TGBU6513623 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | CAAU5344353 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EGHU9642540 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EISU8283421 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EISU9444393 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EISU9918569 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EITU1233607 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-08 |  | DELIVERED | CLOSED IN CELLO 02/09 (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EITU1879650 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EITU9057470 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EITU9102440 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | EMCU9834526 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | HMCU9127017 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | TEMU8921120 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | TGBU6773298 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | TGBU6891270 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (PIONEERNB20)
PIONEER | 72001055 | EVER LISSOME | EGLV091030770461 | PLIMY4B01881 | TLLU4035681 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | CAIU9783758 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | EITU1822398 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | HMCU9135563 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | TCLU6463989 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | TCNU6630960 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | TEMU6045482 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
PIONEER | 72001054 | EVER LISSOME | EGLV091030770461 | PLIMY4B01882 | TLLU4130122 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2020-12-23 | 2021-02-04 |  |  | 2021-01-22 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (PIONEERNB20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | APHU6365194 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | APHU6584295 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | APHU7035833 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | BMOU5490978 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | CMAU5036438 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001054 | APL YANGSHAN | CMDUAYN0637439 | SDSMY20201231-02 | SEGU6353771 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CAIU9761825 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU5049250 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU7060639 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCKU6248377 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCNU8350844 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TLLU4343447 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TRLU5637365 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | BMOU4764518 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | BMOU6139525 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU4364772 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU4719635 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU6251203 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU6314106 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU7020636 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU7409607 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | CMAU7500506 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | DFSU6628446 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | ECMU9453659 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | FCIU8924778 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | FCIU9097674 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | FCIU9227227 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | FCIU9350545 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | GATU8813829 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | GCXU5044010 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | SEGU4344003 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | SEGU4636772 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCLU1498642 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCNU3415496 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCNU5683081 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001058 | APL YANGSHAN | CMDUAYN0637765 | SDSMY20201231-01 | TCNU7236077 | Q.PEAK DUO L-G8.2 425 | 12004246R | 20 | 660 | 22 | 2021-01-07 | 2021-02-05 |  |  | 2021-01-26 |  |  | 2021-02-11 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | HLBU1956187 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/10 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | HLBU2146909 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | TCLU5510047 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | TCNU9243331 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5316386 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-15 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5357533 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5391923 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5604715 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5618977 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-12 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA20)
GTG | 72001055 | SEASPAN GANGES | HLCUKUL201222490 | SDSMY20201222-01 | UACU5948325 | Q.PEAK DUO L-G8.2 430 | 12004245R | 20 | 660 | 22 | 2020-12-26 | 2021-02-06 |  |  | 2021-01-29 |  |  | 2021-02-15 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA20)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | BSIU9628905 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | BSIU9918951 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | CAAU5127450 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | CAIU7254713 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | CAIU7638827 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | CAIU7688242 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | DFSU6717630 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | DFSU6803831 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | DRYU9233080 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | FSCU8497079 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | GAOU6208800 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | GAOU6212158 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6002973 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6018481 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6038615 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/19 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6054200 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6149603 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/19 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6191521 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6207818 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | HMMU6209575 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4059343 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4255238 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4265940 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4525185 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4702568 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4750102 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | KOCU4751140 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | SEGU5694650 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | TCNU7903349 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | HYUNDAI HOPE | HDMUBUWB5068908 | PTIK20S12701 | TGBU6343110 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2020-12-31 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000108 | COSCO SHIPPING JASMINE | EGLV040000424829 | PTIK21S01002 | TCNU3114065 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-04 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-09 |  | DELIVERED | CLOSED IN CELLO 02/10 (GTGBA18)
GTG | 72000108 | COSCO SHIPPING JASMINE | EGLV040000424829 | PTIK21S01002 | FCIU7182191 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-04 | 2021-02-07 |  |  | 2021-01-27 |  |  | 2021-02-12 |  |  | 2021-02-11 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | BEAU5035408 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | CAIU4427116 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | CAIU4429211 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | CAIU9229113 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | DFSU6486146 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | FCIU8692055 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | GVCU5324458 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | MAGU5621284 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU2314578 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU2712972 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU4377826 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU4401795 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU5848936 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU6909337 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TCNU7037012 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TEMU6185334 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TEMU6651469 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TEMU6796689 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-13 |  | DELIVERED | CLOSED IN CELLO 02/15 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TEMU8128138 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TGCU5080100 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TGHU6237682 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TGHU6601114 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TGHU6926742 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TGHU6958333 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TLLU5205761 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | TLLU5911937 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | ZCSU8685729 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000110 | SEAMAX FAIRFIELD | ZIMUSEL7046534 | PTIK20S12698 | ZCSU8803842 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72000109 | SEAMAX FAIRFIELD | ZIMUSEL200216561 | PTIK20S12699 | TGBU5065503 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA18)
GTG | 72000109 | SEAMAX FAIRFIELD | ZIMUSEL200216561 | PTIK20S12699 | ZCSU8734166 | Q.PEAK DUO L-G6P.3/BFG 420 | 30381260F | 18 | 638 | 22 | 2020-12-28 | 2021-02-09 |  |  | 2021-01-25 |  |  | 2021-02-15 |  |  | 2021-02-10 |  | DELIVERED | CLOSED IN CELLO 02/11 (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | BMOU4109250 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-16 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | BMOU4523296 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-16 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | CAIU8900084 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-15 |  |  | 2021-02-10 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | TCNU4400700 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-15 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | TEMU6189999 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-16 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | MAERSK SANA | SSPHPKL8076670 | SDSMY20201223-01 | ZCSU7112790 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-30 | 2021-02-09 |  |  | 2021-01-28 |  |  | 2021-02-16 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18)
PSS | Kearsarge Return | RETURN-NJPO15111003R | HDMUBUWB4987611 | NEDFSEATSSE55121 | NJPO15111003R-RETURN | Q.PEAK DUO L-G8.3.1.V 420 | 30382860R | 20 | 29 | 1 | 2021-02-17 | 2021-02-18 | [8 empty] | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (DAMAGE-PSS) - PLT# 200308_K2_PLKG83_420A_746; Return Damaged from Kearsarge
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TCNU6786090 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1873034 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TEMU8405607 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EGSU9019127 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TCLU8726282 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | DRYU9236540 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1166643 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TCLU9144882 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/19 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | HMCU9195834 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1796067 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TCLU9350693 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EGSU9170853 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | GAOU6323547 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | HMCU9016034 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EGHU9718460 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EGSU9138105 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | TCNU1659390 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1340668 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1457680 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1327835 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | MAGU5412221 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1909369 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EGSU9057111 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EISU9430379 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EISU9059490 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1823291 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EISU9159293 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | LTIU8037480 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | IMTU9040947 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001055 | TRITON | EGLV091030764711 | PLIMY4B01858 | EITU1903490 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TEMU6380921 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | BMOU5309740 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TCNU6809106 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | FFAU2090860 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EGHU9700414 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1584129 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | BMOU4465461 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1187327 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EISU9317830 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1304552 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | BMOU4796114 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TLLU4584110 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | BMOU5008520 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EMCU9657626 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EISU9390445 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EGSU9022687 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TGBU6609812 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TCNU2137169 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/19 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EMCU9814387 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU9079247 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | DRYU9447517 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EGSU9044449 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EGHU9301097 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | MAGU5417856 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | HMCU9133920 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1662031 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-15 |  | DELIVERED | CLOSED IN CELLO 02/16 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TGBU6486512 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | GAOU6261471 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1823687 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | DRYU9895105 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EITU1462732 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TEMU8959569 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | GAOU6220195 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-23 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TCLU9144265 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EMCU9809668 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-17 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | EISU9369371 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | BMOU4983331 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-17 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18)
GTG | 72001054 | TRITON | EGLV091030764711 | PLIMY4B01859 | TCLU8900326 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-01-21 | 2021-02-11 |  |  | 2021-01-25 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | NYKU5194124 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCLU1529002 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCLU7937850 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCLU7963171 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCLU7988483 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCNU7214360 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA69022400 | NEDFPKGAWL10610 | TCNU9942004 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | HDMUKULM57125700 | PLIMY4B01915 | HMMU6279314 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | HDMUKULM57125700 | PLIMY4B01915 | KOCU4559816 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | HDMUKULM57125700 | PLIMY4B01915 | KOCU4724551 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA72122600 | NEDFPKGAWP08394 | NYKU0808873 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA72122600 | NEDFPKGAWP08394 | NYKU5123917 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA72122600 | NEDFPKGAWP08394 | TEMU7474732 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA72122600 | NEDFPKGAWP08394 | TGHU9074676 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001054 | DALIAN EXPRESS | ONEYPKGA72122600 | NEDFPKGAWP08394 | TLLU4553799 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-07 | 2021-02-12 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18)
GTG | 72001049 | MSC UBERTY | MAEU206769974 | SDSMY20201207-04 | INKU2301303 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-18 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/23 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206769974 | SDSMY20201207-04 | MRKU4147631 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-18 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206769974 | SDSMY20201207-04 | MRSU3638192 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-18 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206769974 | SDSMY20201207-04 | MSKU0271179 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-18 |  |  | 2021-02-16 |  | DELIVERED | (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206769974 | SDSMY20201207-04 | MSKU0535163 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-18 |  |  | 2021-02-16 |  | DELIVERED | CLOSED IN CELLO 02/17 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | FSCU9655306 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | MRKU3195888 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | MSKU1230003 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | SUDU8693359 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | TCNU9556830 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001051 | MSC UBERTY | MAEU206895279 | SDSMY20201207-05 | TGHU7961347 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MIEU2034750 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MRKU3851899 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MRKU5872458 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MRKU6472311 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MRSU3269509 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU0103806 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU0226858 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU0304539 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU0911466 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU9268216 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | MSKU9851542 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/26 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | PONU7407251 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | PONU7587981 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | TGHU6184664 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (GTGBA18) NYC GLOBAL
GTG | 72001049 | MSC UBERTY | MAEU206787298 | SDSMY20201207-03 | TGHU8000909 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-10 | 2021-02-12 |  |  | 2021-01-29 |  |  | 2021-02-19 |  |  | 2021-02-22 |  | DELIVERED | (GTGBA18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | AMFU8781177 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | BEAU5533627 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | CAIU9538560 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | MOTU0626196 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | MOTU5819623 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | MOTU6720677 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | NYKU4097789 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | NYKU4139586 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | NYKU5240580 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TCLU5694200 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TCLU5796096 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TCLU8261919 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TCNU4830547 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TCNU5983129 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001054 | ONE MAXIM | ONEYPKGA56666700 | NEDFPKGAWG77840 | TEMU8923720 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | CAIU9039730 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | CAIU9188992 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | DRYU6031193 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | FSCU8652874 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | KKFU7527898 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | NYKU0848177 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | NYKU4075666 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | NYKU4155910 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-19 |  |  | 2021-02-17 |  | DELIVERED | CLOSED IN CELLO 02/18 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | NYKU4728293 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | NYKU5119500 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | ONEU0222658 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | TCLU8837136 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | TCNU6349654 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-19 |  | DELIVERED | CLOSED IN CELLO 02/22 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | TEMU7457756 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001057 | ONE MAXIM | ONEYPKGA63943300 | NEDFPKGAVZ92723 | TGHU6624819 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-04 | 2021-02-15 |  |  | 2021-02-09 |  |  | 2021-02-22 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/23 (PIONEERNBNEW18) NYC GLOBAL
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | AMFU8792119 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | BMOU5536847 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | DRYU9150750 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | DRYU9870010 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | FSCU8075094 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | FSCU8077190 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLBU1203250 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLBU1433078 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLBU2001269 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLBU2223482 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLXU8383530 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | HLXU8453052 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | TCLU6521956 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | TCNU3278860 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | TCNU7360107 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | TEMU7507630 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | TRLU7307974 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | UACU5079290 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | UACU5332290 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
PIONEER | 72001055 | YM WARMTH | HLCUKUL201223543 | YASVPKG0026002 | UACU5644195 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-13 | 2021-02-16 |  |  | 2021-02-08 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/02 (PIONEERNBNEW18)
PIONEER | 72001054 | YM WARMTH | HDMUKULM11052200 | SDSMY20201227-01 | HJMU1566464 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-11 | 2021-02-16 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 03/02 (PIONEERNBNEW18)
PIONEER | 72001054 | YM WARMTH | HDMUKULM11052200 | SDSMY20201227-01 | KOCU4279311 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-11 | 2021-02-16 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNBNEW18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | APHU7008951 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | CMAU5729812 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | CMAU6408340 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | FFAU1604040 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | GLDU7558778 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TCKU7610979 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TCNU4007117 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TCNU7303555 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TEMU7897170 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TGHU6388760 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TLLU4382119 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0647243 | SDSMY20210108-06 | TLLU4804493 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | (GTGBA18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | CMAU4433410 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | CMAU7324496 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-03-01 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/02 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | FDCU0012845 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | SEKU4301942 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | TCNU7057723 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | TLLU4353580 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM PANAMA | CMDUAYN0643778 | SDSMY20210108-04 | TLLU5029298 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001053 | CMA CGM PANAMA | CMDUAYN0643782 | SDSMY20210108-01 | GVTU5003427 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001053 | CMA CGM PANAMA | CMDUAYN0643782 | SDSMY20210108-01 | BMOU6416492 | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-03-04 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0643786 | SDSMY20210108-05 | CAUI9207881 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/27 (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0643786 | SDSMY20210108-05 | SEGU4287330 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | (GTGBA18)
GTG | 72001058 | CMA CGM PANAMA | CMDUAYN0643786 | SDSMY20210108-05 | TLLU4792469 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | APHU6881586 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | BEAU4045422 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | BMOU4933599 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | BMOU6715261 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | CAIU9482100 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | CMAU4451270 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | CMAU4752567 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | CMAU5572868 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/27 (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | CMAU6017387 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | TCKU7831814 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (GTGBA18)
GTG | 72001055 | CMA CGM PANAMA | CMDUAYN0644034 | SDSMY20210108-02 | TCNU1775317 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (GTGBA18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | CMAU5826237 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | FSCU7285795 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | SGRU5022610 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | TCKU7613725 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | TCKU7824029 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | TCNU4610922 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001055 | CMA CGM PANAMA | CMDUAYN0648600 | SDSMY20210108-03 | TGBU6711505 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | APHU6812414 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | APHU7134060 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | APHU7246440 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | CMAU4632284 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | CMAU4714633 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | CMAU4991258 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | CMAU7623060 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | FCIU9361750 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | GLDU9943639 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCLU6541090 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCLU8602574 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU2198858 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU3163120 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU3231478 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU6129937 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU6351203 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-23 |  | DELIVERED | (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU7590558 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU7660552 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TCNU8357237 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TGHU8368188 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | TGHU9601226 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/02 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM PANAMA | CMDUAYN0647132 | SDSMY20210114-01 | UETU5003025 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-16 | 2021-02-17 |  |  | 2021-02-09 |  |  | 2021-02-24 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18)
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | CAIU4339479 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | CAIU9839522 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21 | BIFACIAL HOLD
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | CAIU9842444 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | GAOU6203789 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | GCXU5017668 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21 | BIFACIAL HOLD
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324301 | PTIK21S01008 | KOCU4355094 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM06099200 | PTIK21S01010 | BMOU5184005 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM06099200 | PTIK21S01010 | HDMU6863340 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM06099200 | PTIK21S01010 | TCNU1696671 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000107 | HYUNDAI VICTORY | HDMUSELM14946200 | PTIK21S01011 | CAIU7690738 | Q.PEAK DUO L-G8P.3.1/BFG 415 | 30368159F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | BHCU4993460 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-26 |  |  | 2021-02-27 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | BMOU4595830 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | BMOU5178450 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | BSIU9294027 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | CAIU4351598 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | CAIU4427374 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-03 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | CAIU4441156 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | CAIU7152619 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | CAIU7386828 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | GAOU6224138 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | HDMU6683288 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-27 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | HDMU6813714 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | HMMU6087693 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | HMMU6190269 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4312744 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-05 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4319137 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-27 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4329536 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4444993 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-27 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4496261 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-27 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4574364 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-26 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4591145 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4636110 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/25 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | KOCU4731083 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | TEMU7259386 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-03-01 |  | DELIVERED | CLOSED IN CELLO 03/03 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72000108 | HYUNDAI VICTORY | HDMUSELM25324300 | PTIK21S01007 | TGBU6353720 | Q.PEAK DUO L-G8P.3.1/BFG 420 | 30368160F | 18 | 638 | 22 | 2021-01-23 | 2021-02-20 |  |  | 2021-02-12 |  |  | 2021-02-25 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 03/01 (PIONEERNB18); ON HOLD IN CELLO PER QCELLS 03/01/21
PIONEER | 72001054 | YANTIAN EXPRESS | HDMUKULM61487400 | SDSMY20210117-01 | HMMU6224461 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-18 | 2021-02-24 |  |  | 2021-02-18 |  |  | 2021-03-02 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18) NYC GLOBAL
PIONEER | 72001054 | YANTIAN EXPRESS | HDMUKULM61487400 | SDSMY20210117-01 | HMMU6176888 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-18 | 2021-02-24 |  |  | 2021-02-18 |  |  | 2021-03-02 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18) NYC GLOBAL
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | CLHU9029049 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | HASU4689126 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | HASU5027886 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | MRKU4046997 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | MRKU4248030 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | MRSU3989324 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | MSKU0752615 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | MSKU1133472 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-03 |  |  | 2021-03-02 |  | DELIVERED | (GTGBA18)
GTG | 72001051 | SPIRIT OF HAMBURG | MAEU206731140 | SDSMY20201130-02 | UETU5045400 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-03 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/03 (GTGBA18)
GTG | 72001049 | SPIRIT OF HAMBURG | MAEU206707126 | SDSMY20201130-01 | INKU2901313 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001049 | SPIRIT OF HAMBURG | MAEU206707126 | SDSMY20201130-01 | MSKU0382402 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001049 | SPIRIT OF HAMBURG | MAEU206707126 | SDSMY20201130-01 | MSKU0707072 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
GTG | 72001049 | SPIRIT OF HAMBURG | MAEU206707126 | SDSMY20201130-01 | TCNU9635707 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2020-12-23 | 2021-02-25 |  |  | 2021-01-22 |  |  | 2021-03-04 |  |  | 2021-03-01 |  | DELIVERED | (GTGBA18)
PIONEER | 72001054 | ONE MUNCHEN | HDMUKULM40016100 | SDSMY20210116-01 | TLLU5769226 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-26 | 2021-02-27 |  |  | 2021-02-22 |  |  | 2021-03-04 |  |  | 2021-03-03 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18)
PIONEER | 72001054 | ONE MUNCHEN | HDMUKULM40016100 | SDSMY20210116-01 | BSIU9234814 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-26 | 2021-02-27 |  |  | 2021-02-22 |  |  | 2021-03-04 |  |  | 2021-03-02 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | APHU7041100 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-03 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | APHU7337237 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | APHU7351003 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | APHU7353388 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | BEAU4104398 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | BMOU4911120 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | BMOU6071533 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-13 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CAIU7060261 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CAIU9407175 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-12 |  | DELIVERED | CLOSED IN CELLO 03/15 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU4173009 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU4784667 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-03 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU5287515 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU5658853 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-03 |  | DELIVERED | CLOSED IN CELLO 03/04 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU5741130 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU7170087 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU7238931 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU7332151 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | CMAU7741550 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | FSCU8213568 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-12 |  | DELIVERED | CLOSED IN CELLO 03/15 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | GESU6540335 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-13 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | SEGU5476431 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCKU6326593 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCLU8636846 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU1111133 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU1567838 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU2249913 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU5516079 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU5860443 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TCNU8355569 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TEMU6466603 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TGHU9838732 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TLLU4276420 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/16 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LYRA | CMDUAYN0658200 | SDSMY20210126-01 | TLLU5100293 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | BEAU4032512 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CAXU9322547 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CLHU8893344 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CMAU4203021 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CMAU4594918 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-08 |  | DELIVERED | CLOSED IN CELLO 03/09 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CMAU5604163 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | CMAU7369124 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-08 |  | DELIVERED | CLOSED IN CELLO 03/09 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | GAOU6032520 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | INKU2596987 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | TCLU9600046 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | TGHU6313801 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-08 |  | DELIVERED | CLOSED IN CELLO 03/09 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LYRA | CMDUAYN0658206 | SDSMY20210126-02 | TLLU4326877 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-01-27 | 2021-02-28 |  |  | 2021-02-23 |  |  | 2021-03-11 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | CMDUAYN0656726 | SDSMY20210204-01 | SEGU4405963 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-02-26 |  |  | 2021-03-09 |  |  | 2021-03-08 |  | DELIVERED | CLOSED IN CELLO 03/09 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | DFSU6445532 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | EISU9980328 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | EITU1561988 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | EITU1573248 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | EITU1584828 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | EMCU9888369 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | HMCU9039868 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | IMTU9027441 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | MAGU5252205 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | TGBU6573134 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 27 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060635 | PLIMY4C00156 | TGBU6723960 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | BEAU4385654 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-12 |  | DELIVERED | CLOSED IN CELLO 03/15 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | BMOU5340772 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | DRYU9799143 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | EGHU9616140 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-13 |  | DELIVERED | CLOSED IN CELLO 03/15 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | EGSU9152870 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/11 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | EITU1869100 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-11 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | EITU1980304 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | FFAU2102529 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | GAOU6264790 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | LTIU8017307 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/11 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | OCGU8026446 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/11 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | SEGU5898951 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-06 |  | DELIVERED | CLOSED IN CELLO 03/08 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | TCNU4993992 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNB18)
PIONEER | 72001054 | CMA CGM LEO | EGLV091130060627 | PLIMY4C00157 | TGBU6625618 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/11 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EGHU9286006 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EGSU9046971 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-11 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EISU9278991 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EITU1278197 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EITU1801667 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EITU1915757 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | EITU1974467 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | GAOU6370430 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | HMCU9224275 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TEMU6060620 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-10 |  |  | 2021-03-10 |  | DELIVERED | CLOSED IN CELLO 03/12 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TEMU8816125 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TEMU8952179 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TGBU7024951 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TGHU6937562 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | CMA CGM LEO | EGLV091130060601 | PLIMY4C00152 | TLLU4056299 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-03 |  |  | 2021-03-01 |  |  | 2021-03-09 |  |  | 2021-03-09 |  | DELIVERED | CLOSED IN CELLO 03/10 (PIONEERNB18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | BMOU4718641 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | CAAU5289220 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | CAIU4425601 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | HMCU9020327 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | SEGU5280140 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | SLSU8051047 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-17 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TCNU8111304 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-16 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TCNU8186659 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TCNU8930689 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TCNU8936692 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-17 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TCNU8937092 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | TGBU7178480 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-17 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | WFHU5137926 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-17 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72001058 | MAERSK SARNIA | SSPHPKL8079423 | SDSMY20210203-02 | ZCSU7054420 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-06 | 2021-03-12 |  |  | 2021-03-08 |  |  | 2021-03-18 |  |  | 2021-03-15 |  | DELIVERED | CLOSED IN CELLO 03/17 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | BMOU5480877 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-04-01 |  |  | 2021-04-01 |  | DELIVERED | CLOSED IN CELLO 04/06 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | BSIU9965001 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-31 |  |  | 2021-03-26 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | CAAU5202425 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-31 |  |  | 2021-03-26 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | DRYU9858457 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-31 |  |  | 2021-03-26 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | EGHU9518204 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-04-01 |  |  | 2021-03-31 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | EITU1210767 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-04-01 |  |  | 2021-03-31 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | EITU1532486 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-31 |  |  | 2021-03-26 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | EITU1894588 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-31 |  |  | 2021-03-26 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | TCNU4079170 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-04-01 |  |  | 2021-04-01 |  | DELIVERED | CLOSED IN CELLO 04/06 (PIONEERNBNEW18)
PIONEER | 72000110 | CMA CGM ARGENTINA | EGLV040000434891 | PTIK21S01004 | TGBU6311860 | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259F | 18 | 638 | 22 | 2021-01-27 | 2021-03-23 |  |  | 2021-03-15 |  |  | 2021-03-29 |  |  | 2021-03-24 |  | DELIVERED | CLOSED IN CELLO 04/01 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | BEAU4066024 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | BEAU5396669 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | BMOU4915044 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-27 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | CMAU7512169 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | FSCU7127887 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | SEGU6375955 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-27 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | TCLU1699708 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | TCNU3418812 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-27 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | TCNU3485390 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685601 | SDSMY20210318-01 | TRLU7132351 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-26 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685602 | SDSMY20210318-02 | BEAU4041643 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685602 | SDSMY20210318-02 | GESU4596633 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-29 |  | DELIVERED | CLOSED IN CELLO 04/30 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | APHU7242384 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18) (1 PALLET TO THIS CONTAINER WITHOUT PLT ID 150000000791490 NEED TO NOTIFY THE WAREHOUSE-DONE)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | BEAU4656870 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | CAIU8031870 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | GESU6454577 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | TCNU5494848 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72101004 | CMA CGM MEXICO | CMDUAYN0685604 | SDSMY20210318-03 | TGBU5063959 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-03-21 | 2021-04-24 |  |  | 2021-04-16 |  |  | 2021-04-29 |  |  | 2021-04-28 |  | DELIVERED | CLOSED IN CELLO 04/29 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | BSIU9227760 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-06 |  |  | 2021-05-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | GAOU6209621 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-11 |  |  | 2021-05-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | GAOU6212564 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-11 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | HDMU6845440 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | HMMU6146121 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | HMMU6330864 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | KOCU4072242 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/12 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | KOCU4250690 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | KOCU4561330 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | KOCU4717721 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/12 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM57942100 | SDSKNYC002 | TCNU6926355 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM09525100 | SDSKNYC003 | CAAU5140719 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM09525100 | SDSKNYC003 | CAIU9479370 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/11 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM09525100 | SDSKNYC003 | HMMU6175990 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM09525100 | SDSKNYC003 | HMMU6317163 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-07 |  |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/11 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | BMOU5916662 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | CAIU7346384 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | CAIU7371392 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | DRYU9181582 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/10 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | DRYU9219836 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/10 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | HMMU6067491 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/10 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4005413 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/12 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4021034 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4241759 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/11 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4372640 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4423347 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/11 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4738690 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/13 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | KOCU4764019 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/07 (PIONEERNBNEW18)
PIONEER | 72100011 | YM WARRANTY | HDMUSELM60401000 | SDSKNYC001 | TCNU6334042 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-01 | 2021-05-02 |  |  | 2021-04-27 |  |  | 2021-05-10 |  |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/10 (PIONEERNBNEW18)
PIONEER | 72100011 | COSCO SHIPPING ORCHID | EGLV040100115712 | PTIK21S04057 | EITU1928348 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-05 | 2021-05-09 |  |  | 2021-05-03 |  |  | 2021-05-13 |  |  | 2021-05-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/17 (PIONEERNBNEW18)
PIONEER | 72100011 | COSCO SHIPPING ORCHID | EGLV040100115712 | PTIK21S04057 | EITU1641492 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-05 | 2021-05-09 |  |  | 2021-05-03 |  |  | 2021-05-13 |  |  | 2021-05-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/17 (PIONEERNBNEW18)
PIONEER | 72100011 | COSCO SHIPPING ORCHID | EGLV040100115712 | PTIK21S04057 | BMOU4565624 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-05 | 2021-05-09 |  |  | 2021-05-03 |  |  | 2021-05-13 |  |  | 2021-05-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/17 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM09831600 | SDSKNYC004 | KOCU4576120 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-20 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/21 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | CAIU7409517 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-19 |  |  | 2021-05-19 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/20 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | CAIU7472551 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | CAIU7706794 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | DFSU6722811 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | GAOU6189192 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | GCXU5011931 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-19 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | HDMU6711585 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-19 |  |  | 2021-05-19 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/20 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | HMMU6155843 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | HMMU6221544 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | HMMU6314349 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | KOCU4401060 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-14 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | KOCU4416435 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/19 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | KOCU4579113 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-17 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | KOCU4588861 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-19 |  |  | 2021-05-19 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/20 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | TCLU1795234 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-17 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/18 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | TCLU8947175 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-19 |  |  | 2021-05-19 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/20 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI SPEED | HDMUSELM29275900 | SDSKNYC005 | TGBU6050067 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-07 | 2021-05-11 |  |  | 2021-05-03 |  |  | 2021-05-18 |  |  | 2021-05-18 |  | DELIVERED (FYI, Heavy Congestion at Global terminal; possible demurrage/per-diem charges) | DELIVERED CLOSED IN CELLO 05/20 (PIONEERNBNEW18)
PIONEER | 72100011 | CMA CGM T. ROOSEVELT | EGLV040100115721 | PTIK21S04059 | EISU8245993 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-19 |  |  | 2021-05-11 |  |  | 2021-05-25 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/25 (PIONEERNBNEW18)
PIONEER | 72100011 | CMA CGM T. ROOSEVELT | EGLV040100115721 | PTIK21S04059 | EISU8206317 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-19 |  |  | 2021-05-11 |  |  | 2021-05-27 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/25 (PIONEERNBNEW18)
PIONEER | 72100011 | CMA CGM T. ROOSEVELT | EGLV040100115721 | PTIK21S04059 | TEMU8804891 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-19 |  |  | 2021-05-11 |  |  | 2021-05-26 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/25 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | HDMUSELM45082800 | SDSKNYC006 | HMMU6190309 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | HDMUSELM59440200 | SDSKNYC007 | DFSU6480364 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | HDMUSELM59440200 | SDSKNYC007 | HDMU6829602 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/02 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | HDMUSELM59440200 | SDSKNYC007 | TCNU7653764 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-16 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | ONEYPUSB03612900 | HW2104035 | NYKU4415914 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-20 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | ONEYPUSB03612900 | HW2104035 | TGBU5312809 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-20 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-26 |  |  | 2021-05-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | ONEYPUSB03612900 | HW2104035 | TRLU8205581 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-20 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI VICTORY | ONEYPUSB03612900 | HW2104035 | UETU5845281 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-20 | 2021-05-20 |  |  | 2021-05-10 |  |  | 2021-05-27 |  |  | 2021-05-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/26 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | BEAU6234868 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | BMOU5678311 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | CAIU8949607 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | CAIU9238096 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/28 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | DFSU6177553 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/28 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | DFSU6927278 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | FSCU8604285 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | OOCU7691857 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/28 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | OOCU7855098 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/28 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | OOLU8301902 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | OOLU9203454 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | TCNU1374470 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | TCNU3862093 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/28 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | TCNU6581187 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM CHILE | COSU6297807690 | SDSMY20210421-03 | TGBU5341263 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-04-27 | 2021-05-24 |  |  | 2021-05-18 |  |  | 2021-05-28 |  |  | 2021-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/01 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI DRIVE | YMLUE360784923 | HW2105005 | YMLU9005706 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/07 (PIONEERNBNEW18)
GTG | 72100021 | HYUNDAI DRIVE | HDMUSELM58374500 | PTIK21S05070 | CAIU7201842 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/16 (GTGSS18)
GTG | 72100021 | HYUNDAI DRIVE | HDMUSELM58374500 | PTIK21S05070 | KOCU4325865 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18)
GTG | 72100021 | HYUNDAI DRIVE | HDMUSELM58374500 | PTIK21S05070 | KOCU4789953 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18)
PIONEER | 72100011 | HYUNDAI DRIVE | HDMUSELM40778200 | SDSKNYC008 | CAIU8806503 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/07 (PIONEERNBNEW18)
PIONEER | 72100011 | HYUNDAI DRIVE | HDMUSELM40778200 | SDSKNYC008 | GAOU6364335 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-03 | 2021-05-29 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/07 (PIONEERNBNEW18)
PIONEER | 72100011 | EVER LEGION | EGLV040100115704 | PTIK21S04058 | FCIU7292692 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-14 | 2021-05-31 |  |  | 2021-05-24 |  |  | 2021-06-07 |  |  | 2021-06-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/04 (PIONEERNBNEW18)
PIONEER | 72100011 | EVER LEGION | EGLV040100115704 | PTIK21S04058 | BMOU5779873 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-14 | 2021-05-31 |  |  | 2021-05-24 |  |  | 2021-06-04 |  |  | 2021-06-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/03 (PIONEERNBNEW18)
PIONEER | 72100011 | EVER LEGION | EGLV040100115704 | PTIK21S04058 | EITU1975740 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-04-14 | 2021-05-31 |  |  | 2021-05-24 |  |  | 2021-06-07 |  |  | 2021-06-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/08 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | FCIU9835063 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/03 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | FSCU8733451 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/04 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | OOLU8621085 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/03 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | TCNU3740198 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/04 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | TEMU6810555 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/04 (PIONEERNBNEW18)
PIONEER | 72101010 | CMA CGM T. JEFFERSON | COSU6298431800 | SDSMY20210429-01 | TLLU4503967 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 24 | 2021-05-02 | 2021-05-31 |  |  | 2021-05-25 |  |  | 2021-06-04 |  |  | 2021-06-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/08 (PIONEERNBNEW18)
SC | 72100025 | CAPE KORTIA | ZIMUSEL200220794 | ENISCHS2104040 | ZCSU7326473 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-05 | 2021-06-01 |  |  | 2021-05-26 |  |  | 2021-06-07 |  |  | 2021-06-02 |  | DELIVERED | CLOSED IN CELLO 06/15 (CELL# MO18) (Customer - Conti.)
SC | 72100025 | CAPE KORTIA | ZIMUSEL200220794 | ENISCHS2104040 | ZCSU7326621 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-05 | 2021-06-01 |  |  | 2021-05-26 |  |  | 2021-06-07 |  |  | 2021-06-08 |  | DELIVERED | CLOSED IN CELLO 06/15 (CELL# MO18) (Customer - Conti.)
SC | 72100025 | CAPE KORTIA | ZIMUSEL200220794 | ENISCHS2104040 | ZCSU7326719 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-05 | 2021-06-01 |  |  | 2021-05-26 |  |  | 2021-06-07 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/15 (CELL# MO18) (Customer - Conti.)
PIONEER | 72100021 | HYUNDAI RESPECT | HDMUSELM58374501 | PTIK21S05071 | GAOU6195045 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI RESPECT | HDMUSELM58374501 | PTIK21S05071 | KOCU4826810 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/08 (PIONEERNBNEW18)
GTG | 72100021 | HYUNDAI RESPECT | HDMUSELM20535600 | PTIK21S05073 | CAIU7480114 | Q.PEAK DUO XL-G9P.3/BFG.L455 | 30396567F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-09 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18) --> Bay Av
GTG | 72100021 | HYUNDAI RESPECT | HDMUSELM20535600 | PTIK21S05073 | CAIU9965120 | Q.PEAK DUO XL-G9P.3/BFG.L455 | 30396567F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18) --> Bay Av
GTG | 72100021 | HYUNDAI RESPECT | HDMUSELM20535600 | PTIK21S05073 | GAOU6185617 | Q.PEAK DUO XL-G9P.3/BFG.L455 | 30396567F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18) --> Bay Av
GTG | 72100021 | HYUNDAI RESPECT | HDMUSELM20535600 | PTIK21S05073 | HMMU6159957 | Q.PEAK DUO XL-G9P.3/BFG.L455 | 30396567F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (GTGSS18) --> Bay Av
GTG | 72100021 | HYUNDAI RESPECT | HDMUSELM20535600 | PTIK21S05073 | TLLU8299450 | Q.PEAK DUO XL-G9P.3/BFG.L450 | 30396566F | 18 | 580 | 20 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/17 (GTGSS18) --> Bay Av
PIONEER | 72100021 | HYUNDAI RESPECT | HDMUSELM15457900 | EGNYC2105002 | KOCU4740362 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 87 | 3 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI RESPECT | HDMUSELM15457900 | EGNYC2105002 | KOCU4740362 | Q.PEAK DUO XL-G9P.3/BFG 450 | 30396066F | 18 | 145 | 5 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI RESPECT | HDMUSELM15457900 | EGNYC2105002 | KOCU4740362 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 348 | 12 | 2021-05-08 | 2021-06-02 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | BSIU9573530 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | DRYU9418015 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | TCKU6746615 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU7013925 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU7150168 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU7198449 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-11 |  |  | 2021-06-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU7198808 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU7257449 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU8604959 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073149 | PTIK21S05075 | ZCSU8693489 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/11 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | BEAU5147500 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | CAIU4342338 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/09 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | CAIU8743494 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | SEGU5190330 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-11 |  |  | 2021-06-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | TCNU9886209 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | TGBU7135620 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/09 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | TLLU5314741 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | ZCSU7098310 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | ZCSU8259364 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | GSL ARCADIA | ZIMUSEL7073150 | PTIK21S05076 | ZCSU8780120 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-10 | 2021-06-04 |  |  | 2021-06-03 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/10 (PIONEERNBNEW18)
PIONEER | 72100021 | CMA CGM ARGEN | EGLV040100148696 | HW2105032 | DRYU9240089 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-14 | 2021-06-06 |  |  | 2021-05-27 |  |  | 2021-06-11 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | CMA CGM ARGEN | EGLV040100148696 | HW2105032 | BMOU4993216 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 348 | 12 | 2021-05-14 | 2021-06-06 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | CMA CGM ARGEN | EGLV040100148696 | HW2105032 | BMOU4993216 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 232 | 8 | 2021-05-14 | 2021-06-06 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | CMA CGM ARGEN | EGLV040100148696 | HW2105032 | TEMU7113149 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-14 | 2021-06-06 |  |  | 2021-05-27 |  |  | 2021-06-10 |  |  | 2021-06-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/14 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | YMLUE360785248 | HW2105019 | BEAU4823302 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-16 |  |  | 2021-06-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/16 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | YMLUE360785248 | HW2105019 | FBLU0139690 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-17 |  |  | 2021-06-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/18 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | YMLUE360785248 | HW2105019 | TCNU3895100 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-16 |  |  | 2021-06-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/16 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | YMLUE360785276 | HW2105047 | YMLU8554595 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-16 |  |  | 2021-06-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/16 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | YMLUE360785276 | HW2105047 | TCNU4941936 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-15 |  |  | 2021-06-11 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/16 (PIONEERNBNEW18)
GTG | 72100021 | HYUNDAI PRIDE | YMLUE360785249 | HW2105037 | TCNU3804327 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-17 |  |  | 2021-06-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (GTGSS18)
GTG | 72100021 | HYUNDAI PRIDE | YMLUE360785249 | HW2105037 | YMMU6037560 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-16 |  |  | 2021-06-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (GTGSS18)
GTG | 72100021 | HYUNDAI PRIDE | YMLUE360785249 | HW2105037 | BEAU4884123 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-02 |  |  | 2021-06-17 |  |  | 2021-06-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (GTGSS18)
PIONEER | 72100021 | HYUNDAI PRIDE | HDMUSELM77919800 | PTIK21S05077 | BSIU9935429 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-17 |  |  | 2021-06-18 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | HDMUSELM77919800 | PTIK21S05077 | CAIU7554393 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-17 |  |  | 2021-06-18 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | HDMUSELM77919800 | PTIK21S05077 | HMMU6059120 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-17 |  |  | 2021-06-18 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | HDMUSELM77919800 | PTIK21S05077 | KOCU4244824 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-16 |  |  | 2021-06-18 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI PRIDE | HDMUSELM77919800 | PTIK21S05077 | KOCU4805099 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-09 |  |  | 2021-06-03 |  |  | 2021-06-16 |  |  | 2021-06-18 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | HDMU6677412 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-24 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | TGBU6466943 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | CAIU4386022 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/25 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | HDMU6881690 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | KOCU5166747 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | TCNU6875129 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | BMOU5208241 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | HDMUSELM65054600 | PTIK21S05078 | TCNU6222762 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-16 | 2021-06-17 |  |  | 2021-06-08 |  |  | 2021-06-23 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | YMLUE360785250 | HW2105060 | CAIU7970600 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-20 | 2021-06-17 |  |  | 2021-06-09 |  |  | 2021-06-23 |  |  | 2021-06-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | YMLUE360785250 | HW2105060 | SEGU6856251 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-20 | 2021-06-17 |  |  | 2021-06-09 |  |  | 2021-06-24 |  |  | 2021-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | ONE HAWK | YMLUE360785250 | HW2105060 | BEAU5160863 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-20 | 2021-06-17 |  |  | 2021-06-09 |  |  | 2021-06-24 |  |  | 2021-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/24 (PIONEERNBNEW18)
PIONEER | 72100021 | GUTHORM MAERSK | ZIMUSEL7072381 | PTIK21S05081 | TCNU7260643 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-26 | 2021-06-21 |  |  | 2021-06-14 |  |  | 2021-06-29 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100021 | GUTHORM MAERSK | ZIMUSEL7072381 | PTIK21S05081 | ZCSU8467970 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-26 | 2021-06-21 |  |  | 2021-06-14 |  |  | 2021-06-29 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | HDMUSELM92732700 | PTIK21S05079 | CAIU7503101 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-25 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | HDMUSELM92732700 | PTIK21S05079 | DRYU9189979 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-25 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | HDMUSELM92732700 | PTIK21S05079 | HMMU6150287 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-25 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/02 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | HDMUSELM92732700 | PTIK21S05079 | HMMU6219444 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-25 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/02 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | HDMUSELM92732700 | PTIK21S05079 | TRLU6891184 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-25 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100021 | HYUNDAI HONOUR | HDMUSELM94470800 | HW2105048 | KOCU4246365 | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | 2021-05-27 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-06-30 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | YMLUE360784955 | SHTCS2105271 | YMMU6316204 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-27 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | YMLUE360784955 | SHTCS2105271 | TEMU7775232 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-27 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-07-01 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI HONOUR | YMLUE360784955 | SHTCS2105271 | TLLU5151650 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-27 | 2021-06-23 |  |  | 2021-06-14 |  |  | 2021-06-30 |  |  | 2021-06-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM24839300 | PTIK21S05084 | BSIU9208008 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM24839300 | PTIK21S05084 | BSIU9934340 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM24839300 | PTIK21S05084 | CAIU7488603 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM24839300 | PTIK21S05084 | KOCU4189990 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM24839300 | PTIK21S05084 | TGBU6387607 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-07-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/07 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | TGBU5890290 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | GAOU6232468 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | KOCU4190857 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | CLKU5017518 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/02 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | TCNU7902189 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-07-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/07 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | CAIU7467663 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | HYUNDAI DUBAI | HDMUSELM45229700 | PTIK21S05085 | KOCU4788284 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-28 | 2021-06-27 |  |  | 2021-06-16 |  |  | 2021-07-02 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
PIONEER | 72100031 | MAERSK YUKON | ZIMUSEL7072382 | PTIK21S06086 | TCNU2975393 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-02 | 2021-06-27 |  |  | 2021-06-22 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | MAERSK YUKON | ZIMUSEL7072382 | PTIK21S06086 | ZCSU7075450 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-02 | 2021-06-27 |  |  | 2021-06-22 |  |  | 2021-07-01 |  |  | 2021-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/30 (PIONEERNBNEW18)
PIONEER | 72100031 | COSCO FORTUNE | EGLV040100239454 | PTIK21S05087 | TEMU8542430 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-31 | 2021-06-27 |  |  | 2021-06-17 |  |  | 2021-07-05 |  |  | 2021-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/01 (PIONEERNBNEW18)
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | BEAU5143207 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-12 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | DRYU9135484 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED CLOSED IN CELLO 06/15 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | GCXU5347356 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-12 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | TCKU6758318 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | TCNU7189910 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | TGBU5367252 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-11 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | TGHU6754113 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-12 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | TLLU5931379 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-10 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | ZCSU7158127 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-11 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | MSC BILBAO | ZIMUSEL7070429 | PTIK21S05072 | ZCSU8521290 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-04 | 2021-06-06 |  |  | 2021-05-25 |  |  | 2021-06-10 |  |  | 2021-06-12 |  | DELIVERED CLOSED IN CELLO 06/14 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | CMA CGM ARGENTINA | EGLV040100148581 | HW2105033 | TGBU6207285 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-14 | 2021-06-11 |  |  | 2021-06-03 |  |  | 2021-06-19 |  |  | 2021-06-15 |  | DELIVERED CLOSED IN CELLO 06/16 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | CMA CGM ARGENTINA | EGLV040100148581 | HW2105033 | TCNU3460427 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-14 | 2021-06-11 |  |  | 2021-06-03 |  |  | 2021-06-19 |  |  | 2021-06-15 |  | DELIVERED CLOSED IN CELLO 06/16 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | CMA CGM ARGENTINA | EGLV040100148581 | HW2105033 | EGSU9170616 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-14 | 2021-06-11 |  |  | 2021-06-03 |  |  | 2021-06-19 |  |  | 2021-06-16 |  | DELIVERED CLOSED IN CELLO 06/17 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | HYUNDAI PRIDE | YMLUE360785116 | HW2105036 | TCNU1081614 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-14 |  |  | 2021-06-04 |  |  | 2021-06-23 |  |  | 2021-06-21 |  | DELIVERED CLOSED IN CELLO 06/21 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | HYUNDAI PRIDE | YMLUE360785116 | HW2105036 | FFAU1519591 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-13 | 2021-06-14 |  |  | 2021-06-04 |  |  | 2021-06-23 |  |  | 2021-06-18 |  | DELIVERED CLOSED IN CELLO 06/21 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | COSCO SHIPPING SAKURA | EGLV040100148599 | HW2105055 | FCIU7185396 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-20 | 2021-06-23 |  |  | 2021-06-11 |  |  | 2021-07-01 |  |  | 2021-06-25 |  | DELIVERED CLOSED IN CELLO 06/29 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | COSCO SHIPPING SAKURA | EGLV040100148599 | HW2105055 | TGBU7279696 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-20 | 2021-06-23 |  |  | 2021-06-11 |  |  | 2021-06-30 |  |  | 2021-06-28 |  | DELIVERED CLOSED IN CELLO 06/29 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | COSCO SHIPPING SAKURA | EGLV040100148599 | HW2105055 | EITU1058504 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-20 | 2021-06-23 |  |  | 2021-06-11 |  |  | 2021-07-01 |  |  | 2021-06-25 |  | DELIVERED CLOSED IN CELLO 06/29 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100033 | CMA CGM LAPEROUSE | EGLV040100275299 | HW2105079 | TEMU6176435 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-29 | 2021-06-27 |  |  | 2021-06-18 |  |  | 2021-07-06 |  |  | 2021-07-06 |  | DELIVERED CLOSED IN CELLO 07/07 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100033 | CMA CGM LAPEROUSE | EGLV040100275299 | HW2105079 | EITU1426761 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-05-29 | 2021-06-27 |  |  | 2021-06-18 |  |  | 2021-07-06 |  |  | 2021-07-06 |  | DELIVERED CLOSED IN CELLO 07/07 (PNCW18) | Customer - Conti.
NORFOLK, VA | 72100024 | CMA CGM LAPEROUSE | EGLV040100148572 | HW2105078 | EISU9373392 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-05-29 | 2021-06-27 |  |  | 2021-06-18 |  |  | 2021-07-06 |  |  | 2021-07-06 |  | DELIVERED CLOSED IN CELLO 07/07 (PNCW18) | Customer - Conti.
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699100 | PTIK21S06092 | CAIU8253096 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699100 | PTIK21S06092 | GAOU6355610 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699100 | PTIK21S06092 | HMMU6097916 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | BSIU9311470 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-26 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/27 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | CAIU7662994 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/21 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | HMMU6112271 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-26 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/27 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | KOCU4277915 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-23 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | KOCU4671580 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-27 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/28 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | TCLU5327606 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 290 | 10 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/21 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | TCNU9913650 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/21 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699101 | PTIK21S06091 | TGBU6233263 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-22 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699102 | PTIK21S06095 | BSIU9915016 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699102 | PTIK21S06095 | GAOU6217268 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-16 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699102 | PTIK21S06095 | KOCU4288210 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM04699102 | PTIK21S06095 | KOCU4915687 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM82933000 | PTIK21S06090 | BSIU9345171 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-16 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM82933000 | PTIK21S06090 | CAIU4570560 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-16 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM82933000 | PTIK21S06090 | DRYU9184895 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-16 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM82933000 | PTIK21S06090 | KOCU4183729 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-17 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/20 (PIONEERNBNEW18)
PIONEER | 72100031 | ANTWERPEN EXPRESS | HDMUSELM82933000 | PTIK21S06090 | TGBU6359210 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-11 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-17 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/19 (PIONEERNBNEW18)
PIONEER | 72100031 | COSCO SHIPPING JASMINE | EGLV040100239471 | PTIK21S06093 | EITU9065048 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-10 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100031 | COSCO SHIPPING JASMINE | EGLV040100239471 | PTIK21S06093 | TCLU8894603 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-10 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO (PIONEERNBNEW18)
PIONEER | 72100031 | COSCO SHIPPING JASMINE | EGLV040100239471 | PTIK21S06093 | TCNU2263300 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-10 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | APHU6648086 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | BMOU5344973 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | CMAU4334232 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-13 |  | DELIVERED | PIONEERNBNEW18 (CUSTOMER - IMPA)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | CMAU4808331 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | GESU5577875 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/14 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | TCNU2988153 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM PANAMA | CMDUAYN0752482 | SDSMY20210610-05 | TCNU3201616 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | APHU7226681 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | BMOU5945758 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | CAIU8008020 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | CMAU4084880 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | CMAU4600203 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | CMAU5054874 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | FCIU8351249 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | FCIU8584580 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | TCNU5461973 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM PANAMA | CMDUAYN0743022 | SDSMY20210610-03 | TGHU6349738 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-06-14 | 2021-07-10 |  |  | 2021-07-02 |  |  | 2021-07-15 |  |  | 2021-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/16 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | KOCU4302746 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | BSIU9948175 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-23 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | KOCU4309669 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | KOCU4232628 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 86 | 3 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-23 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | KOCU4232628 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 56 | 2 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100044 | ONE WREN | HDMUSELM95840700 | PTIK21S06099 | KOCU4232628 | Q.PEAK DUO XL-G9P.3/BFG.L 460 | 30396568F | 18 | 239 | 9 | 2021-06-16 | 2021-07-15 |  |  | 2021-07-07 |  |  | 2021-07-22 |  |  | 2021-07-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/26 (PIONEERNBNEW18)
PIONEER | 72100031 | GRETE MAERSK | ZIMUSEL7073722 | PTIK21S06088 | TCNU6483386 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-19 | 2021-07-21 |  |  | 2021-07-14 |  |  | 2021-07-27 |  |  | 2021-07-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/28 (PIONEERNBNEW18)
PIONEER | 72100031 | GRETE MAERSK | ZIMUSEL7073722 | PTIK21S06088 | GAOU6441318 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-19 | 2021-07-21 |  |  | 2021-07-14 |  |  | 2021-07-27 |  |  | 2021-07-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/28 (PIONEERNBNEW18)
PIONEER | 72100031 | SEAMAX FAIRFIELD | ZIMUSEL7073787 | PTIK21S06096 | TEMU6197042 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-10 | 2021-07-21 |  |  | 2021-07-07 |  |  | 2021-07-28 |  |  | 2021-07-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/28 (PIONEERNBNEW18)
PIONEER | 72100031 | GERDA MAERSK | ZIMUSEL7074455 | PTIK21S05080 | BSIU9753342 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-13 | 2021-07-28 |  |  | 2021-07-23 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/04 (PIONEERNBNEW18)
PIONEER | 72100031 | GERDA MAERSK | ZIMUSEL7074455 | PTIK21S05080 | TLLU5208605 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-13 | 2021-07-28 |  |  | 2021-07-23 |  |  | 2021-08-03 |  |  | 2021-08-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/03 (PIONEERNBNEW18)
PIONEER | 72100031 | EVER LIVING | EGLV040100165761 | PTIK21S05083 | EISU9345908 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-30 | 2021-08-02 |  |  | 2021-07-22 |  |  | 2021-08-09 |  |  | 2021-08-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/06 (PIONEERNBNEW18)
PIONEER | 72100031 | EVER LIVING | EGLV040100165761 | PTIK21S05083 | TEMU6049533 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-30 | 2021-08-02 |  |  | 2021-07-22 |  |  | 2021-08-06 |  |  | 2021-08-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/06 (PIONEERNBNEW18)
PIONEER | 72100031 | EVER LIVING | EGLV040100165761 | PTIK21S05083 | TLLU4136861 | Q.PEAK DUO XL-G9P.3/BFG.L 450 | 30396566F | 18 | 580 | 20 | 2021-06-30 | 2021-08-02 |  |  | 2021-07-22 |  |  | 2021-08-09 |  |  | 2021-08-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/06 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM JULES VERNE | EGLV091130392611 | PLIMY4C00868 | EITU1126960 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-05 | 2021-08-03 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | EGLV091130392611 | PLIMY4C00868 | TGBU9771299 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-05 | 2021-08-03 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | EGLV091130373854 | PLIMY4C00838 | EITU1540049 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-05 | 2021-08-03 |  |  | 2021-07-26 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | APHU6753918 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | APHU6812841 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | APHU6964973 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | APHU7119106 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | CMAU5200243 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | CMAU6505381 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | CMAU7542667 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-11 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | FCIU8339095 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | FDCU0019536 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-11 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | SEGU4961197 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | SEGU6306933 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-14 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | TCLU6575720 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | TCNU6316687 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | TCNU7685714 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-14 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | TEMU6644259 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752545 | SDSMY20210626-01 | TRLU7193803 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | APHU6479582 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | CMAU4203633 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | FSCU6829600 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | FSCU8768756 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | GESU5687358 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | GESU6341061 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | GESU6629757 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | SEGU5210354 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | TLLU8083991 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | CMDUAYN0743317 | SDSMY20210617-02 | TRLU6605275 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | BEAU4020928 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | BEAU4652690 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | BMOU5293325 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | CMAU5555942 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | CMAU5645840 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | CMAU5795943 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | CMAU7018161 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | CZZU0455444 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | GESU6431801 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TCKU6254277 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-11 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TCLU1869928 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TCNU4285545 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TGBU5819970 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TGHU6478524 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-09 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/10 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TGHU9780585 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | TRLU7330470 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM JULES VERNE | CMDUAYN0752542 | SDSMY20210617-03 | XINU8169868 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | CBHU8945685 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-14 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | CCLU7042463 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | DFSU7401930 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-13 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18) (JERSEY AVE)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | OOLU8664718 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB18)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | OOLU8846327 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNBNEW18)
PIONEER | 72101015 | CMA CGM JULES VERNE | COSU6302503110 | SDSMY20210610-04 | SEGU6329522 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-07-04 | 2021-08-03 |  |  | 2021-07-28 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | CAIU7138170 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-09 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | CAIU7487382 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-09 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | CAIU9933570 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | DFSU6201557 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-09 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | DFSU6652437 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-09 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | DRYU9203737 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-06 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | FSCU8497504 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-06 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | GCXU5052062 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-06 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | HMMU6009134 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/17 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | KOCU4670497 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-06 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | KOCU4717172 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-09 |  | DELIVERED | CLOSED iN CELLO 08/10 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | TCNU1699006 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/17 (PIONEERNBNEW18)
PIONEER | 72100043 | HYUNDAI GOODWILL | HDMUSELM93486200 | PTIK21S07117 | TCNU5170242 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | CAIU7469590 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | CAIU9980510 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | DFSU6245410 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | DFSU6708080 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | HMMU6232087 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | KOCU4331003 | Q.PEAK DUO BLK ML-G9P+.0.3 375 | 30368516F | 18 | 512 | 16 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | KOCU4331003 | Q.PEAK DUO BLK ML-G9P+.0.1 375 | 30369116F | 18 | 250 | 8 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | KOCU4800862 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100037 | HYUNDAI GOODWILL | HDMUSELM93486201 | PTIK21S07126 | KOCU5186039 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 768 | 24 | 2021-07-10 | 2021-08-04 |  |  | 2021-07-26 |  |  | 2021-08-10 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/12 (PIONEERNBNEW18)
PIONEER | 72100031 | CEZANNE | ZIMUSEL7073783 | PTIK21S06089 | CAIU4338132 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-21 | 2021-08-07 |  |  | 2021-07-23 |  |  | 2021-08-12 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72100031 | CEZANNE | ZIMUSEL7073783 | PTIK21S06089 | GAOU6445890 | Q.PEAK DUO XL-G9P.3/BFG.L 455 | 30396567F | 18 | 580 | 20 | 2021-06-21 | 2021-08-07 |  |  | 2021-07-23 |  |  | 2021-08-12 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNBNEW18)
PIONEER | 72101013 | CMA CGM LEO | EGLV091130392620 | PLIMY4C00888 | EISU9210292 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-08 | 2021-08-09 |  |  | 2021-07-26 |  |  | 2021-08-13 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM LEO | EGLV091130392620 | PLIMY4C00888 | TEMU6241063 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-08 | 2021-08-09 |  |  | 2021-07-26 |  |  | 2021-08-13 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101013 | CMA CGM LEO | EGLV091130392620 | PLIMY4C00888 | EGHU9276672 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-07-08 | 2021-08-09 |  |  | 2021-07-26 |  |  | 2021-08-13 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | CAIU9969824 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | GCXU5026823 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | GESU6599328 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | HDMU6676566 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | HMMU6296501 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | KOCU4152733 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-19 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | CLOSED IN CELLO 08/20 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | KOCU4347205 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-19 |  | DELIVERED; Demurrage incured due to heavy congestion and unable to secure appointment with Global | CLOSED IN CELLO 08/20 (PIONEERNB18)
PIONEER | 72100043 | HYUNDAI SPEED | HDMUSELM12121401 | PTIK21S07121 | KOCU4564094 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100037 | HYUNDAI SPEED | HDMUSELM12121400 | PTIK21S07123 | GAOU6365394 | Q.PEAK DUO BLK ML-G9P+.0.3 380 | 30369117F | 18 | 603 | 19 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100037 | HYUNDAI SPEED | HDMUSELM12121400 | PTIK21S07123 | HMMU6308860 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 (PIONEERNB18)
PIONEER | 72100037 | HYUNDAI SPEED | HDMUSELM12121400 | PTIK21S07123 | HMMU6435021 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/20 (PIONEERNB18)
PIONEER | 72100037 | HYUNDAI SPEED | HDMUSELM12121400 | PTIK21S07123 | KOCU4304728 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-17 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (PIONEERNB18)
PIONEER | 72100037 | HYUNDAI SPEED | HDMUSELM12121400 | PTIK21S07123 | KOCU5166270 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-09 | 2021-08-10 |  |  | 2021-07-29 |  |  | 2021-08-16 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/23 (PIONEERNB18)
GTG | 72100051 | ONE APUS | HDMUSELM18406600 | PTIK21S07131 | KOCU4246004 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-20 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/10 GTGSS18
GTG | 72100051 | ONE APUS | HDMUSELM18406600 | PTIK21S07131 | KOCU4651223 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-23 |  | DELIVERED | CLOSED IN CELLO 08/31, RECLOSED IN CELLO ON 9/10 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM18406600 | PTIK21S07131 | SEGU6035338 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM18406600 | PTIK21S07131 | TLLU5294115 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 08/30 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM48752000 | PTIK21S07130 | CAIU7444502 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM48752000 | PTIK21S07130 | CAIU7451179 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM48752000 | PTIK21S07130 | HMMU6322431 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/03 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM48752000 | PTIK21S07130 | KOCU4462908 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/03 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM48752000 | PTIK21S07130 | TGBU6363035 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-20 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 09/13 GTGSS18
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | BSIU9617990 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-20 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/03 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | CAIU4564361 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/13 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | GAOU6229612 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/01 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | KOCU4111919 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 08/30 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | KOCU4247905 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/03 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | KOCU4471181 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-20 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | KOCU4614003 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | KOCU4952187 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | SEGU6043945 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGBA18)
GTG | 72100051 | ONE APUS | HDMUSELM14193200 | PTIK21S07127 | TLLU5840290 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-23 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 08/30 (GTGSS18)
GTG | 72100051 | ONE APUS | HDMUSELM18406601 | PTIK21S07132 | HDMU6812019 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-14 | 2021-08-16 |  |  | 2021-08-04 |  |  | 2021-08-24 |  |  | 2021-08-24 |  | DELIVERED | CLOSED IN CELLO 09/09 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | CAIU4482622 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | CAIU7232078 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | CAIU7456247 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | GAOU6230104 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-09 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | HMMU6454438 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4133395 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4315928 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-08 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4424894 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4576963 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4732691 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-09 |  |  | 2021-09-09 |  | DELIVERED | CLOSED IN CELLO 09/09 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | CAIU4566554 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | HMMU6271186 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4635053 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU4715117 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/28 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM96327400 | PTIK21S07137 | KOCU5061601 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-08 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM86167500 | PTIK21S07136 | CAIU4449120 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM86167500 | PTIK21S07136 | HDMU6652287 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/28 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM86167500 | PTIK21S07136 | HMMU6089377 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-04 |  | DELIVERED | CLOSED IN CELLO 09/07 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM86167500 | PTIK21S07136 | KOCU4149283 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-06 |  | DELIVERED | CLOSED IN CELLO 09/28 (GTGSS18)
GTG | 72100051 | SHANGHAI EXPRESS | HDMUSELM86167500 | PTIK21S07136 | KOCU4696001 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 580 | 20 | 2021-07-25 | 2021-08-30 |  |  | 2021-08-19 |  |  | 2021-09-07 |  |  | 2021-09-08 |  | DELIVERED | CLOSED IN CELLO 09/08 (GTGSS18)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | DFSU6539354 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | MAGU5614114 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | TCNU1760410 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | TCNU2476012 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | TEMU7252442 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | ZCSU7439968 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-03 |  | DELIVERED | CLOSED IN CELLO 09/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | ZCSU8435165 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | ZCSU8530814 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | ZCSU8608722 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086951 | PTIK21S07145 | ZCSU8639390 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | BSIU9699730 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | CRSU9011912 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | SEGU5756520 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | TCNU4237505 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | TCNU4401202 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | TCNU5367334 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | TCNU7937009 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-01 |  | DELIVERED | CLOSED IN CELLO 09/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | TLLU5224720 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | ZCSU7287459 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | GUNDE MAERSK | ZIMUSEL7086952 | PTIK21S07146 | ZCSU7315592 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | CRSU9051263 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | GLDU7421240 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8244596 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8478531 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8526250 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8688796 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-02 |  | DELIVERED | CLOSED IN CELLO 09/03 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8775735 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8782349 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-08 |  | DELIVERED | CLOSED IN CELLO 09/09 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8948419 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNDE MAERSK | ZIMUSEL7086953 | PTIK21S07147 | ZCSU8959028 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-07-29 | 2021-08-30 |  |  | 2021-08-20 |  |  | 2021-09-07 |  |  | 2021-09-07 |  | DELIVERED | CLOSED IN CELLO 09/08 PIONEERNB18 (JERSEY AVE)
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM10026700 | PTIK21S08142 | DFSU6233889 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM10026700 | PTIK21S08142 | GAOU6350732 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM10026700 | PTIK21S08142 | HMMU6184163 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM10026700 | PTIK21S08142 | HMMU6309487 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM10026700 | PTIK21S08142 | KOCU4310741 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | CAIU4427414 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | DFSU6949507 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-15 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HDMU6695592 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HDMU6732320 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HMMU6094590 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HMMU6098492 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HMMU6316613 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HMMU6433630 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | HMMU6459527 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4076124 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4148224 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4416630 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4600463 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4845846 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
GTG | 72100051 | NEW YORK EXPRESS | HDMUSELM62224600 | PTIK21S08144 | KOCU4887950 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-11 | 2021-09-08 |  |  | 2021-08-25 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/30 GTGSS18
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | TGHU6579031 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | TEMU6696709 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | GCXU5059323 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | ZCSU7149320 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | GAOU6107759 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | JZPU8028954 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | FCIU8913670 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | TLLU4859304 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | ZCSU7027030 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUSTAV MAERSK | ZIMUSEL7087726 | PTIK21S08157 | ZCSU7203530 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | FSCU8155292 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | JXLU8671303 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-10 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TCNU2760311 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TCNU2766496 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-13 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TCNU4297762 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TEMU7537912 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TGBU7140252 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TLLU4780236 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-14 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | TLLU4939694 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-15 |  |  | 2021-09-10 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | GUSTAV MAERSK | ZIMUSEL7087724 | PTIK21S08155 | ZCSU7180481 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-09 | 2021-09-09 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | APHU6294378 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | APHU6978067 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/20 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | CMAU4407220 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/21 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | FCIU8115433 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/21 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | GESU6900278 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | TCNU2987603 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | TCNU5159794 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | TCNU5549154 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | TLLU5781983 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | CMDUAYN0783420 | SDSMY20210806-01 | UESU5086978 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | COSU6309089480 | SDSMY20210806-02 | CSNU6596622 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-03 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | COSU6309089480 | SDSMY20210806-02 | TRHU4908422 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-03 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/21 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101019 | CMA CGM MEXICO | COSU6309089480 | SDSMY20210806-02 | WBPU7010670 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-14 | 2021-09-12 |  |  | 2021-09-03 |  |  | 2021-09-16 |  |  | 2021-09-16 |  | DELIVERED | CLOSED IN CELLO 09/17 PIONEERNB18 (JERSEY AVE)
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | KKFU7818194 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-20 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | KKFU8082641 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-19 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | MOTU6701152 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-19 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | ONEU0249140 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-20 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | TCLU1658695 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-19 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | TCLU9877909 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-19 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/28 GTGSS18
GTG | 72101019 | HYUNDAI FAITH | ONEYPKGB55269600 | SDSMY20210805-01 | TCNU5997800 | Q.PEAK DUO L-G8C.2 430 | 12005803F | 18 | 660 | 22 | 2021-08-09 | 2021-09-12 |  |  | 2021-09-02 |  |  | 2021-09-20 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 10/01 GTGSS18
PIONEER | 72100047 | EVER FAITH | EGLV040100339408 | PTIK21S07141 | DFSU7294908 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-05 | 2021-09-15 |  |  | 2021-09-01 |  |  | 2021-09-21 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | EVER FAITH | EGLV040100339408 | PTIK21S07141 | EISU8222750 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-05 | 2021-09-15 |  |  | 2021-09-01 |  |  | 2021-09-21 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | EVER FAITH | EGLV040100339408 | PTIK21S07141 | TCKU6078476 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-05 | 2021-09-15 |  |  | 2021-09-01 |  |  | 2021-09-21 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | HYUNDAI PRIDE | HDMUSELM77606100 | PTIK21S08148 | CAIU7452431 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-27 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/24PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | HYUNDAI PRIDE | HDMUSELM77606100 | PTIK21S08148 | HDMU6821197 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-27 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | HYUNDAI PRIDE | HDMUSELM77606100 | PTIK21S08148 | HDMU6835734 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-27 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | HYUNDAI PRIDE | HDMUSELM77606100 | PTIK21S08148 | KOCU4617804 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-27 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100050 | HYUNDAI PRIDE | HDMUSELM77606100 | PTIK21S08148 | TGBU6338536 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-27 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | CAIU7439065 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | CAIU7482164 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | CAIU9826947 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | CAXU8019602 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | DFSU6948326 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | GAOU6188806 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | HDMU6711081 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | HMMU6217879 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU4024943 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU4516584 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU4741883 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU4768333 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU4890608 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | KOCU5176365 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | HYUNDAI PRIDE | HDMUSELM00587600 | PTIK21S08149 | TCNU7704250 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-12 | 2021-09-16 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | BSIU9679604 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | BSIU9688170 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 | 2021-09-18 | 2 | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO ON 09/22, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | DRYU9638642 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | GAOU6096504 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | GAOU6450855 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | GLDU7112106 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | KSSU1009543 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | SEGU5203798 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | ZCSU8470546 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-11 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087728 | PTIK21S08159 | ZCSU8682000 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-11 |  | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | BSIU9710989 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | CAIU9226177 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 | 2021-09-22 | 6 | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | DFSU6941949 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | TCNU5502542 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 | 2021-09-22 | 6 | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | TCNU8762883 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | TEMU8389595 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 | 2021-09-22 | 6 | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | TGBU7215393 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 | 2021-09-22 | 6 | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | TGBU9301037 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | ZCSU7383961 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-10-04 | 2021-10-08 | 22 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE); CONTAINER WAS IN CLOSED AREA
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087727 | PTIK21S08158 | ZCSU8776454 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-08-15 | 2021-09-16 |  |  | 2021-09-09 | 2021-09-16 | 0 | 2021-09-22 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | COSU6309096450 | SDSMY20210817-02 | FSCU8619562 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-13 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | COSU6309096450 | SDSMY20210817-02 | CSNU6535313 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-13 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | COSU6309096450 | SDSMY20210817-02 | CCLU7239771 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-13 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | CAIU9651725 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | CMAU4690608 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/22, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | CMAU5278982 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | CXDU1678354 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/22, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | GAOU6052358 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | GESU6476302 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | TCLU5640647 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/27 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM CORTE REAL | CMDUAYN0783421 | SDSMY20210817-01 | TGHU9896256 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-08-23 | 2021-09-17 |  |  | 2021-09-08 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 PIONEERNB18 (JERSEY AVE)
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | CAIU4646407 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | CRXU9969559 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/23 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRKU2482292 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/23 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRKU3082310 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 09/28 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRKU6222879 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 09/23 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRSU3023705 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 09/28 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRSU4382762 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 09/24 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MRSU4825120 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-27 |  | DELIVERED | CLOSED IN CELLO 09/27 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | MSKU1766418 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/23 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MSC DITTE --> NORTHERN PRIORITY | SUDUN1SOL0170851 | HW2108013 | SUDU8643337 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-18 |  |  | 2021-09-10 |  |  | 2021-09-23 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 09/24 (PNCW18) DUKE PROJECT
PIONEER | 72100057 | COSCO SHIPPING JASMINE | EGLV040100364909 | SHTCS2108158 | EGHU9258257 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-27 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
GTG | 72100047 | ONE HAWK | HDMUSELM36636200 | PTIK21S08174 | CAIU4412800 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-07 | 6 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100047 | ONE HAWK | HDMUSELM36636200 | PTIK21S08174 | HMMU6081674 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100047 | ONE HAWK | HDMUSELM36636200 | PTIK21S08174 | HMMU6332173 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-04 | 10 | 2021-10-05 | 1 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100047 | ONE HAWK | HDMUSELM36636200 | PTIK21S08174 | KOCU4608422 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100047 | ONE HAWK | HDMUSELM36636200 | PTIK21S08174 | TCNU7043165 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | DFSU6706092 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | HDMU6766192 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | HMMU6286627 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | HMMU6321604 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-10-01 | 2021-10-01 | 7 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | KOCU4120016 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-04 | 10 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
GTG | 72100062 | ONE HAWK | HDMUSELM30405201 | PTIK21S08171 | KOCU4752907 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-10-01 | 2021-10-01 | 7 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | CAIU7663711 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-05 | 11 | 2021-10-08 | 3 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | GAOU6371843 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-09-30 | 6 | 2021-09-30 | 0 | DELIVERED | CLOSED IN CELLO 10/06 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | HDMU6768908 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-08 | 7 | DELIVERED | CLOSED IN CELLO 10/18 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | HDMU6838899 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-04 | 10 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | HMMU6326904 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-07 | 6 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | KOCU4130478 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-08 | 7 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | KOCU4534572 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | TCNU7237237 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-08 | 7 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72100050 | ONE HAWK | HDMUSELM30405200 | PTIK21S08173 | TLLU5780992 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-08-20 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-09-30 | 2021-10-01 | 7 | 2021-10-07 | 6 | DELIVERED | CLOSED IN CELLO 10/19 GTGBA18
GTG | 72101011 | CONTI CONTESSA | ONEYPKGB55178500 | SDSMY20210812-02 | DRYU9164179 | Q.PEAK DUO XL G10.3/BFG 470 | 12005560F | 18 | 600 | 20 | 2021-08-12 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-10-01 | 2021-10-01 | 7 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
GTG | 72101011 | CONTI CONTESSA | ONEYPKGB55178500 | SDSMY20210812-02 | ONEU0105986 | Q.PEAK DUO XL G10.3/BFG 470 | 12005560F | 18 | 600 | 20 | 2021-08-12 | 2021-09-24 |  |  | 2021-09-13 | 2021-09-24 | 0 | 2021-10-02 | 2021-10-01 | 7 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/13 GTGBA18
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | CAIU9227717 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-29 |  | DELIVERED | CLOSED IN CELLO 09/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | GAOU6087354 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-29 |  | DELIVERED | CLOSED IN CELLO 09/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | GAOU6108061 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-29 |  | DELIVERED | CLOSED IN CELLO 09/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | TCNU1832572 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-10-01 |  | DELIVERED | CLOSED IN CELLO 10/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU7013680 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU7033515 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU7389580 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU8694696 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU8885434 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100051 | GUNHILDE MAERSK | ZIMUSEL7087725 | PTIK21S08156 | ZCSU8904597 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-08-15 | 2021-09-26 |  |  | 2021-09-22 |  |  | 2021-09-30 |  |  | 2021-09-30 |  | DELIVERED | CLOSED IN CELLO 10/01 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | APL SOUTHAMPTON | EGLV040100337201 | SHTCS2108095 | EMCU8212317 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-15 | 2021-09-27 |  |  | 2021-09-09 | 2021-09-27 | 0 | 2021-10-01 | 2021-10-01 | 4 | 2021-10-05 | 4 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100047 | APL SOUTHAMPTON | EGLV040100337201 | SHTCS2108095 | BMOU4899468 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-08-15 | 2021-09-27 |  |  | 2021-09-09 | 2021-09-27 | 0 | 2021-10-01 | 2021-10-01 | 4 | 2021-10-01 | 0 | DELIVERED | CLOSED IN CELLO 10/04 PIONEERNB18 (JERSEY AVE)
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | HASU4458425 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | MRKU3352842 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-11 | 4 | DELIVERED | CLOSED IN CELLO 10/12 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | MRKU5313676 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | MRSU4636194 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | MSKU0218050 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-08 | 7 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/12 (PNCW18) DUKE PROJECT; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND LACK OF CHASSIS
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | MSKU1496945 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-08 | 7 | 2021-10-13 | 5 | DELIVERED | CLOSED IN CELLO 10/13 (PNCW18) DUKE PROJECT; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND LACK OF CHASSIS
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | SUDU6682041 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | SUDU8558805 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | TCNU8698906 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (PNCW18) DUKE PROJECT
NORFOLK, VA | 72100055 | MARGRETHE MAERSK --> NORTHERN PRECISION | SUDUN1SOL0173841 | HW2108026 | TRHU7745041 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-01 |  | 2021-10-12 | 2021-09-23 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-08 | 7 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/12 (PNCW18) DUKE PROJECT; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND LACK OF CHASSIS
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | BEAU4156909 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-05 | 2 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | BMOU6139274 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-05 | 2 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | CAIU8181170 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-05 | 2 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | CMAU4786736 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSE IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | CMAU5019889 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-06 | 3 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | CMAU7450447 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-06 | 3 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | DRYU9686872 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-06 | 3 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | FSCU9973760 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | TCNU5372156 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783423 | SDSMY20210826-02 | TEMU6460502 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310009050 | SDSMY20210826-04 | BMOU4581008 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-07 | 2021-10-05 | 1 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310009050 | SDSMY20210826-04 | CSNU7541964 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-07 | 2021-10-05 | 1 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310009050 | SDSMY20210826-04 | CSLU6252980 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-07 | 2021-10-05 | 1 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/07 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310008970 | SDSMY20210826-03 | BEAU6064930 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-07 | 2021-10-06 | 2 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310008970 | SDSMY20210826-03 | CAIU4792628 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-08 | 2021-10-08 | 4 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101011 | CMA CGM J. MADISON | COSU6310008970 | SDSMY20210826-03 | CSNU7828527 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-27 | 2021-10-04 | 2 | 2021-10-07 | 2021-10-06 | 2 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | APHU6240936 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | APHU7014722 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/13 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | CAIU9310436 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | CMAU4506542 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | CMAU5962906 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/13 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | CMAU7932773 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | TCLU5205779 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSEd IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | TCNU8136072 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/11 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | TGHU6603837 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/12 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM J. MADISON | CMDUAYN0783415 | SDSMY20210826-01 | TTNU9022668 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-09-04 | 2021-10-02 |  | 2021-10-13 | 2021-09-24 | 2021-10-03 | 1 | 2021-10-07 | 2021-10-07 | 4 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/13 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | APHU6359340 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | APHU6622728 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | CMAU5248191 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-19 | 5 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | CMAU5958547 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | GESU5671897 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | SEGU6303908 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | TCKU9944091 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | TCLU4971297 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | TCNU9799043 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803889 | SDSMY20210911-03 | TEMU7431411 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803892 | SDSMY20210911-02 | TGCU0068340 | Q.PEAK DUO L-G8.2 435 | 12005802F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-12 | 2 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/14 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | CMDUAYN0803892 | SDSMY20210911-02 | TCNU9584240 | Q.PEAK DUO L-G8.2 435 | 12005802F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-29 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-12 | 2 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/14 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | COSU6311751600 | SDSMY20210911-01 | BMOU5048056 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-30 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-13 | 3 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | COSU6311751600 | SDSMY20210911-01 | OOLU9779671 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-30 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-13 | 3 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM MARCO POLO | COSU6311751600 | SDSMY20210911-01 | TCNU1204555 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-15 | 2021-10-09 |  | 2021-10-20 | 2021-09-30 | 2021-10-10 | 1 | 2021-10-14 | 2021-10-14 | 4 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | HMMU6482419 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | KOCU4127221 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | KOCU4304116 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | KOCU4556252 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-22 | 3 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | KOCU4696423 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-15 | 2021-10-15 | 3 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100050 | ROME EXPRESS | HDMUSELM98690700 | PTIK21S09182 | KOCU4707338 | Q.PEAK DUO BLK-G6C+/TS 340 | 30376509F | 18 | 676 | 26 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | CAIU7457650 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | DFSU6192563 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | GCXU5034855 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | HMMU6108230 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-15 | 3 | 2021-10-16 | 1 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | KOCU4439153 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-15 | 3 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/22 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | KOCU4545047 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-19 | 1 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
GTG | 72100062 | ROME EXPRESS | HDMUSELM98690702 | PTIK21S09184 | TCNU7401422 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-30 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/26 GTGBA18
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM21874500 | PTIK21S09181 | CAIU7296405 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM21874500 | PTIK21S09181 | GCXU5012769 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-25 | 7 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM21874500 | PTIK21S09181 | KOCU4411500 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-25 | 7 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM21874500 | PTIK21S09181 | TCKU6115292 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-13 | 3 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM21874500 | PTIK21S09181 | TCNU1697934 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-25 | 7 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100051 | ROME EXPRESS | HDMUSELM98690701 | PTIK21S09183 | TCNU9448922 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100051 | ROME EXPRESS | HDMUSELM98690701 | PTIK21S09183 | KOCU5033066 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-15 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM53403301 | SHTCS2109058 | KOCU4258880 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-15 | 3 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | ROME EXPRESS | HDMUSELM53403301 | SHTCS2109058 | KOCU4594735 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-07 | 2021-10-10 |  | 2021-10-21 | 2021-09-29 | 2021-10-12 | 2 | 2021-10-18 | 2021-10-15 | 3 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | EVER FAST | EGLV040100365034 | SHTCS2108186 | HMCU9151163 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100047 | EVER FAST | EGLV040100401871 | SHTCS2108159 | BMOU4571186 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-15 | 2 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100047 | EVER FAST | EGLV040100401871 | SHTCS2108159 | DRYU9427172 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-22 | 3 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100047 | EVER FAST | EGLV040100401871 | SHTCS2108159 | IMTU9066134 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-20 | 7 | 2021-10-25 | 5 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100047 | EVER FAST | EGLV040100401871 | SHTCS2108159 | TCNU6178490 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-20 | 7 | 2021-10-26 | 6 | DELIVERED | CLOSED IN CELLO 10/27 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100047 | EVER FAST | EGLV040100401871 | SHTCS2108159 | WFHU5191188 | Q.PEAK DUO BLK ML-G9P+.0.1 380 | 30368517F | 18 | 768 | 24 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-20 | 1 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100057 | EVER FAST | EGLV040100364992 | SHTCS2108123 | EGHU8246842 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-05 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | BEAU5811250 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | EISU9197776 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | EISU9444984 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | EMCU8278377 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | FCIU7255702 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | HMCU9164704 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | SEGU5902054 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | TGBU6776949 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | TLLU4139500 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100434176 | PTIK21S08177 | TRHU6992520 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | BEAU5080921 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-22 | 3 | DELIVERED | CLOSED IN CELLO 10/26 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | BMOU5436431 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-15 | 2 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | DRYU9279080 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | DRYU9551917 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EGHU9408378 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EGHU9744639 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-15 | 2 | 2021-10-15 | 0 | DELIVERED | CLOSED IN CELLO 10/18 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EITU1895183 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EITU9032403 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EITU9291111 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | EITU9294487 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | FBLU0202621 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | GAOU6261445 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | HMCU9145915 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-20 | 2021-10-20 | 7 | 2021-10-21 | 1 | DELIVERED | CLOSED IN CELLO 10/22 (CONTAINER IS LOST AT PORT ON 10/19 DRY-RUN CHARGE WILL APPLY) PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | HMCU9207196 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-21 | 3 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | SEGU5989429 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | TCLU7962874 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | TCNU2408743 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | TCNU4517960 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | TGBU4274319 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-19 | 2021-10-19 | 6 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER FAST | EGLV040100434192 | PTIK21S08178 | TGBU6737074 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/15 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100062 | EVER FAST | EGLV040100456668 | PTIK21S09187 | DRYU9424240 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100456668 | PTIK21S09187 | EITU1783368 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-16 | 3 | 2021-10-21 | 5 | DELIVERED | CLOSED IN CELLO 10/22 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100456668 | PTIK21S09187 | TCNU2130328 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100062 | EVER FAST | EGLV040100456668 | PTIK21S09187 | TCNU3750452 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-08-29 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-13 | 2 | 2021-10-18 | 2021-10-18 | 5 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/19 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | APL CHONGQING | EGLV040100365000 | SHTCS2108140 | TEMU6368546 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-09-08 | 2021-10-20 |  | 2021-10-31 | 2021-10-11 | 2021-10-21 | 1 | 2021-10-27 | 2021-10-27 | 6 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | APL CHONGQING | EGLV040100365000 | SHTCS2108140 | BMOU5373225 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-09-08 | 2021-10-20 |  | 2021-10-31 | 2021-10-11 | 2021-10-21 | 1 | 2021-10-27 | 2021-10-27 | 6 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100057 | ANTWERPEN EXPRESS | HDMUSELM39809600 | HW2109038 | CAIU7399682 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-16 | 2021-10-18 |  | 2021-10-29 | 2021-10-11 | 2021-10-19 | 1 | 2021-10-25 | 2021-10-26 | 7 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1) - Duke Charlie Creek ONLY
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | APHU6638513 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-25 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-26 | 4 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | APHU6684740 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-27 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-26 | 4 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | BMOU5486345 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-25 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-27 | 2021-10-22 | 0 | 2021-10-25 | 3 | DELIVERED | CLOSED IN CELLO 10/29 (Plus 10 Boxes and 10 Lids in container ) PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | CAIU8279491 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-25 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-25 | 3 | 2021-10-25 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | CAIU8512900 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-25 | 2021-10-14 | 2021-10-21 | 0 | 2021-10-27 | 2021-10-25 | 4 | 2021-10-25 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | CMAU4530370 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-27 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-25 | 3 | 2021-10-25 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | CMAU4737557 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-26 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-26 | 4 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | CMAU6513751 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-27 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-26 | 4 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | ECMU9483885 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-26 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-27 | 5 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101020 | CMA CGM CHILE | CMDUAYN0806483 | SDSMY20210918-01 | TGHU9530924 | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 660 | 22 | 2021-09-22 | 2021-10-21 |  | 2021-10-26 | 2021-10-14 | 2021-10-22 | 1 | 2021-10-28 | 2021-10-27 | 5 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 PIONEERNBNEW18 (RT. 1)
PIONEER | 72101021 | CMA CGM PEGASUS | CMDUAYN0816587 | SDSMY20211004-02 | CMAU7134217 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833F | 18 | 600 | 20 | 2021-10-04 | 2021-10-27 |  | 2021-11-07 | 2021-10-21 | 2021-10-27 | 0 | 2021-11-02 | 2021-11-01 | 5 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CMA CGM PEGASUS | CMDUAYN0816587 | SDSMY20211004-02 | DFSU6439458 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833F | 18 | 600 | 20 | 2021-10-04 | 2021-10-27 |  | 2021-11-07 | 2021-10-21 | 2021-10-28 | 1 | 2021-11-02 | 2021-10-29 | 1 | 2021-10-29 | 0 | DELIVERED | CLOSED IN CELLO 11/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CMA CGM PEGASUS | CMDUAYN0816587 | SDSMY20211004-02 | FCIU8755765 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833F | 18 | 600 | 20 | 2021-10-04 | 2021-10-27 |  | 2021-11-07 | 2021-10-21 | 2021-10-28 | 1 | 2021-11-02 | 2021-11-01 | 4 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CMA CGM PEGASUS | CMDUAYN0816587 | SDSMY20211004-02 | TEMU6603901 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833F | 18 | 600 | 20 | 2021-10-04 | 2021-10-27 |  | 2021-11-07 | 2021-10-21 | 2021-10-27 | 0 | 2021-11-02 | 2021-10-29 | 2 | 2021-10-29 | 0 | DELIVERED | CLOSED IN CELLO 11/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CMA CGM PEGASUS | CMDUAYN0816587 | SDSMY20211004-02 | TRLU7336210 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833F | 18 | 600 | 20 | 2021-10-04 | 2021-10-27 |  | 2021-11-07 | 2021-10-21 | 2021-10-27 | 0 | 2021-11-02 | 2021-11-01 | 5 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100079 | CONTSHIP LEO | ZIMUSEL7089597 | HW2109063 | ZCSU8953483 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-01 | 2021-10-28 |  | 2021-11-08 | 2021-10-21 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 4 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/05 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | CMA CGM AMERIGO VES PUCCI | EGLV040100431002 | SHTCS2110016 | TLLU4718775 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-03 | 2021-10-29 |  | 2021-11-09 | 2021-10-18 | 2021-10-31 | 2 | 2021-11-04 | 2021-11-02 | 2 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72101020 | CMA CGM T. JEFFERSON | CMDUAYN0806601 | SDSMY20210929-03 | TCNU4629152 | Q.PEAK DUO L-G8.2 435 | 12005802F | 18 | 660 | 22 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-03 | 1 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101020 | CMA CGM T. JEFFERSON | CMDUAYN0806601 | SDSMY20210929-03 | TEMU7343603 | Q.PEAK DUO L-G8.2 435 | 12005802F | 18 | 660 | 22 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-03 | 1 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101020 | CMA CGM T. JEFFERSON | CMDUAYN0807335A | SDSMY20210929-01 | CMAU4928975 | Q.PEAK DUO L-G8.2 435 | 12005802F | 18 | 660 | 22 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM T. JEFFERSON | CMDUAYN0807335B | SDSMY20210929-02 | CMAU5849459 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-03 | 1 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM T. JEFFERSON | CMDUAYN0807335B | SDSMY20210929-02 | CMAU7325928 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-03 | 2 | 2021-11-08 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM T. JEFFERSON | CMDUAYN0807335B | SDSMY20210929-02 | TCNU2674430 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-04 | 2 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101018 | CMA CGM T. JEFFERSON | CMDUAYN0807335B | SDSMY20210929-02 | TEMU8581165 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559F | 18 | 600 | 20 | 2021-10-01 | 2021-11-01 |  | 2021-11-12 | 2021-10-21 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
NORFOLK, VA | 72100065 | VIRGO | SUDUN1SOL0180122 | HW2108037 | FFAU2351310 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-31 | 2021-10-29 |  | 2021-11-09 | 2021-10-25 | 2021-10-29 | 0 | 2021-11-04 | 2021-11-01 | 3 | 2021-11-04 | 3 | DELIVERED | CLOSED IN CELLO 11/16 (PNCW18) Duke Charlie Creek
NORFOLK, VA | 72100065 | VIRGO | SUDUN1SOL0180122 | HW2108037 | MSKU1369196 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-31 | 2021-10-29 |  | 2021-11-09 | 2021-10-25 | 2021-10-30 | 1 | 2021-11-04 | 2021-11-03 | 4 | 2021-11-08 | 5 | DELIVERED | CLOSED IN CELLO 11/09 (PNCW18) Duke Charlie Creek
NORFOLK, VA | 72100065 | VIRGO | SUDUN1SOL0180122 | HW2108037 | MSKU9899530 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-31 | 2021-10-29 |  | 2021-11-09 | 2021-10-25 | 2021-10-30 | 1 | 2021-11-04 | 2021-11-02 | 3 | 2021-11-04 | 2 | DELIVERED | CLOSED IN CELLO 11/16 (PNCW18) Duke Charlie Creek
NORFOLK, VA | 72100065 | VIRGO | SUDUN1SOL0180122 | HW2108037 | TCNU1457173 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-31 | 2021-10-29 |  | 2021-11-09 | 2021-10-25 | 2021-10-29 | 0 | 2021-11-04 | 2021-11-01 | 3 | 2021-11-04 | 3 | DELIVERED | CLOSED IN CELLO 11/16 (PNCW18) Duke Charlie Creek
NORFOLK, VA | 72100065 | VIRGO | SUDUN1SOL0180122 | HW2108037 | TRLU7548502 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-08-31 | 2021-10-29 |  | 2021-11-09 | 2021-10-25 | 2021-10-30 | 1 | 2021-11-04 | 2021-11-02 | 3 | 2021-11-04 | 2 | DELIVERED | CLOSED IN CELLO 11/16 (PNCW18) Duke Charlie Creek
PIONEER | 72100062 | ONE WREN | HDMUSELM74220400 | PTIK21S09192 | BMOU4635300 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-02 | 1 | 2021-11-04 | 2 | DELIVERED | CLOSED IN CELLO 11/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM74220400 | PTIK21S09192 | CAIU4354196 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM74220400 | PTIK21S09192 | GAOU6192391 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM74220400 | PTIK21S09192 | KOCU4291317 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM74220400 | PTIK21S09192 | KOCU4751670 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM47906201 | PTIK21S09193 | CAIU7220204 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM47906201 | PTIK21S09193 | CAIU7348155 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM47906201 | PTIK21S09193 | DFSU6247394 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM47906201 | PTIK21S09193 | HDMU6875676 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-11-01 | 1 | 2021-11-04 | 2021-11-04 | 3 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | ONE WREN | HDMUSELM47906201 | PTIK21S09193 | TGBU6488428 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-16 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-10-31 | 0 | 2021-11-04 | 2021-11-03 | 3 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | ONE WREN | HDMUSELM86615100 | HW2109046 | BMOU4593755 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-24 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-10-31 | 0 | 2021-11-04 | 2021-11-04 | 4 | 2021-11-05 | 1 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ONE WREN | HDMUSELM89856601 | SHTCS2109177 | KOCU4228968 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-01 | 2021-10-31 |  | 2021-11-11 | 2021-10-21 | 2021-10-31 | 0 | 2021-11-04 | 2021-11-04 | 4 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER LADEN | EGLV040100427064 | SHTCS2109169 | TGBU4014625 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-29 | 2021-11-03 |  | 2021-11-14 | 2021-10-21 | 2021-11-05 | 2 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100062 | EVER LADEN | EGLV040100430995 | SHTCS2109083 | DRYU9286388 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-29 | 2021-11-03 |  | 2021-11-14 | 2021-10-21 | 2021-11-05 | 2 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100062 | EVER LADEN | EGLV040100430995 | SHTCS2109083 | TLLU4131129 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-09-29 | 2021-11-03 |  | 2021-11-14 | 2021-10-21 | 2021-11-05 | 2 | 2021-11-11 | 2021-11-10 | 5 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | COSCO SHIPPING PEONY | OOLU2676625851 | HW2109051 | TGBU8761260 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-29 | 2021-11-05 |  | 2021-11-16 | 2021-11-03 | 2021-11-06 | 1 | 2021-11-11 | 2021-11-11 | 5 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNBNEW18 (RT.1) Duke Charlie Creek ONLY
PIONEER | 72100059 | EVER LEGION | EGLV040100426963 | SHTCS2109084 | EITU1161446 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-09-29 | 2021-11-08 |  | 2021-11-19 | 2021-10-29 | 2021-11-09 | 1 | 2021-11-15 | 2021-11-12 | 3 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/18 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | BMOU5553211 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | CMAU4730568 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | ECMU9408583 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-12 | 2 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | ECMU9806479 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-12 | 2 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | FCIU8593617 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | FCIU9382727 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-16 | 4 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/18 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | GLDU9950290 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-22 | 5 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | SEGU6372010 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-15 | 5 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | TCNU9740718 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1230642 | TWSC21100265 | TGBU5212775 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-15 | 5 | 2021-11-16 | 1 | DELIVERED | CLOSED IN CELLO 11/18 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1231456 | TWSC21100263 | CAIU9433364 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-12 | 2 | 2021-11-13 | 1 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1231456 | TWSC21100263 | CMAU6634814 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-18 | 1 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1231456 | TWSC21100263 | CMAU7093329 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-13 | 1 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1231456 | TWSC21100263 | TCNU7998616 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-13 | 3 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | CMA CGM MAGELLAN | CMDUSEL1231456 | TWSC21100263 | TGBU5069094 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-10 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-13 | 3 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | CMA CGM MAGELLAN | OOLU2681433050 | HW2110019 | FFAU2414363 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-11 | 2 | 2021-11-17 | 2021-11-13 | 2 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | CMA CGM MAGELLAN | OOLU2681433050 | HW2110019 | OOLU8810746 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-13 | 3 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | CMA CGM MAGELLAN | OOLU2681433050 | HW2110019 | UETU5397530 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-13 | 1 | 2021-11-13 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | CMA CGM MAGELLAN | EGLV040100451925 | SHTCS2110049 | BMOU5776025 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-13 | 2021-11-09 |  | 2021-11-19 | 2021-10-28 | 2021-11-12 | 3 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | CMA CGM MAGELLAN | EGLV040100451925 | SHTCS2110049 | TGBU9760205 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-13 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-12 | 2 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100062 | CMA CGM MAGELLAN | EGLV040100431134 | SHTCS2109188 | TCNU1665069 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-13 | 2021-11-09 |  | 2021-11-20 | 2021-10-28 | 2021-11-11 | 2 | 2021-11-17 | 2021-11-12 | 1 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/16 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100079 | GUNVOR MAERSK | ZIMUSEL7095202 | SHTCS2110093 | BSIU9769842 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-10 |  | 2021-11-21 | 2021-11-04 | 2021-11-11 | 1 | 2021-11-17 | 2021-11-17 | 6 | 2021-11-22 | 5 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100079 | GUNVOR MAERSK | ZIMUSEL7095202 | SHTCS2110093 | CAIU9226876 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-10 |  | 2021-11-21 | 2021-11-04 | 2021-11-11 | 1 | 2021-11-17 | 2021-11-17 | 6 | 2021-11-20 | 3 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100079 | GUNVOR MAERSK | ZIMUSEL7095202 | SHTCS2110093 | TGBU5756716 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-10 |  | 2021-11-21 | 2021-11-04 | 2021-11-11 | 1 | 2021-11-17 | 2021-11-17 | 6 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100079 | GUNVOR MAERSK | ZIMUSEL7095202 | SHTCS2110093 | ZCSU7376113 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-10 |  | 2021-11-21 | 2021-11-04 | 2021-11-11 | 1 | 2021-11-17 | 2021-11-17 | 6 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100079 | GUNVOR MAERSK | ZIMUSEL7095202 | SHTCS2110093 | ZCSU7765408 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-10 |  | 2021-11-21 | 2021-11-04 | 2021-11-11 | 1 | 2021-11-16 | 2021-11-16 | 5 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100068 | EVER LENIENT | EGLV040100429474 | SHTCS2109231 | EITU9227750 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-04 | 2021-11-11 |  | 2021-11-22 | 2021-11-04 | 2021-11-13 | 2 | 2021-11-18 | 2021-11-19 | 6 | 2021-11-19 | 0 | DEMURRAGE INCURRED DUE TO PORT CONGESTION AND DELAYS ON GETTING CHASSIS | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100068 | EVER LENIENT | EGLV040100429474 | SHTCS2109231 | HMCU9196316 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-04 | 2021-11-11 |  | 2021-11-22 | 2021-11-04 | 2021-11-11 | 0 | 2021-11-17 | 2021-11-16 | 5 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | EVER LENIENT | EGLV040100429474 | SHTCS2109231 | TCNU2175908 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 580 | 20 | 2021-10-04 | 2021-11-11 |  | 2021-11-22 | 2021-11-04 | 2021-11-11 | 0 | 2021-11-17 | 2021-11-16 | 5 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | EVER LENIENT | EGLV040100427056 | SHTCS2109168 | EGHU8330402 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-04 | 2021-11-11 |  | 2021-11-22 | 2021-11-04 | 2021-11-13 | 2 | 2021-11-18 | 2021-11-18 | 5 | 2021-11-22 | 4 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | BEAU5134036 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-16 | 4 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | BEAU5141890 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | GAOU6043649 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | TCNU4557155 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | TCNU8756387 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-16 | 4 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | ZCSU7095841 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | ZCSU8713190 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | ZCSU8714405 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | ZCSU8835032 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ALBERT MAERSK | ZIMUSEL7094053 | PTIK21S09216 | ZCSU8865398 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | BMOU4505076 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | BSIU9708997 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | CAAU5440634 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | CAIU4419105 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-22 | 5 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | CAIU8417414 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-19 | 7 | 2021-11-19 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND DELAYS ON GETTING CHASSIS | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | CRSU9032324 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | FSCU8097025 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | JXLU7848170 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | JXLU7853495 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | SEGU5194715 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-17 | 5 | 2021-11-22 | 5 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | SEGU5333451 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | TCNU6460591 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-24 | 2021-11-24 | 12 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | TGBU7210792 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | TLLU4458338 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | TRHU8481473 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | ZCSU7022399 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | ZCSU7546689 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-19 | 7 | 2021-11-19 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND DELAYS ON GETTING CHASSIS | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | ZCSU8508699 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | ZCSU8630789 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ALBERT MAERSK | ZIMUSEL7093369 | SHTCS2109224 | ZCSU8634824 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-12 |  | 2021-11-23 | 2021-11-03 | 2021-11-12 | 0 | 2021-11-18 | 2021-11-18 | 6 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100087 | COSCO SHIPPING LOTUS | EGLV040100508781 | PTIK21S10227 | EGHU9350527 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-23 | 6 | 2021-11-23 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND DELAYS ON GETTING CHASSIS | CLOSED IN CELLO 11/24, PIONEERNBNEW18 (RT. 1)
PIONEER | 72100087 | COSCO SHIPPING LOTUS | EGLV040100508781 | PTIK21S10227 | EITU1751680 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-16 | 3 | 2021-11-19 | 2021-11-18 | 2 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100087 | COSCO SHIPPING LOTUS | EGLV040100508781 | PTIK21S10227 | GAOU6277293 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | COSCO SHIPPING LOTUS | CMDUSEL1226189 | HW2110018 | BMOU6438758 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-16 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-20 | 3 | 2021-11-20 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | COSCO SHIPPING LOTUS | CMDUSEL1226189 | HW2110018 | CAAU6163895 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-16 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-16 | 3 | 2021-11-19 | 2021-11-17 | 1 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100085 | COSCO SHIPPING LOTUS | CMDUSEL1233156 | TWSC21100540 | CMAU4708414 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-16 | 3 | 2021-11-19 | 2021-11-19 | 3 | 2021-11-19 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | COSCO SHIPPING LOTUS | CMDUSEL1233156 | TWSC21100540 | APHU6500904 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-20 | 3 | 2021-11-22 | 2 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | COSCO SHIPPING LOTUS | CMDUSEL1233156 | TWSC21100540 | CMAU5544064 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100079 | COSCO SHIPPING LOTUS | EGLV040100431061 | SHTCS2110059 | EITU1856947 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | COSCO SHIPPING LOTUS | EGLV040100451933 | SHTCS2110082 | EISU9453271 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | COSCO SHIPPING LOTUS | EGLV040100451933 | SHTCS2110082 | DRYU9580900 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-17 | 2021-11-13 |  | 2021-11-24 | 2021-11-04 | 2021-11-17 | 4 | 2021-11-22 | 2021-11-23 | 6 | 2021-11-23 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND DELAYS ON GETTING CHASSIS | CLOSED IN CELLO 11/24, PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100079 | ESSEN EXPRESS | HDMUSELM81672301 | SHTCS2110072 | CAIU7474596 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-14 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-18 | 2021-11-17 | 2 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ESSEN EXPRESS | HDMUSELM44303801 | PTIK21S10220 | GAOU6193720 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | ESSEN EXPRESS | HDMUSELM44303801 | PTIK21S10220 | KOCU4094956 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/23 PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | CAIU4354344 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | CAIU7366518 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | CAIU7663645 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-16 | 3 | 2021-11-22 | 2021-11-17 | 1 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | HDMU6696304 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | HDMU6700338 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | HDMU6805750 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | HMMU6000944 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | HMMU6217159 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | KOCU4224900 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | KOCU4340324 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | KOCU4580346 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | KOCU4905293 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100062 | ESSEN EXPRESS | HDMUSELM44303800 | PTIK21S10219 | TCLU5342175 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/23 GTGBA18
GTG | 72100079 | ESSEN EXPRESS | HDMUPUSM43736700 | HW2110029 | BSIU9944483 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 435 | 15 | 2021-10-14 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/25 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100079 | ESSEN EXPRESS | HDMUPUSM43736700 | HW2110029 | CAIU7659497 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 435 | 15 | 2021-10-14 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/25 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100079 | ESSEN EXPRESS | HDMUPUSM43736700 | HW2110029 | BSIU9948555 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 435 | 15 | 2021-10-14 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/25 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100079 | ESSEN EXPRESS | HDMUPUSM43736700 | HW2110029 | GAOU6200584 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 435 | 15 | 2021-10-14 | 2021-11-13 |  | 2021-11-24 | 2021-11-01 | 2021-11-15 | 2 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/25 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100057 | HYUNDAI SPEED | HDMUSELM10445100 | PTIK21S10221 | BMOU4282877 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-21 | 2 | 2021-11-26 | 2021-11-22 | 1 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGBA18
GTG | 72100057 | HYUNDAI SPEED | HDMUSELM10445100 | PTIK21S10221 | GAOU6168203 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGBA18
GTG | 72100057 | HYUNDAI SPEED | HDMUSELM10445100 | PTIK21S10221 | HDMU6863891 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGBA18
GTG | 72100057 | HYUNDAI SPEED | HDMUSELM10445100 | PTIK21S10221 | KOCU4371536 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGBA18
GTG | 72100057 | HYUNDAI SPEED | HDMUSELM10445100 | PTIK21S10221 | KOCU4626679 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-10 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGBA18
GTG | 72100059 | HYUNDAI SPEED | HDMUSELM44544000 | PTIK21S10225 | GCXU5039543 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-21 | 2 | 2021-11-26 | 2021-11-22 | 1 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/07, GTGBA18
GTG | 72100059 | HYUNDAI SPEED | HDMUSELM44544000 | PTIK21S10225 | HDMU6567380 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-21 | 2 | 2021-11-26 | 2021-11-22 | 1 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/07, GTGBA18
GTG | 72100059 | HYUNDAI SPEED | HDMUSELM44544000 | PTIK21S10225 | KOCU4652683 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/07, GTGBA18
GTG | 72100059 | HYUNDAI SPEED | HDMUSELM44544000 | PTIK21S10225 | SEGU6015310 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/06 GTGBA18
GTG | 72100059 | HYUNDAI SPEED | HDMUSELM44544000 | PTIK21S10225 | TCNU1699011 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517F | 18 | 768 | 24 | 2021-10-13 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-20 | 1 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
PIONEER | 72100079 | YM WARRANTY | HDMUSELM02060801 | PTIK21S10218 | HMMU6175829 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-29 | 6 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 Duke Charlie Creek ONLY
GTG | 72100057 | YM WARRANTY | HDMUSELM02060800 | PTIK21S10217 | CAIU4355720 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100057 | YM WARRANTY | HDMUSELM02060800 | PTIK21S10217 | KOCU4032384 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100057 | YM WARRANTY | HDMUSELM02060800 | PTIK21S10217 | KOCU4272066 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100057 | YM WARRANTY | HDMUSELM02060800 | PTIK21S10217 | KOCU4724654 | Q.PEAK DUO L-G6C.2 425 | 30384561C | 15 | 638 | 22 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18 - Duke Charlie Creek ONLY
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | CAIU7138863 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | CAIU7398942 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | CAIU7483561 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | GAOU6201066 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | GAOU6231923 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HDMU6652610 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HDMU6799982 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HDMU6861749 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HMMU6019997 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HMMU6354300 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | HMMU6412941 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/07, GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | KOCU4120567 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | KOCU4442814 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | KOCU4511406 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100062 | YM WARRANTY | HDMUSELM31682000 | PTIK21S10197 | TLLU5817849 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-10-12 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | YM WARRANTY | HLCUSEL211005402 | HW2110044 | UACU5665583 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-18 | 2021-11-22 |  | 2021-12-03 | 2021-11-15 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | YM WARRANTY | HLCUSEL211005402 | HW2110044 | BEAU4161891 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-18 | 2021-11-22 |  | 2021-12-03 | 2021-11-15 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-26 | 3 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
PIONEER | 72100075 | YM WARRANTY | HDMUSELM99826501 | HW2110038 | HDMU6880780 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-18 | 2021-11-22 |  | 2021-12-03 | 2021-11-12 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | YM WARRANTY | HLCUSEL211005519 | HW2110064 | CAIU4505800 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-18 | 2021-11-22 |  | 2021-12-03 | 2021-11-15 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | BSIU9939785 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | DFSU6719757 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/10, GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | HDMU6694826 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | HMMU6112590 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU4058856 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU4388204 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU4547380 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU4845825 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU4874269 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM15538600 | SDSKNYC018 | KOCU5217438 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | CAIU7659239 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | CLKU5018387 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | HMMU6136566 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/04 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU4206296 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU4329304 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU4342477 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU4424317 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU5028434 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | KOCU5059060 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100059 | HYUNDAI ULSAN | HDMUSELM17182100 | SDSKNYC019 | TCNU8800047 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 608 | 19 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | BMOU4631731 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | BSIU9630970 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | CAIU7403801 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | HMMU6226607 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | KOCU4227447 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | KOCU4828319 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | KOCU5208565 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | TCKU6118630 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | TCNU4022981 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM23659100 | PTIK21S10231 | TCNU7641737 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | HDMU6842163 | Q.PEAK DUO L-G6C.2 425 | 30384561C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | KOCU4840124 | Q.PEAK DUO L-G6C.2 425 | 30384561C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | BMOU4130323 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | CAIU7224262 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | CAIU9973280 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | CLKU5002457 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | HMMU6405027 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | KOCU4076968 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | KOCU4209382 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM05690900 | SDSKNYC011 | KOCU4823847 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | BSIU9211059 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | DFSU6650331 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-27 | 4 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | HMMU6110089 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU4013872 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU4038654 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-27 | 4 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU4301441 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU4972795 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU5094056 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | KOCU5174207 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM52444500 | PTIK21S10232 | TEMU7280064 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | CAIU4455890 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | CAIU7349932 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | GAOU6357383 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | HMMU6094305 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | HMMU6182160 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-23 | 1 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | KOCU4098782 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | KOCU4140516 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | KOCU4361332 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-29 | 9 | 2021-11-29 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | KOCU4853651 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM32842200 | SDSKNYC010 | TCNU8516956 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | HYUNDAI ULSAN | HDMUSELM32716301 | SDSKNYC016 | HMMU6495123 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 448 | 14 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | HYUNDAI ULSAN | HDMUSELM32716301 | SDSKNYC016 | TRLU8186603 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 448 | 14 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | BSIU9941170 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | CAIU4356270 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | GAOU6292317 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | HDMU6857190 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | KOCU4036100 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | KOCU4415300 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | KOCU4433134 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | KOCU4742555 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-26 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | KOCU5036804 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM54477700 | SDSKNYC009 | TGBU6481526 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | BMOU5165772 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | CAIU7439553 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | CLKU5019505 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | DRYU9192294 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | GAOU6201512 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | HMMU6420850 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4130971 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4211986 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4631612 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4721207 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4854391 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-27 | 4 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4873236 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU4921463 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | KOCU5122923 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM86648200 | PTIK21S10226 | TGBU6231574 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-17 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-27 | 4 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | GAOU6371782 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | HMMU6389179 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | KOCU4590494 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | KOCU5051835 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | TCLU9765880 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | TCNU7400365 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | TGBU6470497 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100087 | HYUNDAI ULSAN | HDMUSELM32716300 | SDSKNYC017 | TLLU5822275 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/6 GTGBA18
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | CAIU7234300 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | CAIU8432260 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | DFSU6249041 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | HMMU6189972 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | HMMU6262013 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | KOCU4073260 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | KOCU4187956 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | KOCU4690554 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | KOCU4780935 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | KOCU4970914 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100068 | HYUNDAI ULSAN | HDMUSELM60114200 | PTIK21S10233 | TCNU7648198 | Q.PEAK DUO XL-G10BC.C 480 | 30397472C | 15 | 580 | 20 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | DFSU6720613 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | DRYU9207603 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | HDMU6759465 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | HMMU6015055 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | HMMU6365691 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | KOCU4268512 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | KOCU4651305 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | KOCU4823894 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | KOCU4869241 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM65158100 | SDSKNYC015 | TCLU5088780 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | BSIU9628612 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | CAIU7155916 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | CAIU7399044 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | HDMU6726369 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | HDMU6746724 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | HMMU6085068 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | HMMU6211994 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4085960 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4260701 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4277279 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4301101 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4444355 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4498222 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | KOCU4810768 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-27 | 4 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | HYUNDAI ULSAN | HDMUSELM86979900 | PTIK21S10234 | SEGU6014588 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | BMOU4284099 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | BSIU9630585 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | CAIU4449413 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | HMMU6122393 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | KOCU4021667 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | KOCU4039500 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | KOCU4372738 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | TCNU5454275 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | TEMU7521201 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM89712100 | SDSKNYC014 | TLLU8348771 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | BSIU9289078 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | BSIU9338300 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | CAIU9823064 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | DFSU6480359 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | GAOU6202571 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | HMMU6038493 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | KOCU4573500 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | KOCU4644060 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | KOCU4878808 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM64035200 | SDSKNYC013 | SEGU5696307 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | CAIU7140346 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | GAOU6197325 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | HMMU6105375 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | HMMU6230335 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4038973 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4092660 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-23 | 2 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4243746 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4486730 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4521209 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
GTG | 72100085 | HYUNDAI ULSAN | HDMUSELM71037000 | SDSKNYC012 | KOCU4764765 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 493 | 17 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-17 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 12/5 GTGBA18
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | HMMU6041542 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | HMMU6348570 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-29 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU4061124 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-23 | 1 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU4084644 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU4094133 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-29 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU4402072 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU4768499 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | KOCU5031968 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | TCNU6810616 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM29341600 | HW2110070 | TCNU9427215 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUPUSM87110900 | HW2110081 | KOCU4202449 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUPUSM87110900 | HW2110081 | KOCU4680880 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM89503100 | EGNYC2110016 | BSIU9624026 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM89503100 | EGNYC2110016 | KOCU4633636 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM89503100 | EGNYC2110016 | KOCU4326882 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852701 | EGNYC2110014 | BMOU4165588 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852701 | EGNYC2110014 | BSIU9463810 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-27 | 1 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852701 | EGNYC2110014 | HMMU6095425 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-27 | 3 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852701 | EGNYC2110014 | HMMU6286205 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852701 | EGNYC2110014 | SEGU6015687 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852700 | EGNYC2110013 | KOCU4055477 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-29 | 8 | 2021-11-29 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852700 | EGNYC2110013 | KOCU4184767 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-29 | 9 | 2021-11-29 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852700 | EGNYC2110013 | KOCU4505086 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-03 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-29 | 9 | 2021-12-01 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 12/5 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852700 | EGNYC2110013 | KOCU4530746 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-29 | 8 | 2021-11-29 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM78852700 | EGNYC2110013 | TCNU6353490 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-18 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-26 | 6 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101020 | APL SENTOSA | COSU6314233910 | SDSMY20211010-03 | CXDU2287729 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 23 | 2021-10-31 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/02 PIONEERNB18 (JERSEY AVE) 23 pallet IDs
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | APHU6430746 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | APHU6823390 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | APHU7354126 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-24 | 2 | 2021-12-01 | 2021-11-29 | 5 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | CMAU5175897 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-24 | 2 | 2021-12-01 | 2021-11-29 | 5 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | CMAU5190470 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-26 | 3 | 2021-11-27 | 1 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | CMAU5660830 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | FCIU8825728 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-24 | 2 | 2021-12-01 | 2021-12-01 | 7 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | SEGU4122120 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | SEGU4732930 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | TCNU3120495 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-24 | 2 | 2021-11-30 | 2021-11-30 | 6 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | TCNU7668213 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-27 | 4 | 2021-11-27 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | APL SENTOSA | CMDUAYN0818013 | SDSMY20211010-02 | TRLU5910269 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-16 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-24 | 2 | 2021-12-01 | 2021-11-27 | 3 | 2021-11-27 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | CAIU7247550 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | CAIU8759401 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-12-01 | 2 | DELIVERED | CLOSED IN CELLO 12/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | FFAU2195060 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MEDU4490510 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-12-02 | 2 | DELIVERED | CLOSED IN CELLO 12/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MEDU7923609 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MEDU8353060 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/22 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MEDU8548101 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-12-01 | 2 | DELIVERED | CLOSED IN CELLO 12/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MSDU7239002 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MSDU7399850 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MSMU6370945 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MSMU7361700 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | MSMU7789031 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | TCNU1790883 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-12-03 | 3 | DELIVERED | CLOSED IN CELLO 12/06 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | TEMU8188374 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-12-02 | 2 | DELIVERED | CLOSED IN CELLO 12/05 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334038 | MEDUP9334038 | TGHU6785177 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | CMA CGM ARGENTINA | CMDUSEL1232257 | HW2110046 | TEMU6864947 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-18 | 2021-11-18 |  | 2021-11-29 | 2021-11-08 | 2021-11-20 | 2 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | CMA CGM ARGENTINA | OOLU2681724000 | HW2110051 | TGBU4706454 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-18 | 2021-11-18 |  | 2021-11-29 | 2021-11-05 | 2021-11-22 | 4 | 2021-11-29 | 2021-11-24 | 2 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | CMA CGM ARGENTINA | EGLV040100427340 | SHTCS2110085 | TCNU3746299 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-16 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-22 | 4 | 2021-11-29 | 2021-11-24 | 2 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNBNEW18 (RT. 1)
PIONEER | 72100059 | CMA CGM ARGENTINA | EGLV040100487300 | SHTCS2110086 | EGSU9064471 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 768 | 24 | 2021-10-18 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-22 | 4 | 2021-11-29 | 2021-11-29 | 7 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 11/30 PIONEERNBNEW18 (RT. 1)
GTG | 72101023 | MOL MAESTRO | ONEYPKGB72041700 | SDSMY20211002-01 | BEAU5481098 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-02 | 2021-11-18 |  | 2021-11-29 | 2021-11-10 | 2021-11-19 | 1 | 2021-11-25 | 2021-11-22 | 3 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGSS18
GTG | 72101023 | MOL MAESTRO | ONEYPKGB72041700 | SDSMY20211002-01 | DRYU6010626 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-02 | 2021-11-18 |  | 2021-11-29 | 2021-11-10 | 2021-11-19 | 1 | 2021-11-25 | 2021-11-22 | 3 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGSS18
GTG | 72101023 | MOL MAESTRO | ONEYPKGB72041700 | SDSMY20211002-01 | NYKU5572965 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-02 | 2021-11-18 |  | 2021-11-29 | 2021-11-10 | 2021-11-19 | 1 | 2021-11-25 | 2021-11-22 | 3 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGSS18
GTG | 72101023 | MOL MAESTRO | ONEYPKGB72041700 | SDSMY20211002-01 | TEMU8864864 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-02 | 2021-11-18 |  | 2021-11-29 | 2021-11-10 | 2021-11-19 | 1 | 2021-11-25 | 2021-11-22 | 3 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/30 GTGSS18
GTG | 72101023 | MOL MAESTRO | ONEYPKGB72041700 | SDSMY20211002-01 | TRHU6639791 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-02 | 2021-11-18 |  | 2021-11-29 | 2021-11-10 | 2021-11-19 | 1 | 2021-11-25 | 2021-11-19 | 0 | 2021-11-19 | 0 | DELIVERED | CLOSED IN CELLO 12/09, GTGSS18
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM33869500 | PTIK21S10236 | BSIU9444636 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-24 | 4 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM33869500 | PTIK21S10236 | DFSU6752061 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM33869500 | PTIK21S10236 | HMMU6349915 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM33869500 | PTIK21S10236 | TGBU6349470 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-23 | 3 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM33869500 | PTIK21S10236 | TLLU5771692 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-26 | 2021-11-22 | 2 | 2021-11-23 | 1 | DELIVERED | CLOSED IN CELLO 11/25 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM94196000 | SHTCS2110159 | GAOU6358883 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-26 | 5 | 2021-11-26 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | HYUNDAI ULSAN | HDMUSELM94196000 | SHTCS2110159 | HDMU6786199 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-23 | 2021-11-20 |  | 2021-12-01 | 2021-11-12 | 2021-11-21 | 1 | 2021-11-26 | 2021-11-24 | 3 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | BEAU5850350 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-27 | 4 | 2021-11-27 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | BMOU4270773 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | BMOU6800738 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-27 | 4 | 2021-11-27 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | CAIU7603918 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | FCIU9076985 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | FFAU2914353 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | GLDU7670957 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | MEDU7330270 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | MEDU8511313 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | MEDU8688377 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | MEDU8798076 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-29 | 6 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | MSMU7609021 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-27 | 4 | 2021-11-27 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | TCLU4926596 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-29 | 2021-11-24 | 1 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | TCNU8913866 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CCNI ANGOL | MEDUP9334020 | MEDUP9334020 | TGBU7436521 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-05 | 2021-11-22 |  | 2021-12-03 | 2021-11-16 | 2021-11-23 | 1 | 2021-11-30 | 2021-11-30 | 7 | 2021-11-30 | 0 | DELIVERED | CLOSED IN CELLO 12/04 PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | EVER LOVELY | CMDUSEL1207266 | HW2110002 | SEKU4329873 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-04 | 2021-11-26 |  | 2021-12-02 | 2021-11-15 | 2021-11-26 | 0 | 2021-12-02 | 2021-12-02 | 6 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100057 | EVER LOVELY | CMDUSEL1207266 | HW2110002 | TEMU6935655 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-04 | 2021-11-26 |  | 2021-12-02 | 2021-11-15 | 2021-11-26 | 0 | 2021-12-02 | 2021-12-02 | 6 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE) Duke Charlie Creek ONLY
PIONEER | 72100075 | ONE APUS | HLCUSEL211016858 | HW2110065 | UETU5863900 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-10-24 | 2021-11-27 |  | 2021-12-02 | 2021-11-18 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
GTG | 72100075 | ONE APUS | HDMUSELM09434200 | PTIK21S10229 | CAIU4456686 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-17 | 2021-11-27 |  | 2021-12-02 | 2021-11-12 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-01 | 2 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | ONE APUS | HDMUSELM09434200 | PTIK21S10229 | HMMU6024289 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-17 | 2021-11-27 |  | 2021-12-02 | 2021-11-12 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-01 | 2 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | ONE APUS | HDMUSELM09434200 | PTIK21S10229 | HMMU6242716 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-17 | 2021-11-27 |  | 2021-12-02 | 2021-11-12 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | ONE APUS | HDMUSELM09434200 | PTIK21S10229 | HMMU6460636 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-17 | 2021-11-27 |  | 2021-12-02 | 2021-11-12 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
GTG | 72100075 | ONE APUS | HDMUSELM09434200 | PTIK21S10229 | KOCU4609394 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-17 | 2021-11-27 |  | 2021-12-02 | 2021-11-12 | 2021-11-29 | 2 | 2021-12-02 | 2021-12-02 | 3 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/9 GTGBA18
PIONEER | 72100059 | EVER FAITH | EGLV040100427226 | SHTCS2110054 | TEMU6406224 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 768 | 24 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-12-01 | 2 | 2021-12-06 | 2021-12-01 | 0 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100079 | EVER FAITH | EGLV040100427145 | SHTCS2110048 | EGHU8282897 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-11-30 | 1 | 2021-12-06 | 2021-12-01 | 1 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100079 | EVER FAITH | EGLV040100427145 | SHTCS2110048 | EMCU9822891 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-11-30 | 1 | 2021-12-06 | 2021-12-02 | 2 | 2021-12-02 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | EVER FAITH | EGLV040100431118 | SHTCS2110060 | EGHU8205817 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-12-01 | 2 | 2021-12-06 | 2021-12-01 | 0 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | EVER FAITH | EGLV040100431118 | SHTCS2110060 | EGHU9661787 | Q.PEAK DUO BLK-G6C+ 340 | 30376609C | 15 | 832 | 26 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-12-01 | 2 | 2021-12-06 | 2021-12-01 | 0 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | EVER FAITH | EGLV040100487334 | SHTCS2110101 | EGHU8252845 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 768 | 24 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-11-30 | 1 | 2021-12-06 | 2021-12-01 | 1 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | EVER FAITH | EGLV040100487334 | SHTCS2110101 | TGBU5118624 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 768 | 24 | 2021-10-21 | 2021-11-29 |  | 2021-12-06 | 2021-11-16 | 2021-11-30 | 1 | 2021-12-06 | 2021-12-01 | 1 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | BEAU4256976 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09. PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | BMOU6660322 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09. PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | CAAU5830653 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-06 | 4 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/09. PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | FCIU8604748 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-09 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-09 | 2021-12-09 | 7 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | FCIU9812005 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | FDCU0049232 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | FSCU6144576 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | INKU6551234 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-10 | 2 | DELIVERED | CLOSED IN CELLO 12/13, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MEDU7516218 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MEDU7843859 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2022-01-11 | 2021-11-24 | 2021-12-03 | 1 | 2022-01-11 | 2022-01-11 | 39 | 2022-01-13 | 2 | DELIVERED | CLOSED IN CELLO 1/20 (TOTAL 5 DAMAGED PALLETS, PUT ALL 20 PALLETS ON HOLD IN CELLO); 12/10-located cntr, LFD extended, TONU incurred; Damage container LFD extended; PIONEERNB15 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MEDU7992873 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MEDU8916815 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MEDU9379407 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-09 | 2021-11-24 | 2021-12-03 | 1 | 2021-12-09 | 2021-12-09 | 6 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MSDU7443079 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | MSMU6606795 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-09 | 2021-11-24 | 2021-12-03 | 1 | 2021-12-09 | 2021-12-09 | 6 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | TCNU2460799 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | TCNU3553155 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | TCNU8302131 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | TEMU8198290 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9350505 | PKG0030577 | TGHU8591904 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-15 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | BEAU5906865 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | BMOU6945921 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | CAAU5670977 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-03 | 1 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | CAIU7797990 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-06 | 4 | 2021-12-07 | 1 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | DRYU9398330 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-09 | 7 | 2021-12-13 | 4 | DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/14, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MAXU6277167 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-09 | 2021-11-24 | 2021-12-03 | 1 | 2021-12-09 | 2021-12-09 | 6 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MEDU4657254 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MEDU7033950 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MEDU9434361 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MSDU7636329 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MSMU7373065 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-08 | 6 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | MSMU8068805 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-14 | 2021-11-24 | 2021-12-03 | 1 | 2021-12-20 | 2021-12-20 | 17 | 2021-12-22 | 2 | DELIVERED | CLOSED IN CELLO ON 12/23; 12/10-located cntr, LFD extended, TONU incurred; 12/17-container has been repaired LFD exended again; PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | TCNU5459087 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | TEMU8203674 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-09 | 2021-11-24 | 2021-12-03 | 1 | 2021-12-09 | 2021-12-09 | 6 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/11, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101021 | CSAV TOCONAO | MEDUP9334988 | MEDUP9334988 | TGBU7198906 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-14 | 2021-12-02 |  | 2021-12-08 | 2021-11-24 | 2021-12-02 | 0 | 2021-12-08 | 2021-12-07 | 5 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | SHANGHAI EXPRESS | HLCUSEL2109AVAF7 | HW2110069 | TCKU6445890 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-24 | 2021-12-05 |  | 2021-12-13 | 2021-11-24 | 2021-12-07 | 2 | 2021-12-13 | 2021-12-08 | 1 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100085 | SHANGHAI EXPRESS | HLCUSEL2109AVAF7 | HW2110069 | FCIU7095008 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-24 | 2021-12-05 |  | 2021-12-13 | 2021-11-24 | 2021-12-07 | 2 | 2021-12-13 | 2021-12-08 | 1 | 2021-12-08 | 0 | DELIVERED | CLOSED IN CELLO 12/09, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100057 | COSCO SHIPPING SAKURA | EGLV040100431100 | SHTCS2110084 | EGHU9739020 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-31 | 2021-12-05 |  | 2021-12-14 | 2021-11-16 | 2021-12-09 | 4 | 2021-12-14 | 2021-12-10 | 1 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100059 | COSCO SHIPPING SAKURA | EGLV040100487318 | SHTCS2110227 | TCLU8532380 | Q.PEAK DUO BLK ML-G9C+ 380 | 30369517C | 15 | 768 | 24 | 2021-10-31 | 2021-12-05 |  | 2021-12-13 | 2021-11-16 | 2021-12-07 | 2 | 2021-12-13 | 2021-12-09 | 2 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/19, PIONEERNB18 (JERSEY AVE)
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | BMOU4142221 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | BSIU9630564 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | HMMU6073642 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | KOCU4388729 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | KOCU4659965 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | KOCU4687545 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-16 | 2 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | KOCU4929994 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | HDMUKULM57315300 | SDSMY20211018-01 | KOCU5112627 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-23 | 2021-12-08 |  | 2021-12-16 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB71829600 | SDSMY20211016-01 | FDCU0477776 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB71829600 | SDSMY20211016-01 | FFAU3652263 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB71829600 | SDSMY20211016-01 | GESU6503270 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB71829600 | SDSMY20211016-01 | NYKU4778458 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB71829600 | SDSMY20211016-01 | TCLU8927179 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-15 | 2021-11-23 | 2021-12-09 | 1 | 2021-12-15 | 2021-12-09 | 0 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB78848700 | SDSMY20211021-01 | NYKU0705710 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB78848700 | SDSMY20211021-01 | NYKU0734805 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB78848700 | SDSMY20211021-01 | NYKU0797803 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-17 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-17 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB78848700 | SDSMY20211021-01 | NYKU5262580 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101021 | HUMEN BRIDGE | ONEYPKGB78848700 | SDSMY20211021-01 | NYKU5273990 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101026 | HUMEN BRIDGE | ONEYPKGB78850700 | SDSMY20211026-01 | KKFU7815770 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101026 | HUMEN BRIDGE | ONEYPKGB78850700 | SDSMY20211026-01 | KKFU7895436 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-17 | 2021-11-23 | 2021-12-10 | 2 | 2021-12-17 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101026 | HUMEN BRIDGE | ONEYPKGB78850700 | SDSMY20211026-01 | KKFU7917561 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101026 | HUMEN BRIDGE | ONEYPKGB78850700 | SDSMY20211026-01 | TCNU5797490 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
GTG | 72101026 | HUMEN BRIDGE | ONEYPKGB78850700 | SDSMY20211026-01 | TLLU5442439 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-22 | 2021-12-08 |  | 2021-12-18 | 2021-11-23 | 2021-12-11 | 3 | 2021-12-18 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, GTGBA18
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | BMOU4796623 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-16 | 5 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | BMOU5310485 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | DRYU9552180 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-16 | 5 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | EITU1412834 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | EITU1754740 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-14 | 3 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | TCKU6534350 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 2 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | TCNU2402534 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-17 | 6 | 2021-12-17 | 0 | DELIVERED; DEMURRAGE INCURRED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | EGLV091130780000 | PLIMY4C01403 | TCNU3269719 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-13 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM A. LINCOLN | COSU6317259870 | SDSMY20211107-02 | SEKU4371791 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 2 | 2021-12-21 | 2021-12-18 | 6 | 2021-12-20 | 2 | DELIVERED | CLOSED IN CELLO 12/28 ; LFD EXTENDED DUE TO CONTAINER LOST SINCE 12/12; PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | APHU6803198 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-14 | 3 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | APHU7206469 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-14 | 3 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | BMOU6440884 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | CAIU9481697 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | CMAU4299466 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-14 | 3 | 2021-12-16 | 2 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | CMAU4326345 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | CMAU5597594 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-20 | 5 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | FBLU0097280 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | FCIU8737993 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | TGBU6326330 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | TGHU6349867 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818050 | SDSMY20211107-01 | TGHU6366000 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-16 | 2 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818018 | SDSMY20211020-02 | APHU6452215 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818018 | SDSMY20211020-02 | BMOU5667997 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818018 | SDSMY20211020-02 | CMAU5116214 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818018 | SDSMY20211020-02 | CMAU7577982 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0818018 | SDSMY20211020-02 | CMAU7947048 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | APHU6644049 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-16 | 1 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | APHU6658037 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-20 | 5 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | BMOU4491774 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-20 | 6 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | CLHU8942475 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | CLHU8972741 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | CMAU5075331 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | CMAU5263257 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | CMAU5649208 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | FCIU8534609 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | GESU5554139 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 0 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-21 | 6 | DELIVERED | CLOSED IN CELLO ON 12/23, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | GESU5677787 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-16 | 5 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101023 | CMA CGM A. LINCOLN | CMDUAYN0820182 | SDSMY20211020-01 | TCLU9626502 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-09 | 2021-12-10 |  | 2021-12-16 | 2021-12-02 | 2021-12-11 | 1 | 2021-12-16 | 2021-12-15 | 4 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, PIONEERNB18 (JERSEY AVE)
PIONEER | 72101020 | CMA CGM LAPEROUSE | COSU6313342690 | SDSMY20211003-03 | TGBU5015523 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 22 | 2021-10-14 | 2021-12-11 |  | 2021-12-21 | 2021-12-02 | 2021-12-15 | 4 | 2021-12-21 | 2021-12-21 | 6 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO ON 12/23, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | EVER FORE | EGLV040100487342 | SHTCS2111026 | EITU9373945 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-11-12 | 2021-12-13 |  | 2021-12-20 | 2021-12-10 | 2021-12-14 | 1 | 2021-12-20 | 2021-12-20 | 6 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | EVER FORE | EGLV040100487351 | SHTCS2111037 | EGHU8286974 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-11-07 | 2021-12-13 |  | 2021-12-20 | 2021-12-10 | 2021-12-14 | 1 | 2021-12-20 | 2021-12-20 | 6 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21, PIONEERNB18 (JERSEY AVE)
PIONEER | 72100075 | EVER FORE | EGLV040100487351 | SHTCS2111037 | EISU9196851 | Q.PEAK DUO BLK-G6C+.0.1 340 | 30376709C | 15 | 832 | 26 | 2021-11-07 | 2021-12-13 |  | 2021-12-20 | 2021-12-10 | 2021-12-14 | 1 | 2021-12-20 | 2021-12-20 | 6 | 2021-12-22 | 2 | DELIVERED | CLOSED IN CELLO ON 12/23, PIONEERNB18 (JERSEY AVE)
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | CAIU4344449 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | CAIU4892252 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | DRYU9181181 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-21 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-21 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | GAOU6184122 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | GAOU6346028 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | HMMU6259935 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-16 | 0 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | KOCU4647840 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | TCLU9905430 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | TCNU6385820 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM57363100 | SDSMY20211031-05 | TGBU6338428 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/28 GTGBA18
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | BSIU9209370 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | CAIU7257380 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | DFSU6652210 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/31 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | DFSU6955937 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/31 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | GAOU6204255 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | HDMU6702541 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | HDMU6789135 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | KOCU4123273 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | KOCU5188432 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-21 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-21 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM74320300 | SDSMY20211031-06 | TLLU5813437 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | BMOU5225830 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/31 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | CAIU7225485 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | DFSU7357647 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | HDMU6712299 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | HDMU6726570 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | HDMU6796089 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | KOCU4700272 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | TCNU5862282 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | TCNU7785230 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101023 | HYUNDAI FAITH | HDMUKULM85947700 | SDSMY20211031-03 | TGBU6228462 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | BHCU4995308 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | CAIU7295142 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | CAIU7385164 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | CAIU7456740 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | DRYU9183179 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | HDMU6741424 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | HMMU6050821 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-23 | 2021-12-06 | 2021-12-17 | 2 | 2021-12-23 | 2021-12-20 | 3 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | KOCU4267835 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-22 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | TCNU6368607 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-21 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-21 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101026 | HYUNDAI FAITH | HDMUKULM36736300 | SDSMY20211031-07 | TCNU7133607 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-15 |  | 2021-12-21 | 2021-12-06 | 2021-12-16 | 1 | 2021-12-21 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO 12/30 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | BEAU4388355 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | BMOU4802346 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EGHU9496342 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EGSU9023934 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EGSU9044557 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EISU9174600 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EITU1319439 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | EITU1422874 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | TCNU2405467 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, GTGBA15
GTG | 72101028 | CMA CGM PANAMA | EGLV091130862553 | PLIMY4C01429 | TGBU8629464 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-20 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO ON 01/10, GTGBA15
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | BMOU5142000 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 570 | 19 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | BMOU5142000 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 30 | 1 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEER PIONEERNB15 (Replacement pallet 150000000880977 for SSPHPKL8095024)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | IMTU9075814 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-21 | 3 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | TCLU4975862 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | EISU9836590 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | DRYU9553313 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | SEGU5988823 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | HMCU9116100 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | EITU1492737 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | EITU1003203 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | EGLV091130822993 | NEDFPKGBEB22233 | EISU9156653 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | COSU6317259780 | SDSMY20211115-02 | OOLU9322448 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-10 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | APHU6586791 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | BMOU5647711 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-29 | 6 | DELIVERED | CLOSE IN CELLO 12/31 PIONEERNB18
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | CMAU6592025 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | ECMU9889920 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | FCIU8867847 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | FSCU8368240 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | SEGU5049023 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | TCLU8738853 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | TCNU4462928 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | TCNU6135760 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM PANAMA | CMDUAYN0854154A | SDSMY20211115-06 | TGHU9602794 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | APHU6736361 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | APHU6854390 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-17 | 1 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | CMAU5040680 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-17 | 1 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | CMAU5730264 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | SEGU4007511 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-17 | 1 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | TCNU3157621 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | TEMU7863396 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-17 | 1 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | TRLU6656755 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-22 | 4 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | TRLU7099633 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | UETU5556709 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
PIONEER | 72101026 | CMA CGM PANAMA | CMDUAYN0852847 | SDSMY20211115-03 | WWWU9602051 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-23 | 2021-12-07 | 2021-12-18 | 2 | 2021-12-23 | 2021-12-23 | 5 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/28 PIONEERNB18 (JERSEY AVE)
GTG | 72101026 | ONE HOUSTON | ONEYPKGB82674600 | SDSMY20211109-01 | KKFU7817860 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-10 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-29 | 2021-12-29 | 9 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | ONEYPKGB82674600 | SDSMY20211109-01 | NYKU4196483 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-10 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | ONEYPKGB82674600 | SDSMY20211109-01 | NYKU5920130 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-10 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | ONEYPKGB82674600 | SDSMY20211109-01 | TCNU4413060 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-10 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | ONEYPKGB82674600 | SDSMY20211109-01 | TCNU6662397 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-10 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-30 | 8 | 2021-12-30 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | BMOU5173037 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO ON 1/10, GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | BSIU9266339 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | CAIU9879567 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | GCXU5033020 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-28 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HDMU6766206 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-30 | 8 | 2021-12-30 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO ON 1/10, GTGBA15 (WILL ADD IN JAN BILLING)
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HDMU6875130 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HMMU6074823 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-28 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HMMU6129021 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-28 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HMMU6194161 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-30 | 2 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | HMMU6288105 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | KOCU4798786 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | SEGU5846639 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-23 | 4 | 2021-12-29 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | SEGU6005930 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-28 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | SEGU6040057 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM07162600 | SDSMY20211031-08 | TLLU5847268 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | BSIU9950790 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-30 | 8 | 2021-12-30 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15 (WILL ADD IN JAN BILLING)
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | HMMU6276594 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-28 | 0 | DELIVERED | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | HMMU6343218 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | KOCU4049896 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-30 | 8 | 2021-12-30 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15 (WILL ADD IN JAN BILLING)
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | KOCU4190630 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | KOCU4192037 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | KOCU4547163 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | KOCU5095005 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | TCKU6103901 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM40257100 | SDSMY20211031-04 | TCNU5074125 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-10-30 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-28 | 8 | 2021-12-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 12/31 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | DFSU6233560 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | GAOU6232540 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | HDMU6784283 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | HDMU6867330 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | HDMU6888307 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | HMMU6181708 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-28 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | HMMU6289605 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-28 | 2021-12-28 | 6 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | TCLU5458720 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-20 | 1 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | TCNU5080745 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 1/5 GTGBA15
GTG | 72101026 | ONE HOUSTON | HDMUKULM05702800 | SDSMY20211031-02 | TCNU6131718 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-19 |  | 2021-12-30 | 2021-12-13 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-30 | 8 | 2021-12-30 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION AND SHORTAGE ON CHASSIS | CLOSE IN CELLO 1/5 GTGBA15 (WILL ADD IN JAN BILLING)
PIONEER | 72101020 | COSCO SHIPPING CAMELLIA | COSU6312770250 | SDSMY20210918-02 | OOCU8261660 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 22 | 2021-10-04 | 2021-12-19 |  | 2021-12-30 | 2021-12-16 | 2021-12-22 | 3 | 2021-12-29 | 2021-12-29 | 7 | 2021-12-29 | 0 | DELIVERED | CLOSE IN CELLO 12/31 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | BMOU4312288 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | BMOU4501574 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | BMOU4818300 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | FCIU8953903 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 570 | 19 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | FCIU8953903 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 30 | 1 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE) (NEED TO HOLD THIS PALLET 150000000880913 ITEM 12005833F)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | GAOU6047665 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2022-01-03 | 6 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | TCKU6008170 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2022-01-03 | 6 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095024 | SDSMY20211102-01 | TGBU7244703 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2021-12-29 | 1 | DELIVERED | CLOSE IN CELLO 12/31 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101023 | MAERSK KOWLOON | SSPHPKL8095751 | SDSMY20211102-03 | TCNU2303830 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-27 | 6 | 2021-12-27 | 0 | DELIVERED | CLOSE IN CELLO 1/5 .PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL8095750 | SDSMY20211102-02 | KSSU1001060 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSE IN CELLO 1/5 .PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL8095750 | SDSMY20211102-02 | TCNU8114371 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-27 | 6 | 2021-12-30 | 3 | DELIVERED | CLOSE IN CELLO 1/5 .PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL8095750 | SDSMY20211102-02 | CAIU4337809 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-28 | 7 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 12/30 PIONEERNB15 (JERSEY AVE)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL8095750 | SDSMY20211102-02 | TGBU5778058 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-27 | 7 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF PIONEERNB15 (JERSEY AVE)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL300020177 | SDSMY20211102-04 | CAIU8993805 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-27 | 6 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF PIONEERNB15 (JERSEY AVE)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL300020177 | SDSMY20211102-04 | TLLU4307239 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2022-01-03 | 2022-01-03 | 13 | 2022-01-03 | 0 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (TONU INCURRED DUE TO CONTAINER LOST AT TERMINAL 12/27)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL300020177 | SDSMY20211102-04 | BEAU5044971 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-21 | 1 | 2021-12-28 | 2021-12-23 | 2 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF PIONEERNB15 (JERSEY AVE)
PIONEER | 72101026 | MAERSK KOWLOON | SSPHPKL300020177 | SDSMY20211102-04 | TCNU8238747 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-03 | 2021-12-20 |  | 2021-12-31 | 2021-12-16 | 2021-12-20 | 0 | 2021-12-27 | 2021-12-23 | 3 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO 12/30 AGAIN DUE TO TARIFF PIONEERNB15 (JERSEY AVE)
GTG | 72101026 | HYUNDAI FORCE | ONEYPKGB82675700 | SDSMY20211115-01 | BEAU4622273 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-21 | 2021-12-22 |  | 2022-01-05 | 2021-12-16 | 2021-12-29 | 7 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72101026 | HYUNDAI FORCE | ONEYPKGB82675700 | SDSMY20211115-01 | FFAU1818329 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-21 | 2021-12-22 |  | 2022-01-05 | 2021-12-16 | 2021-12-29 | 7 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72101026 | HYUNDAI FORCE | ONEYPKGB82675700 | SDSMY20211115-01 | FFAU1823752 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-21 | 2021-12-22 |  | 2022-01-05 | 2021-12-16 | 2021-12-29 | 7 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72101026 | HYUNDAI FORCE | ONEYPKGB82675700 | SDSMY20211115-01 | SEKU4390446 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-21 | 2021-12-22 |  | 2022-01-04 | 2021-12-16 | 2021-12-28 | 6 | 2022-01-04 | 2022-01-04 | 7 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72101026 | HYUNDAI FORCE | ONEYPKGB82675700 | SDSMY20211115-01 | TCLU1559590 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-11-21 | 2021-12-22 |  | 2022-01-05 | 2021-12-16 | 2021-12-29 | 7 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
PIONEER | 72100094 | MAERSK YUKON | ZIMUSEL7101672 | HW2111080 | TEMU6798300 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-27 | 2021-12-27 |  | 2022-01-04 | 2021-12-16 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72100094 | MAERSK YUKON | ZIMUSEL7101672 | HW2111080 | BSIU9679841 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-27 | 2021-12-27 |  | 2022-01-03 | 2021-12-16 | 2021-12-27 | 0 | 2022-01-03 | 2021-12-30 | 3 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72100094 | MAERSK YUKON | ZIMUSEL7101672 | HW2111080 | ZCSU6738856 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-27 | 2021-12-27 |  | 2022-01-03 | 2021-12-16 | 2021-12-27 | 0 | 2022-01-03 | 2021-12-30 | 3 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 1/5 PIONEERNB15 (JERSEY AVE) (WILL ADD IN JAN BILLING)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | BMOU5283693 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | DRYU9239339 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | EGHU9122126 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-05 | 2021-12-21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-03 | 5 | 2022-01-03 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | EISU9437500 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-05 | 6 | 2022-01-05 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | EITU1383649 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-06 | 7 | 2022-01-06 | 0 | DELIVERED | CLOSED IN CELLO ON 01/11, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | EITU1917702 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | EITU9132125 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-05 | 6 | 2022-01-05 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | MAGU5375350 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-05 | 6 | 2022-01-05 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | TCNU3829747 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-05 | 2021-12-21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | EGLV091130823001 | NEDFPKGBEB22082 | TCNU3839719 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | CMDUAYN0852849 | SDSMY20211125-01 | CMAU5670036 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-29 | 2021-12-29 |  | 2022-01-05 | 2021-12-21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/11, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | CMDUAYN0852849 | SDSMY20211125-01 | APHU6969316 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-05 | 2021-12-21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-03 | 5 | 2022-01-03 | 0 | DELIVERED | CLOSED IN CELLO ON 01/11, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | CMDUAYN0852849 | SDSMY20211125-01 | TCNU4143751 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/11, PIONEERNB15 (JERSEY AVE)
PIONEER | 72101028 | CMA CGM ALEXANDER VON HUMBOLDT | CMDUAYN0852849 | SDSMY20211125-01 | ECMU9716713 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-24 | 2021-12-29 |  | 2022-01-06 | 2021-12-21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-04 | 5 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/11, PIONEERNB15 (JERSEY AVE)
GTG | 72100094 | ONE HAWK | HDMUSELM75996800 | PTIK21S11255 | CAIU7373651 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-30 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/11 GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM75996800 | PTIK21S11255 | HMMU6282004 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-30 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM75996800 | PTIK21S11255 | KOCU4122256 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-30 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM75996800 | PTIK21S11255 | TGBU5891064 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-30 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO 1/11 GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM75996800 | PTIK21S11255 | TGBU6358424 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-30 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | BMOU4137647 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | BMOU4150253 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | CAIU9828235 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-12 | 1 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | DRYU9188801 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HDMU6578087 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HDMU6754756 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HDMU6835800 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-12 | 6 | 2022-01-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION | CLOSED IN CELLO ON 01/13, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HDMU6892950 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HMMU6151405 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HMMU6169220 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HMMU6236333 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | HMMU6413212 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | KOCU4226760 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | TCNU6811891 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-11 | 5 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72100094 | ONE HAWK | HDMUSELM20594000 | PTIK21S11256 | TRLU6993205 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-29 | 2022-01-04 |  | 2022-01-11 | 2021-12-27 | 2022-01-06 | 2 | 2022-01-11 | 2022-01-10 | 4 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, GTGBA15
GTG | 72101028 | ONE HANGZHOU BAY | ONEYPKGB86677600 | SDSMY20211202-01 | FDCU0566087 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-03 | 2022-01-06 |  | 2022-01-17 | 2021-12-28 | 2022-01-11 | 5 | 2022-01-18 | 2022-01-18 | 7 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE HANGZHOU BAY | ONEYPKGB86677600 | SDSMY20211202-01 | NYKU5209712 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-03 | 2022-01-06 |  | 2022-01-17 | 2021-12-28 | 2022-01-11 | 5 | 2022-01-18 | 2022-01-18 | 7 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE HANGZHOU BAY | ONEYPKGB86677600 | SDSMY20211202-01 | TCLU9771157 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-03 | 2022-01-06 |  | 2022-01-17 | 2021-12-28 | 2022-01-12 | 6 | 2022-01-19 | 2022-01-18 | 6 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE HANGZHOU BAY | ONEYPKGB86677600 | SDSMY20211202-01 | TCNU5863381 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-03 | 2022-01-06 |  | 2022-01-17 | 2021-12-28 | 2022-01-12 | 6 | 2022-01-19 | 2022-01-18 | 6 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE HANGZHOU BAY | ONEYPKGB86677600 | SDSMY20211202-01 | TLLU4208128 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-03 | 2022-01-06 |  | 2022-01-17 | 2021-12-28 | 2022-01-11 | 5 | 2022-01-18 | 2022-01-18 | 7 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | BEAU4401694 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | EITU1180169 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | TEMU6117303 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | TGBU6617422 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | TRHU4462731 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | EGHU9123483 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-13 | 4 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 1/18 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | EISU9191607 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | EITU9064530 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | FCIU7045521 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-11 | 2 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | GAOU6407587 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905040 | PLIMY4C01512 | TCNU3832890 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | BMOU4775282 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-11 | 2 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | BMOU4780463 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | BMOU5281690 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | BMOU5434193 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | BMOU5475232 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-07 | 0 | 2022-01-13 | 2022-01-13 | 6 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EGHU9093028 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-11 | 2 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO ON 01/12, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EGHU9440024 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EGHU9651135 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EISU9275462 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EISU9458231 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EITU1076895 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EITU1120386 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EITU1500560 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-12 | 3 | 2022-01-17 | 5 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | EMCU9687596 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | FSCU7252929 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | TCLU4964718 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-17 | 5 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | TCLU4970855 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-13 | 4 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | TCNU2202813 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-13 | 4 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19; 1/31 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | TCNU3839920 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/19 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | EGLV091130905031 | PLIMY4C01507 | TEMU8681014 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-09 | 2022-01-07 |  | 2022-01-18 | 2021-12-23 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-12 | 4 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO ON 01/13, PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | CMDUAYN0877862 | SDSMY20211204-04 | CMAU6014310 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-10 | 1 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | CMDUAYN0877862 | SDSMY20211204-04 | TCNU2997134 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-14 | 5 | 2022-01-14 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO APM NOT ACCEPTING CMA EMPTY REROUTED TO MAHER TERMINAL WHICH IS VERY CONGESTED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | CMDUAYN0877862 | SDSMY20211204-04 | TGHU6924544 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-10 | 2 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101031 | CMA CGM JULES VERNE | CMDUAYN0877862 | SDSMY20211204-04 | SEGU4343537 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-10 | 1 | 2022-01-10 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | CMAU4147165 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | CMAU5104281 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-09 | 2 | 2022-01-13 | 2022-01-13 | 4 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | CMAU5439201 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | GESU6622979 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-14 | 6 | 2022-01-14 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO APM NOT ACCEPTING CMA EMPTY REROUTED TO MAHER TERMINAL WHICH IS VERY CONGESTED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | TCKU9095878 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-17 | 9 | 2022-01-17 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO APM NOT ACCEPTING CMA EMPTY REROUTED TO MAHER TERMINAL WHICH IS VERY CONGESTED; 1/14 APM EXTREME CONGESTION TODAY UNABLE TO COLLECT. | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | TCLU5352609 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-13 | 2022-01-13 | 5 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | TCNU9325194 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-08 | 1 | 2022-01-24 | 2022-01-22 | 14 | 2022-01-24 | 2 | DELIVERED ; DEMURRAGE INCURRED DUE TO APM NOT ACCEPTING CMA EMPTY REROUTED TO MAHER TERMINAL WHICH IS VERY CONGESTED; 1/14 APM EXTREME CONGESTION TODAY UNABLE TO COLLECT.; 1/17 APM holds as this container is in a closed area, due to equipment breakdown; 1/21 container located LFD updated to 1/24. | CLOSE IN CELLO 1/25 PIONEERNB15
PIONEER | 72101028 | CMA CGM JULES VERNE | CMDUAYN0877454 | SDSMY20211204-03 | TEMU6266210 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-12-04 | 2022-01-07 |  | 2022-01-18 | 2021-12-28 | 2022-01-07 | 0 | 2022-01-13 | 2022-01-14 | 7 | 2022-01-17 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO APM NOT ACCEPTING CMA EMPTY REROUTED TO MAHER TERMINAL WHICH IS VERY CONGESTED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101018 | COSCO DEVELOPME | COSU6312968640 | SDSMY20211004-01 | FSCU8454246 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559C | 15 | 600 | 20 | 2021-10-14 | 2022-01-07 |  | 2022-01-18 | 2022-01-04 | 2022-01-10 | 3 | 2022-01-14 | 2022-01-14 | 4 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 1/20 PIONEERNB15
PIONEER | 72101018 | COSCO DEVELOPME | COSU6312968640 | SDSMY20211004-01 | TEMU2791293 | Q.PEAK DUO XL G10.3/BFG 475 | 12005559C | 15 | 85 | 5 | 2021-10-14 | 2022-01-07 |  | 2022-01-18 | 2022-01-04 | 2022-01-10 | 3 | 2022-01-14 | 2022-01-14 | 4 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 01/20 PIONEERNB15 (20'GP CONTAINER) TOTAL 5 PALLET IDS
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | CAIU7401460 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-12 | 1 | 2022-01-18 | 2022-01-14 | 2 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO ON 01/21, GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | DFSU6665692 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-12 | 1 | 2022-01-18 | 2022-01-14 | 2 | 2022-01-18 | 4 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | GAOU6152830 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-13 | 2 | 2022-01-19 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | HDMU6730116 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-12 | 1 | 2022-01-18 | 2022-01-18 | 6 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | HMMU6115368 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-12 | 1 | 2022-01-18 | 2022-01-18 | 6 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | KOCU4647120 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-13 | 2 | 2022-01-19 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72100094 | HYUNDAI HONOUR | HDMUSELM80835000 | PTIK21S12263 | TCLU5150948 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-03 | 2022-01-11 |  | 2022-01-22 | 2021-12-30 | 2022-01-13 | 2 | 2022-01-19 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN 01/20 CELLO GTGBA15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | BEAU4782311 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-17 | 3 | 2022-01-17 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | CMAU4502399 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | CMAU4901887 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | CMAU5972519 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-19 | 5 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | FCIU8763462 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-18 | 4 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | GESU6820547 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TCLU1857552 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-20 | 7 | 2022-01-20 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF DRIVERS THIS WEEK (COVID) | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TCLU6506334 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-19 | 5 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TCNU8341009 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-18 | 4 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TCNU8685175 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TGHU6280117 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | CMDUAYN0877452 | SDSMY20211214-01 | TRLU7191586 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-03 | 2022-01-14 | 2 | 2022-01-20 | 2022-01-20 | 6 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
PIONEER | 72101034 | CMA CGM THALASSA | COSU6320540640 | SDSMY20211214-02 | TRHU4655833 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-04 | 2022-01-14 | 2 | 2022-01-19 | 2022-01-19 | 5 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21, PIONEERNB15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | HDMU6720000 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-17 | 1 | 2022-01-21 | 2022-01-18 | 1 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/26 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | HMMU6333930 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-18 | 2 | 2022-01-21 | 2022-01-18 | 0 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | HMMU6458351 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-18 | 2 | 2022-01-21 | 2022-01-18 | 0 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU4474621 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-17 | 1 | 2022-01-21 | 2022-01-18 | 1 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU4489880 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-17 | 1 | 2022-01-21 | 2022-01-18 | 1 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU4504367 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-18 | 2 | 2022-01-21 | 2022-01-18 | 0 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU4629528 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-18 | 2 | 2022-01-21 | 2022-01-18 | 0 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/19 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU4997129 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-18 | 2 | 2022-01-21 | 2022-01-19 | 1 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU5114548 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-17 | 1 | 2022-01-21 | 2022-01-21 | 4 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 1/26 GTGBA15
GTG | 72101028 | ONE STORK | HDMUKULM07290900 | PLIMY4C01471 | KOCU5217510 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833C | 15 | 600 | 20 | 2021-11-28 | 2022-01-16 |  | 2022-01-27 | 2021-12-30 | 2022-01-17 | 1 | 2022-01-21 | 2022-01-19 | 2 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, GTGBA15
PIONEER | 72100100 | CMA CGM AMERIGO VESPUCCI | OOLU2687266130 | HW2112042 | CCLU7973363 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-16 | 2022-01-19 |  | 2022-01-30 | 2022-01-04 | 2022-01-20 | 1 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/31 PIONEERNB15
PIONEER | 72100094 | CMA CGM AMERIGO VESPUCCI | EGLV040100540464 | HW2112025 | EITU1739452 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-16 | 2022-01-19 |  | 2022-01-30 | 2022-01-04 | 2022-01-21 | 2 | 2022-01-27 | 2022-01-26 | 5 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/31 PIONEERNB15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | BSIU9917533 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | BSIU9952133 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | CAIU9840919 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | HMMU6050708 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | HMMU6379186 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | HMMU6415236 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | HMMU6435232 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | KOCU4011062 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | KOCU4597267 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM46363800 | PTIK21S12281 | TCKU6110752 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | BMOU4154602 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | CAIU7472340 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | FSCU8506993 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | GCXU5027687 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | HMMU6223763 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | HMMU6374395 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | KOCU4006467 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | KOCU4603781 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | KOCU4859027 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM50323800 | PTIK21S12282 | TCNU7044346 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | CAIU9967009 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | DFSU6214981 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | FSCU8507644 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | HDMU6739089 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-25 | 1 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | HDMU6870864 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | KOCU4123442 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | KOCU4607215 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | KOCU4629718 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | SEGU5830252 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM06346100 | PTIK21S12276 | SEGU6013299 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | CAIU4439360 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | CAIU9901871 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | GAOU6231137 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | HDMU6701988 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | HDMU6852351 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | HMMU6033193 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | KOCU4390006 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | KOCU4529262 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | KOCU4546167 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-25 | 1 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM99184400 | PTIK21S12279 | KOCU4881247 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | CAIU7436744 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | HDMU6730923 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | HDMU6736243 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | HMMU6384958 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | KOCU4014138 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | KOCU4416857 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | KOCU4597800 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | KOCU5040804 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | TLLU5298759 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM75216800 | PTIK21S12277 | TRLU8146257 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | CAIU4444242 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | CAIU7517888 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/26 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | GAOU6232832 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/26 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | KOCU4253240 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | KOCU4388610 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | KOCU4691360 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | KOCU4922367 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/26 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | TCNU6057760 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | TCNU7315772 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM20486700 | PTIK21S12280 | TGBU5892184 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-10 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | BSIU9264017 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | CAIU7208317 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | CAIU7406014 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | HDMU6810227 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | KOCU4040728 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | KOCU4083674 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | KOCU4368912 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | KOCU5131313 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | KOCU5174629 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM62251100 | PTIK21S12278 | SEGU5703788 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | BSIU9208353 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | BSIU9951667 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | FCIU8000753 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | HMMU6155680 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | KOCU4234209 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | KOCU4387825 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | KOCU5027079 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-19 | 0 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | KOCU5139227 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | KOCU5182331 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM66831300 | PTIK21S12274 | TCNU1948140 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | BSIU9607184 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | CAIU7485857 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | CAIU9826145 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | GCXU5036230 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | HDMU6712914 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | HMMU6069642 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | KOCU4559360 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | KOCU4889211 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | SEGU6037243 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM53999800 | PTIK21S12272 | TGBU6338264 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | CAAU5031472 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | CAIU7130693 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 2/1, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | HMMU6173512 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | KOCU4633873 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | KOCU4674430 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | KOCU5001520 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | KOCU5127592 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/27 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | KOCU5154900 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | TCNU5067260 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM83350100 | PTIK21S12271 | TCNU8523976 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | CAIU9982852 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-25 | 1 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | HMMU6053097 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | HMMU6091409 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | HMMU6183763 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | HMMU6292609 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | KOCU4959242 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 01/25 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | KOCU5035027 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | KOCU5120216 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | TCNU6283916 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM81820100 | PTIK21S12275 | TCNU7408854 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-11 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-19 | 0 | 2022-01-21 | 2 | DELIVERED | CLOSE IN CELLO 1/31 GTGBA15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | DFSU6811101 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | GAOU6334346 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | HMMU6056178 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-27 | 3 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU4112237 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-19 | 0 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU4756800 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU4758757 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-26 | 6 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU4839191 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-31 | 6 | DELIVERED | CLOSE IN CELLO 2/2 PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU4911193 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | KOCU5208760 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM34808000 | PTIK21S12273 | TGBU6477763 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | GCXU5018155 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | HDMU6749390 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-24 | 5 | 2022-01-27 | 3 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | HMMU6199780 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-26 | 2 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | KOCU4136856 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | KOCU4167116 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | KOCU4303043 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | KOCU5043146 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | KOCU5067786 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100100 | HYUNDAI INTEGRAL | HDMUSELM46372400 | PTIK21S12289 | TCLU8794142 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | CAIU7348896 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-21 | 3 | 2022-01-26 | 2022-01-21 | 0 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | GAOU6182808 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | HMMU6069880 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-21 | 3 | 2022-01-26 | 2022-01-21 | 0 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | HMMU6406300 | Q.PEAK DUO L-G6C.2 425 | 30384561C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-21 | 3 | 2022-01-26 | 2022-01-24 | 3 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | KOCU4292191 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | KOCU4841769 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-21 | 3 | 2022-01-26 | 2022-01-21 | 0 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | KOCU5121470 | Q.PEAK DUO L-G6C.2 425 | 30384561C | 15 | 97 | 4 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15 (211108_J1_DLGG62_425A_701 (10 PCS))
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | KOCU5121470 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 20 | 1 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | SEGU6037829 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100095 | HYUNDAI INTEGRAL | HDMUSELM04555500 | PTIK21S12268 | TLLU5769484 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | BMOU5904928 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | CAIU9844494 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-19 | 0 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | HDMU6779836 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | KOCU4621466 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO 1/25 PIONEERNB15; 1/20 TONU due to staff in terminal went hom early per GCT they will extend LFD.
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | KOCU4624927 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-24 | 3 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | KOCU4820236 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | KOCU5008567 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | KOCU5062629 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM02820800 | PTIK21S12290 | TCNU5064723 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-25 | 1 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | DFSU6218143 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | DRYU9190141 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | HMMU6078644 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | HMMU6097449 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-26 | 1 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | KOCU4185465 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-24 | 4 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | KOCU4217074 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | KOCU4341146 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | KOCU4482062 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | SEGU5702734 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM39700100 | PTIK21S12291 | TCNU5705391 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | CAIU7665458 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | CAIU8845120 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | CAIU9880280 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | HMMU6159052 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | HMMU6225236 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-26 | 1 | DELIVERED | CLOSED IN CELLO ON 1/27, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | HMMU6490918 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | KOCU4176550 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | KOCU4223884 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-21 | 1 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | KOCU5002770 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100101 | HYUNDAI INTEGRAL | HDMUSELM27794700 | PTIK21S12292 | KOCU5184289 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU4383297 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU7200173 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU7200240 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU7406462 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU7458281 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | CAIU9821502 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-20 | 1 | 2022-01-20 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | HMMU6127585 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | HMMU6171079 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSE IN CELLO 1/26 PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | HMMU6441240 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM09840800 | PTIK21S12286 | TCNU7317604 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | CAIU7455430 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | CAIU7671126 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | CAIU9878262 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | HDMU6657611 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | HDMU6684052 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | KOCU4195150 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | KOCU4454440 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-27 | 3 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | KOCU4710007 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | KOCU5170808 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
PIONEER | 72100094 | HYUNDAI INTEGRAL | HDMUSELM08531900 | PTIK21S12287 | SEGU6024610 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/25, PIONEERNB15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | DFSU6244986 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF CHASSIS | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | DFSU7033756 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/27 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | GCXU5015156 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-28 | 8 | 2022-01-28 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF CHASSIS | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | HMMU6044916 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-28 | 8 | 2022-01-31 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF CHASSIS | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | KOCU4167899 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-25 | 6 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | KOCU4669135 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-21 | 2 | 2022-01-21 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | KOCU4758607 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-25 | 2022-01-24 | 5 | 2022-01-24 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | TCNU5084761 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-28 | 8 | 2022-01-28 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF CHASSIS | CLOSE IN CELLO 1/31 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | TGBU6157482 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-25 | 5 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM12544100 | PTIK21S12285 | TLLU5816610 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-28 | 8 | 2022-01-29 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO SHORTAGE OF CHASSIS | CLOSED IN CELLO 2/3 GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM02820802 | PTIK21S12288 | CAAU5048372 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-19 | 1 | 2022-01-24 | 2022-01-21 | 2 | 2022-01-26 | 5 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM02820802 | PTIK21S12288 | CAIU7220267 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 348 | 12 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-25 | 5 | 2022-01-26 | 1 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM02820802 | PTIK21S12288 | CAIU7220267 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 58 | 2 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-25 | 2022-01-25 | 5 | 2022-01-26 | 1 | DELIVERED | CLOSED IN CELLO ON 1/27, GTGBA15
GTG | 72100094 | HYUNDAI INTEGRAL | HDMUSELM02820802 | PTIK21S12288 | TCNU6899012 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-12-20 | 2022-01-18 |  | 2022-01-29 | 2022-01-13 | 2022-01-20 | 2 | 2022-01-26 | 2022-01-26 | 6 | 2022-01-26 | 0 | DELIVERED | CLOSE IN CELLO 1/27 GTGBA15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | APHU6769956 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-08 | 15 | 2022-02-08 | 0 | DELIVERED | CLOSED IN CELLO 02/10 PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | APHU7029466 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-28 | 2 | DELIVERED | CLOSED IN CELLO 1/31/22 PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | BEAU4113147 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | BMOU4300100 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-28 | 1 | DELIVERED | CLOSED IN CELLO 1/31/22 PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | CMAU4736680 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | CMAU4757580 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | CMAU4788066 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | CMAU4934392 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-09 | 16 | 2022-02-09 | 0 | DELIVERED | CLOSED IN CELLO ON 2/10, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | SEGU4266261 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | TCKU6327141 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | TCLU1511446 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | CMDUAYN0877456 | SDSMY20211222-01 | TCNU2828052 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-08 | 15 | 2022-02-08 | 0 | DELIVERED | CLOSED IN CELLO 02/10 PIONEERNB15
PIONEER | 72101034 | CMA CGM J. ADAMS | COSU6320540650 | SDSMY20211222-02 | TGBU4376497 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-22 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-23 | 0 | 2022-01-27 | 2022-01-27 | 4 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | EITU1432574 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-09 | 16 | 2022-02-09 | 0 | DELIVERED | CLOSED IN CELLO ON 2/10, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | EITU9183040 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-04 | 2022-02-04 | 11 | 2022-02-04 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | EGHU9725290 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-10 | 17 | 2022-02-10 | 0 | DELIVERED | CLOSED IN CELLO ON 2/11, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | TLLU5925843 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | BEAU4379733 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-10 | 17 | 2022-02-10 | 0 | DELIVERED | CLOSED IN CELLO ON 2/11, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | EITU1870890 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | EITU9019994 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-09 | 16 | 2022-02-09 | 0 | DELIVERED | CLOSED IN CELLO ON 2/10, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | DRYU9682835 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | DFSU6873211 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, PIONEERNB15
PIONEER | 72101032 | CMA CGM J. ADAMS | EGLV091130919954 | NEDFPKGBEB23456 | FCIU7074659 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-21 | 2022-01-23 |  | 2022-02-03 | 2022-01-18 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-31 | 4 | DELIVERED | CLOSE IN CELLO 2/2 PIONEERNB15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | BMOU4659894 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | BMOU5283672 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EGHU9519860 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-02 | 2022-02-01 | 8 | 2022-02-01 | 0 | DELIVERED | CLOSE IN CELLO 2/2 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EGHU9693341 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/8, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EISU9318266 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EITU1052358 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EITU1085990 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EITU1890392 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EITU9021456 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/8, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EMCU8435440 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | EMCU9772996 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | FCIU9541372 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | FFAU1118670 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | GAOU6416681 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | HMCU9130480 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | SEGU5880910 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | TCNU3117315 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-23 | 0 | 2022-01-27 | 2022-01-27 | 4 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | TCNU3814665 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-28 | 2022-01-28 | 4 | 2022-01-28 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | TEMU8880886 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962604 | PLIMY4C01573 | TGBU4457829 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TGBU5114803 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-25 | 1 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EGHU9272419 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-25 | 1 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TCNU3027649 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EISU9091402 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TEMU8403820 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-25 | 1 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TGBU6207500 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EISU9312360 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TGBU6534781 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/8, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TEMU8681591 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EITU1585547 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-02 | 2022-02-01 | 8 | 2022-02-01 | 0 | DELIVERED | CLOSE IN CELLO 2/2 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TEMU6251884 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-28 | 1 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EGHU9837599 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TGBU4296961 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | TXGU6086099 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-11 | 2022-02-11 | 18 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO ON 2/14, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | FFAU1592669 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EGHU9377425 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-27 | 3 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | DRYU9311855 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | BMOU5383028 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO 1/31/22 GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | EITU1368599 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-02-10 | 2022-02-07 | 14 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, GTGBA15
GTG | 72101032 | CMA CGM J. ADAMS | EGLV091130962612 | PLIMY4C01576 | BEAU4384257 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-13 | 2022-01-24 | 1 | 2022-01-27 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/28, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HDMU6696557 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HDMU6705010 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-27 | 4 | 2022-02-02 | 2022-02-01 | 5 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HDMU6726420 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HDMU6768390 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HMMU6086737 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-27 | 4 | 2022-02-02 | 2022-02-01 | 5 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | HMMU6140530 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | KOCU4131237 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | KOCU4658146 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-26 | 3 | 2022-02-01 | 2022-02-01 | 6 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
GTG | 72100101 | ANTWERPEN EXPRESS | HDMUSELM93026900 | PTIK21S12296 | KOCU5036701 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-28 | 2022-01-23 |  | 2022-02-03 | 2022-01-20 | 2022-01-28 | 5 | 2022-02-02 | 2022-02-01 | 4 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, GTGBA15
PIONEER | 72101032 | MOL CHARISMA | ONEYPKGB90679300 | SDSMY20211215-01 | CAIU4955469 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-15 | 2022-01-27 |  | 2022-02-07 | 2022-01-20 | 2022-02-01 | 5 | 2022-02-07 | 2022-02-04 | 3 | 2022-02-04 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, PIONEERNB15
PIONEER | 72101032 | MOL CHARISMA | ONEYPKGB90679300 | SDSMY20211215-01 | KKFU7941830 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-15 | 2022-01-27 |  | 2022-02-07 | 2022-01-20 | 2022-02-01 | 5 | 2022-02-07 | 2022-02-04 | 3 | 2022-02-07 | 3 | DELIVERED | CLOSED IN CELLO ON 2/8, PIONEERNB15
PIONEER | 72101032 | MOL CHARISMA | ONEYPKGB90679300 | SDSMY20211215-01 | NYKU5127403 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-15 | 2022-01-27 |  | 2022-02-07 | 2022-01-20 | 2022-01-31 | 4 | 2022-02-07 | 2022-02-08 | 8 | 2022-02-09 | 1 | DELIVERED | CLOSED IN CELLO ON 2/10, PIONEERNB15
PIONEER | 72101032 | MOL CHARISMA | ONEYPKGB90679300 | SDSMY20211215-01 | SEGU4333565 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-15 | 2022-01-27 |  | 2022-02-07 | 2022-01-20 | 2022-02-01 | 5 | 2022-02-07 | 2022-02-07 | 6 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/8, PIONEERNB15
PIONEER | 72101032 | MOL CHARISMA | ONEYPKGB90679300 | SDSMY20211215-01 | TCLU1652871 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-15 | 2022-01-27 |  | 2022-02-07 | 2022-01-20 | 2022-02-01 | 5 | 2022-02-07 | 2022-02-07 | 6 | 2022-02-07 | 0 | DELIVERED | CLOSED IN CELLO ON 2/8, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | CAIU7130477 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-01-30 | 2 | 2022-02-03 | 2022-02-01 | 2 | 2022-02-01 | 0 | DELIVERED | CLOSED IN CELLO ON 2/2, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | HMMU6018619 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-02-01 | 4 | 2022-02-04 | 2022-02-03 | 2 | 2022-02-03 | 0 | DELIVERED | CLOSED IN CELLO ON 2/4, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | HMMU6037727 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-02-01 | 4 | 2022-02-04 | 2022-02-02 | 1 | 2022-02-02 | 0 | DELIVERED | CLOSED IN CELLO ON 2/4, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | HMMU6330930 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-01-31 | 3 | 2022-02-04 | 2022-02-02 | 2 | 2022-02-02 | 0 | DELIVERED | CLOSED IN CELLO ON 2/4, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | KOCU4456654 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-02-01 | 4 | 2022-02-04 | 2022-02-03 | 2 | 2022-02-04 | 1 | DELIVERED | CLOSED IN CELLO ON 2/7, PIONEERNB15
PIONEER | 72101032 | ONE HELSINKI | HDMUKULM35973300 | PLIMY4C01553 | KOCU4545411 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832C | 15 | 600 | 20 | 2021-12-26 | 2022-01-28 |  | 2022-02-08 | 2022-01-25 | 2022-02-01 | 4 | 2022-02-04 | 2022-02-04 | 3 | 2022-02-04 | 0 | DELIVERED | CLOSED IN CELLO ON 2/7, PIONEERNB15
GTG | 72100100 | ROME EXPRESS | HDMUSELM70583900 | PTIK21S12298 | CAIU4481502 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
GTG | 72100100 | ROME EXPRESS | HDMUSELM70583900 | PTIK21S12298 | HDMU6712278 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-08 | 2 | 2022-02-14 | 2022-02-14 | 6 | 2022-02-14 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
GTG | 72100100 | ROME EXPRESS | HDMUSELM70583900 | PTIK21S12298 | HMMU6363981 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-07 | 1 | 2022-02-11 | 2022-02-11 | 4 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO 2/15, GTGBA0
GTG | 72100100 | ROME EXPRESS | HDMUSELM70583900 | PTIK21S12298 | KOCU4525570 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 2/15, GTGBA0
GTG | 72100100 | ROME EXPRESS | HDMUSELM70583900 | PTIK21S12298 | KOCU4414480 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-08 | 2 | 2022-02-14 | 2022-02-14 | 6 | 2022-02-15 | 1 | DELIVERED | CLOSED IN CELLO 2/15, GTGBA0
GTG | 72100101 | ROME EXPRESS | HDMUSELM61186800 | PTIK21S12299 | KOCU4082739 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 2/15, GTGBA0
GTG | 72100101 | ROME EXPRESS | HDMUSELM61186800 | PTIK21S12299 | KOCU4816730 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
GTG | 72100101 | ROME EXPRESS | HDMUSELM61186800 | PTIK21S12299 | KOCU4828237 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
GTG | 72100101 | ROME EXPRESS | HDMUSELM61186800 | PTIK21S12299 | KOCU5109259 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-09 | 3 | 2022-02-15 | 2022-02-15 | 6 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
GTG | 72100101 | ROME EXPRESS | HDMUSELM61186800 | PTIK21S12299 | TCNU8583907 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-02 | 2022-02-06 |  | 2022-02-17 | 2022-01-25 | 2022-02-07 | 1 | 2022-02-11 | 2022-02-11 | 4 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO 02/16, GTGBA0
PIONEER | 72100101 | COSCO SHIPPING LOTUS | EGLV040100597512 | SHTCS2112228 | EITU1361742 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-01 | 2022-02-07 |  | 2022-02-18 | 2022-01-20 | 2022-02-10 | 3 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-17 | 1 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100100 | EVER LENIENT | EGLV040100655075 | SHTCS2112158 | EISU9921480 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2021-12-22 | 2022-02-09 |  | 2022-02-20 | 2022-02-01 | 2022-02-09 | 0 | 2022-02-15 | 2022-02-11 | 2 | 2022-02-11 | 0 | DELIVERED | CLOSED IN CELLO 02/16, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108244 | HW2201044 | BMOU4003231 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-09 | 0 | 2022-02-15 | 2022-02-14 | 5 | 2022-02-14 | 0 | DELIVERED | CLOSED IN CELLO 02/16, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108244 | HW2201044 | TCNU7618927 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-15 | 5 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108244 | HW2201044 | FSCU8217558 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-11 | 2 | 2022-02-16 | 2022-02-16 | 5 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108244 | HW2201044 | TEMU6815747 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-09 | 0 | 2022-02-17 | 2022-02-16 | 7 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108247 | HW2201043 | ZCSU6688565 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108247 | HW2201043 | ZCSU7032545 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-11 | 2 | 2022-02-16 | 2022-02-16 | 5 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108247 | HW2201043 | ZCSU7746877 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-22 | 6 | DELIVERED | CLOSED IN CELLO 02/23 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108247 | HW2201043 | ZCSU7648510 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-15 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108247 | HW2201043 | ZCSU8649589 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-15 | 2022-02-18 | 8 | 2022-02-22 | 4 | DELIVERED; DEMURRAGE INCURRED DUE TO A LOT OF CONGESTION AT THE PORTS AND UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 02/23 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | BMOU4725023 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | RFCU5019494 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-17 | 1 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | TCNU4242646 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-15 | 2022-02-15 | 5 | 2022-02-17 | 2 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | TCNU8115526 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | TGHU6582966 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | ZCSU7322122 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSE IN CELLO 2/18, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | ZCSU8676901 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-15 | 2022-02-14 | 4 | 2022-02-14 | 0 | DELIVERED | CLOSED IN CELLO 02/16, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | ZCSU8678925 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-11 | 2 | 2022-02-16 | 2022-02-16 | 5 | 2022-02-17 | 1 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | ZCSU8760648 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-15 | 2022-02-15 | 5 | 2022-02-15 | 0 | DELIVERED | CLOSED IN CELLO 02/16, PIONEERNB
PIONEER | 72100100 | GUNVOR MAERSK | ZIMUSEL7108068 | HW2201049 | ZCSU7278380 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2022-01-16 | 2022-02-09 |  | 2022-02-20 | 2022-02-07 | 2022-02-10 | 1 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-18 | 2 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100101 | ONE WREN | HDMUSELM73492000 | PTIK21S12295 | BSIU9530924 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-17 | 1 | 2022-02-17 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100101 | ONE WREN | HDMUSELM73492000 | PTIK21S12295 | HDMU6671184 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-22 | 2022-02-17 | 1 | 2022-02-17 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100101 | ONE WREN | HDMUSELM73492000 | PTIK21S12295 | KOCU5199099 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-17 | 1 | 2022-02-17 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100101 | ONE WREN | HDMUSELM73492000 | PTIK21S12295 | TCNU7896466 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
PIONEER | 72100101 | ONE WREN | HDMUSELM73492000 | PTIK21S12295 | TEMU7536496 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 PIONEERNB
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | HMMU6384006 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | KOCU4703585 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-17 | 2 | 2022-02-23 | 2022-02-18 | 1 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | KOCU4908939 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-22 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | KOCU4959176 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | KOCU5147454 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-17 | 2 | 2022-02-23 | 2022-02-18 | 1 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
GTG | 72100101 | ONE WREN | HDMUSELM93026901 | PTIK21S12297 | TCNU5061426 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2022-01-06 | 2022-02-15 |  | 2022-02-26 | 2022-01-31 | 2022-02-16 | 1 | 2022-02-21 | 2022-02-18 | 2 | 2022-02-18 | 0 | DELIVERED | CLOSED IN CELLO 02/22 GTGBA0
PIONEER | 72100100 | COSCO FORTUNE | EGLV040100650405 | SHTCS2201067 | EGHU9617085 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-11 | 2022-02-18 |  | 2022-03-01 | 2022-02-11 | 2022-02-19 | 1 | 2022-02-24 | 2022-02-23 | 4 | 2022-02-23 | 0 | DELIVERED | CLOSED IN CELLO 02/24 PIONEERNB
PIONEER | 72100100 | WIDE INDIA | MAEU215741689 | PTIK22U01005 | MRSU4008990 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 447 | 16 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-02-25 | 2 | 2022-02-25 | 0 | DELIVERED | CLOSED IN CELLO 02/28 PIONEERNB / 220112_K1_GXLC13_475A_001 - 12 pcs
PIONEER | 72100118 | WIDE INDIA | MAEU215904607 | PTIK22U01003 | MRKU3032200 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-02-25 | 2 | 2022-02-25 | 0 | DELIVERED | CLOSED IN CELLO 02/28 PIONEERNB
PIONEER | 72100118 | WIDE INDIA | MAEU215904607 | PTIK22U01003 | TCNU5320701 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-02-25 | 2 | 2022-02-25 | 0 | DELIVERED | CLOSED IN CELLO 02/28 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | MRKU2641840 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | MRSU3438682 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | MSKU0458724 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | SUDU6658549 | Q.PEAK DUO XL-G10C.3/BFG 470 | 30397570 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TCNU6152731 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 475 | 17 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-24 | 1 | 2022-03-01 | 2022-03-01 | 5 | 2022-03-03 | 2 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB / 220111_K1_GXCY13_475A_703 -11 PCS
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TCNU6152731 | Q.PEAK DUO XL-G10C.3.1/BFG 485 | 30390373 | 0 | 29 | 1 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-24 | 1 | 2022-03-01 | 2022-03-01 | 5 | 2022-03-03 | 2 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TCNU6152731 | Q.PEAK DUO XL-G10C.3/BFG 470 | 30397570 | 0 | 29 | 1 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-24 | 1 | 2022-03-01 | 2022-03-01 | 5 | 2022-03-03 | 2 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TCNU6152731 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 17 | 1 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-24 | 1 | 2022-03-01 | 2022-03-01 | 5 | 2022-03-03 | 2 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TGBU9320398 | Q.PEAK DUO XL-G10C.3/BFG 470 | 30397570 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100128 | WIDE INDIA | MAEU215904860 | PTIK22U01004 | TRLU8234342 | Q.PEAK DUO XL-G10C.3/BFG 470 | 30397570 | 0 | 580 | 20 | 2022-01-19 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-23 | 0 | 2022-03-01 | 2022-03-01 | 6 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100100 | COSCO SHIPPING SAKURA | EGLV040100650413 | SHTCS2201120 | EITU1082352 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-22 | 2022-02-23 |  | 2022-03-06 | 2022-02-17 | 2022-02-26 | 3 | 2022-03-03 | 2022-03-01 | 3 | 2022-03-01 | 0 | DELIVERED | CLOSED IN CELLO 03/02 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | FCIU9078381 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-03 | 0 | DELIVERED | CLOSED IN CELLO 03/07; 03/14 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | HASU4613579 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-04 | 1 | DELIVERED | CLOSED IN CELLO 03/08 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | HASU4654618 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-03 | 0 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MRKU3996573 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-04 | 1 | DELIVERED | CLOSED IN CELLO 03/08 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MRKU5197067 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-03 | 0 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MRKU5570885 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-02 | 5 | 2022-03-03 | 1 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MSKU1436735 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-02 | 5 | 2022-03-03 | 1 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MSKU8202512 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-02 | 5 | 2022-03-03 | 1 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | MSKU8958259 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-03 | 0 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72100118 | GJERTRUD MAERSK | MAEU215741459 | PTIK22U01002 | SEKU4621463 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-25 | 2022-02-24 |  | 2022-03-07 | 2022-02-16 | 2022-02-25 | 1 | 2022-03-03 | 2022-03-03 | 6 | 2022-03-03 | 0 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | BMOU6757523 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | CAIU7736171 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | DFSU6187778 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | FBLU0052943 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | FSCU6151678 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | MEDU4494250 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | MSCU7723630 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | MSMU5062423 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | TCLU9884770 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542135 | MEDUP9542135 | TEMU6898551 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | BEAU4258583 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-07 | 4 | 2022-03-08 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | DFSU7575356 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-11 | 7 | 2022-03-11 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | DRYU9347400 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-11 | 7 | 2022-03-11 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | FCIU8500086 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-11 | 7 | 2022-03-11 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU4370475 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-11 | 7 | 2022-03-11 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU4696306 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-11 | 2 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU4806276 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-08 | 5 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU4809932 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-11 | 7 | 2022-03-11 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU7347226 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MEDU7976620 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-10 | 1 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MSCU5335087 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-14 | 5 | DELIVERED | CLOSED IN CELLO 03/16 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MSDU7080190 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-09 | 5 | 2022-03-10 | 1 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MSDU7982430 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-11 | 2 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MSMU7325679 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-08 | 5 | 2022-03-10 | 2 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | MSMU7355586 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | TCLU5861437 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-12 | 8 | 2022-03-21 | 9 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/22 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | TCLU7930985 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-12 | 8 | 2022-03-16 | 4 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION UNAVAILABLE APPOINTMENTS | CLOSED IN CELLO 03/18 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | TCLU9105422 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | TCNU7166920 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542184 | MEDUP9542184 | TGBU9881260 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-10 | 1 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | CAIU8807639 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-08 | 5 | 2022-03-08 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | CRXU9942964 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | FFAU3912484 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | MEDU7036055 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-09 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | MSDU7817219 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-08 | 5 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | MSMU7120895 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | MSMU8716322 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | SEGU6256658 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | TCNU3183615 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-09 | 6 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | TGBU5602388 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-03 | 0 | 2022-03-09 | 2022-03-08 | 5 | 2022-03-08 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | TLLU5167002 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72101032 | SEASPAN EMERALD | MEDUP9542200 | MEDUP9542200 | TRHU8393120 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-25 | 2022-03-03 |  | 2022-03-14 | 2022-02-16 | 2022-03-04 | 1 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-08 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72100100 | ESSEN EXPRESS | HDMUSELM93842900 | PTIK22U01001 | BSIU9211850 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-21 | 2022-03-02 |  | 2022-03-13 | 2022-02-17 | 2022-03-04 | 2 | 2022-03-10 | 2022-03-10 | 6 | 2022-03-10 | 0 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB
PIONEER | 72100100 | ESSEN EXPRESS | HDMUSELM93842900 | PTIK22U01001 | CAIU7311114 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-21 | 2022-03-02 |  | 2022-03-13 | 2022-02-17 | 2022-03-04 | 2 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72100100 | ESSEN EXPRESS | HDMUSELM93842900 | PTIK22U01001 | CAIU7344170 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-21 | 2022-03-02 |  | 2022-03-13 | 2022-02-17 | 2022-03-04 | 2 | 2022-03-10 | 2022-03-10 | 6 | 2022-03-10 | 0 | DELIVERED | CLOSED IN CELLO 03/14 PIONEERNB / container arrived with 2 damaged panels 211231_K1_GXLC13_480A_765 Panel IDs: 821121525807601601 & 821721525807601609
PIONEER | 72100100 | ESSEN EXPRESS | HDMUSELM93842900 | PTIK22U01001 | HDMU6899235 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-21 | 2022-03-02 |  | 2022-03-13 | 2022-02-17 | 2022-03-04 | 2 | 2022-03-10 | 2022-03-09 | 5 | 2022-03-09 | 0 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72100100 | ESSEN EXPRESS | HDMUSELM93842900 | PTIK22U01001 | KOCU5183786 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-21 | 2022-03-02 |  | 2022-03-13 | 2022-02-17 | 2022-03-04 | 2 | 2022-03-10 | 2022-03-08 | 4 | 2022-03-09 | 1 | DELIVERED | CLOSED IN CELLO 03/10 PIONEERNB
PIONEER | 72100100 | CMA CGM PEGASUS | EGLV040100650391 | SHTCS2201091 | TEMU6227851 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-01-16 | 2022-03-06 |  | 2022-03-17 | 2022-02-23 | 2022-03-06 | 0 | 2022-03-10 | 2022-03-08 | 2 | 2022-03-08 | 0 | DELIVERED | CLOSED IN CELLO 03/18 PIONEERNB
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | CAIU7658947 | Q.PEAK DUO XL-G10C.3/BFG 485 | 30397573 | 0 | 580 | 20 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-18 | 3 | 2022-03-23 | 2022-03-22 | 4 | 2022-03-22 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | KOCU4040121 | Q.PEAK DUO XL-G10C.3/BFG 485 | 30397573 | 0 | 157 | 6 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-16 | 1 | 2022-03-21 | 2022-03-18 | 2 | 2022-03-21 | 3 | DELIVERED | CLOSED IN CELLO 03/23 PIONEERNB / 220111_K1_GXLC13_485A_701 - 12 pcs
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | TGBU6362614 | Q.PEAK DUO XL-G10C.3/BFG 485 | 30397573 | 0 | 580 | 20 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-17 | 2 | 2022-03-23 | 2022-03-21 | 4 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/23 PIONEERNB
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | SEGU5006649 | Q.PEAK DUO XL-G10C.3.1/BFG 470 | 30390370 | 0 | 259 | 9 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-18 | 3 | 2022-03-23 | 2022-03-21 | 3 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB / 220111_K1_GXCY13_470A_701 - 27 pcs
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | SEGU5006649 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 295 | 11 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-18 | 3 | 2022-03-23 | 2022-03-21 | 3 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB / 211028_K1_GXCY13_480A_701 - 5 pcs
PIONEER | 72100128 | YM WARRANTY | HDMUSELM41620800 | PTIK22U01006 | SEGU5006649 | Q.PEAK DUO XL-G10C.3.1/BFG 485 | 30390373 | 0 | 6 | 1 | 2022-01-26 | 2022-03-15 |  | 2022-03-26 | 2022-03-04 | 2022-03-18 | 3 | 2022-03-23 | 2022-03-21 | 3 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | CAIU8328873 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-23 | 2022-03-22 | 7 | 2022-03-22 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | MRKU3212820 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-23 | 2022-03-22 | 7 | 2022-03-23 | 1 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | MRSU4260656 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-21 | 2022-03-21 | 6 | 2022-03-24 | 3 | DELIVERED | CLOSED IN CELLO 03/25 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | MSKU9719480 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-21 | 2022-03-21 | 6 | 2022-03-22 | 1 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | MSKU9913520 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-21 | 2022-03-21 | 6 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/23 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | TCKU6847544 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-23 | 2022-03-21 | 6 | 2022-03-21 | 0 | DELIVERED | CLOSED IN CELLO 03/23 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216202331 | GLVSKR0016265 | TLLU6847344 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-14 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-15 | 1 | 2022-03-23 | 2022-03-22 | 7 | 2022-03-22 | 0 | DELIVERED | CLOSED IN CELLO 03/24 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216335109 | GLVSKR0016288 | HASU4059322 | DUO BLK ML-G10BC.A+/TS 395 | 30390255H | 14.75 | 624 | 24 | 2022-02-13 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-14 | 0 | 2022-03-18 | 2022-03-18 | 4 | 2022-03-18 | 0 | DELIVERED | CLOSED IN CELLO 03/22 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216335109 | GLVSKR0016288 | MRSU4564520 | DUO BLK ML-G10BC.A+/TS 395 | 30390255H | 14.75 | 624 | 24 | 2022-02-13 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-14 | 0 | 2022-03-18 | 2022-03-18 | 4 | 2022-03-18 | 0 | DELIVERED | CLOSED IN CELLO 03/22 PIONEERNB1475
PIONEER | 72100123 | GUNHILDE MAERSK | MAEU216335109 | GLVSKR0016288 | MRSU3165989 | DUO BLK ML-G10BC.A+/TS 395 | 30390255H | 14.75 | 624 | 24 | 2022-02-13 | 2022-03-14 |  | 2022-03-25 | 2022-03-07 | 2022-03-14 | 0 | 2022-03-18 | 2022-03-18 | 4 | 2022-03-18 | 0 | DELIVERED | CLOSED IN CELLO 03/22 PIONEERNB1475
PIONEER | 72100100 | APL SOUTHAMPTON | EGLV040100650430 | SHTCS2201224 | EITU1191034 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572 | 0 | 580 | 20 | 2022-02-03 | 2022-03-26 |  | 2022-04-06 | 2022-03-17 | 2022-03-27 | 1 | 2022-03-31 | 2022-03-29 | 2 | 2022-03-29 | 0 | DELIVERED | CLOSED IN CELLO 03/30 PIONEERNB
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | BMOU4550202 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-06 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | BSIU9707244 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-07 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | CRSU9012781 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | DFSU6943371 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-08 | 8 | 2022-04-08 | 0 | DELIVERED/ DEMURRAGE INCURRED DUE TO PNCT TERMINAL CONGESTION | CLOSED IN CELLO 04/12 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | FSCU8166358 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | JXLU6637315 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-02 | 2 | 2022-04-04 | 2 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | JZPU8027449 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | KSSU1000649 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-07 | 7 | 2022-04-07 | 0 | DELIVERED/ DEMURRAGE INCURRED DUE TO PNCT TERMINAL CONGESTION | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TCNU6908726 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-07 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TEMU7537698 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-06 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TGBU5492547 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TGBU5768677 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TGHU6587016 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TLLU4780302 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-07 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | TLLU5221680 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-07 | 7 | 2022-04-07 | 0 | DELIVERED/ DEMURRAGE INCURRED DUE TO PNCT TERMINAL CONGESTION | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | UETU5937583 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-07 | 7 | 2022-04-07 | 0 | DELIVERED/ DEMURRAGE INCURRED DUE TO PNCT TERMINAL CONGESTION | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU6797503 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-07 | 1 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7041779 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7076780 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7168296 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7237226 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-01 | 1 | 2022-04-04 | 3 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7282251 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7359543 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-08 | 8 | 2022-04-08 | 0 | DELIVERED/ DEMURRAGE INCURRED DUE TO PNCT TERMINAL CONGESTION | CLOSED IN CELLO 04/12 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7372967 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7385856 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7608965 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-02 | 2 | 2022-04-04 | 2 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7771247 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU7915874 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-05 | 5 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU8495190 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | CORNELIA MAERSK | ZIMUSEL7112408 | ULSO22020381 | ZCSU8563058 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-19 | 2022-03-31 |  | 2022-04-11 | 2022-03-24 | 2022-03-31 | 0 | 2022-04-06 | 2022-04-06 | 6 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | BMOU5888827 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-06 | 4 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | DFSU6495282 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-04 | 2 | 2022-04-05 | 1 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | FSCU8217917 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-04 | 2 | 2022-04-04 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | JXLU6635159 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-04 | 2 | 2022-04-06 | 2 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | TDRU8301656 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-05 | 3 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | TGBU7123189 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-04 | 2 | 2022-04-04 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | ZCSU6768906 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-06 | 4 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | ZCSU7487251 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-05 | 3 | 2022-04-05 | 0 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | ZCSU7674822 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-06 | 4 | 2022-04-07 | 1 | DELIVERED | CLOSED IN CELLO 04/06 PIONEERNB1475
PIONEER | 72100142 | MSC MUM | ZIMUSEL7112411 | ULSO22020464 | ZCSU8663798 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-02-24 | 2022-04-01 |  | 2022-04-12 | 2022-03-24 | 2022-04-02 | 1 | 2022-04-07 | 2022-04-06 | 4 | 2022-04-06 | 0 | DELIVERED | CLOSED IN CELLO 04/08 PIONEERNB1475
PIONEER | 72101038 | HYUNDAI FORCE | ONEYPKGC09345800 | SDSMY20220218-02 | CXDU1305617 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-02-18 | 2022-04-08 |  | 2022-04-19 | 2022-03-17 | 2022-04-10 | 2 | 2022-04-16 |  |  |  |  | Vessel arrived/unloaded | PIONEERNB
PIONEER | 72101038 | HYUNDAI FORCE | ONEYPKGC09345800 | SDSMY20220218-02 | NYKU4443900 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-02-18 | 2022-04-08 |  | 2022-04-19 | 2022-03-17 | 2022-04-08 | 0 | 2022-04-15 |  |  |  |  | Vessel arrived/unloaded | PIONEERNB
PIONEER | 72101038 | HYUNDAI FORCE | ONEYPKGC09345800 | SDSMY20220218-02 | KKFU7761205 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-02-18 | 2022-04-08 |  | 2022-04-19 | 2022-03-17 | 2022-04-10 | 2 | 2022-04-17 |  |  |  |  | Vessel arrived/unloaded | PIONEERNB
PIONEER | 72101038 | CMA CGM T. JEFFERSON | EGLV091230135875 | 22SEPKG12838 | TGBU6951131 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-12 | 2022-04-12 |  | 2022-04-23 | 2022-04-05 | [7 empty] | Vessel arrived/not yet discharged | PIONEERNB
PIONEER | 72101038 | CMA CGM T. JEFFERSON | EGLV091230135883 | 22SEPKG12839 | TGBU6111136 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-15 | 2022-04-12 |  | 2022-04-23 | 2022-04-05 | [7 empty] | Vessel arrived/not yet discharged | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | GESU5712574 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | MSKU0321449 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | MSKU1687582 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | MSKU8508708 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | PONU7624787 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101037 | SC MONTREUX | MAEU216573162 | RSEWR2203016 | TEMU6969830 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-05 | 2022-04-13 |  | 2022-04-24 | 2022-03-28 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | BEAU5420699 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | FCIU8987251 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | FDCU0616001 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | GCXU5205747 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | MOTU6709277 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | TCLU5796732 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | TCLU8146828 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | TLLU5458749 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | TRHU4345817 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100100 | NEW YORK EXPRESS | ONEYSELC10388500 | PTIK22U02001 | TRHU5123537 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-02-10 | 2022-04-14 |  | 2022-04-25 | 2022-03-09 | [7 empty] | On Vessel | PIONEERNB1475
PIONEER | 72101038 | CONTI CONTESSA | ONEYPKGC09715900 | SDSMY20220224-02 | DRYU6020265 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-24 | 2022-04-15 |  | 2022-04-26 | 2022-04-05 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CONTI CONTESSA | ONEYPKGC09715900 | SDSMY20220224-02 | NYKU4194500 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-02-24 | 2022-04-15 |  | 2022-04-26 | 2022-04-05 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CMA CGM AMERIGO VESPUCCI | EGLV091230159537 | SEAE22030086 | OCGU8067023 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-15 | 2022-04-16 |  | 2022-04-27 | 2022-04-11 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CMA CGM AMERIGO VESPUCCI | EGLV091230159537 | SEAE22030086 | FFAU1115054 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-15 | 2022-04-16 |  | 2022-04-27 | 2022-04-11 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CMA CGM AMERIGO VESPUCCI | EGLV091230159537 | SEAE22030086 | CAAU5497748 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-15 | 2022-04-16 |  | 2022-04-27 | 2022-04-11 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CMA CGM AMERIGO VESPUCCI | EGLV091230159537 | SEAE22030086 | EISU9226088 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-15 | 2022-04-16 |  | 2022-04-27 | 2022-04-11 | [7 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | CMA CGM BRAZIL | EGLV091230135905 | 22SEPKG12837 | EITU9236881 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-24 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | CMA CGM BRAZIL | CMDUAYN0947412 | MYNYC2230290 | TCLU9593760 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-23 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | CMA CGM BRAZIL | CMDUAYN0947412 | MYNYC2230290 | CMAU7693811 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-23 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | CMA CGM BRAZIL | CMDUAYN0947412 | MYNYC2230290 | CMAU4210592 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-23 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | CMA CGM BRAZIL | CMDUAYN0947412 | MYNYC2230290 | CMAU6420710 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-23 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | CMA CGM BRAZIL | CMDUAYN0947412 | MYNYC2230290 | CMAU7078643 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-23 | 2022-04-24 |  | 2022-05-05 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | HYUNDAI FORWARD | HDMUSELM54201600 | PTIK22U03002 | HMMU6396970 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-03-24 | 2022-04-28 |  | 2022-05-09 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | HYUNDAI FORWARD | HDMUSELM54201600 | PTIK22U03002 | KOCU4325438 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-03-24 | 2022-04-28 |  | 2022-05-09 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | HYUNDAI FORWARD | HDMUSELM54201600 | PTIK22U03002 | KOCU4544077 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-03-24 | 2022-04-28 |  | 2022-05-09 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | HYUNDAI FORWARD | HDMUSELM54201600 | PTIK22U03002 | KOCU4724757 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-03-24 | 2022-04-28 |  | 2022-05-09 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | HYUNDAI FORWARD | HDMUSELM54201600 | PTIK22U03002 | KOCU5015376 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-03-24 | 2022-04-28 |  | 2022-05-09 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936834 | OERT111702L00788 | CMAU4330957 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936834 | OERT111702L00788 | TLLU5019751 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936834 | OERT111702L00788 | BMOU6981087 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936834 | OERT111702L00788 | CMAU6657830 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936834 | OERT111702L00788 | BEAU4850566 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936788 | OERT111702L00781 | BSIU8073042 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936788 | OERT111702L00781 | APHU6670840 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936788 | OERT111702L00781 | TLLU7926915 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936788 | OERT111702L00781 | TCNU4652445 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0936788 | OERT111702L00781 | FSCU7133405 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0951745 | OERT111702L00997 | ECMU9563255 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0951745 | OERT111702L00997 | APHU7209410 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0951745 | OERT111702L00997 | CMAU7194833 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0951745 | OERT111702L00997 | CMAU6384612 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | APL SENTOSA | CMDUAYN0951745 | OERT111702L00997 | TRHU5154287 | Q.PEAK DUO XL G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-04-06 | 2022-04-30 |  | 2022-05-11 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | GRETE MAERSK | ZIMUSEL7119142 | HWNWY2203001 | JXLU7498425 | Q.PEAK DUO XL-G11C.3/BFG_J 580W | 30391592 | 0 | 464 | 16 | 2022-04-02 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | GRETE MAERSK | ZIMUSEL7119142 | HWNWY2203001 | ZCSU7312464 | Q.PEAK DUO XL-G11C.3/BFG_J 580W | 30391592 | 0 | 464 | 16 | 2022-04-02 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | GRETE MAERSK | ZIMUSEL7119142 | HWNWY2203001 | ZCSU7883340 | Q.PEAK DUO XL-G11C.3/BFG_J 580W | 30391592 | 0 | 464 | 16 | 2022-04-02 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | GRETE MAERSK | ZIMUSEL7119142 | HWNWY2203001 | ZCSU7041228 | Q.PEAK DUO XL-G11C.3/BFG_J 580W | 30391592 | 0 | 464 | 16 | 2022-04-02 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | GRETE MAERSK | ZIMUSEL7119142 | HWNWY2203001 | BEAU5115329 | Q.PEAK DUO XL-G11C.3/BFG_J 580W | 30391592 | 0 | 464 | 16 | 2022-04-02 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | GCXU5560417 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | GCXU5781629 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | HASU5077573 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | MRKU5929620 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | MRSU5425447 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | MSKU8232190 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | MTSU9631603 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | TCKU7003445 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | TCKU7462362 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216579071 | PTIK22U02011 | TGBU5396625 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | CZZU8912043 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | MIEU0051043 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | MRKU5757860 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | MRKU5932161 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | MRSU5421945 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | MSKU8748400 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | TCNU1820231 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | TCNU8853509 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | TLLU5832334 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100141 | GRETE MAERSK | MAEU216573302 | PTIK22U02010 | TRHU5237334 | DUO BLK ML-G10BC.A+/TS 400 | 30390256H | 14.75 | 624 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | FFAU2289240 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | GESU6220630 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | HASU4566775 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | MRSU5440924 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | MRSU5562368 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | MRSU5806335 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | MSKU0587932 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | MSKU9723515 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | TCNU9217219 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579245 | PTIK22U02013 | TGBU6688431 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | GESU5752279 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MRKU4630969 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MRKU4913700 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MRKU5736791 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MRKU5754310 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MRKU6426743 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MSKU0160128 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | MSKU1510175 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | PONU8229107 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72100143 | GRETE MAERSK | MAEU216579133 | PTIK22U02012 | TCLU5567905 | DUO BLK ML-G10BC+.0.1 400 | 30390456H | 14.75 | 768 | 24 | 2022-04-01 | 2022-05-01 |  | 2022-05-12 | [8 empty] | On Vessel | PIONEERNB1475
PIONEER | 72101038 | OOCL BERLIN | COSU6328489080 | YHTPKG489080 | CSNU6608620 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-13 | 2022-05-03 |  | 2022-05-14 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | OOCL BERLIN | COSU6328489080 | YHTPKG489080 | BMOU4812745 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-03-13 | 2022-05-03 |  | 2022-05-14 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000049 | 22SEPKG12836 | SLVU4748085 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000049 | 22SEPKG12836 | SLVU4748130 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000049 | 22SEPKG12836 | SLVU4745506 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000049 | 22SEPKG12836 | SLVU4745337 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000049 | 22SEPKG12836 | SLVU4748110 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000063 | 22SEPKG12878 | CZZU8353860 | Q.PEAK DUO XL-G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-15 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000063 | 22SEPKG12878 | FSCU8304478 | Q.PEAK DUO XL-G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-15 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000063 | 22SEPKG12878 | SLVU4416630 | Q.PEAK DUO XL-G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-15 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000063 | 22SEPKG12878 | SLVU4417955 | Q.PEAK DUO XL-G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-03-15 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101038 | HAKUNA MATATA | SLMP22000063 | 22SEPKG12878 | VOLU4946011 | Q.PEAK DUO XL-G10.3/BFG 475 | 12005833 | 0 | 600 | 20 | 2022-03-15 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | CSNU6638543 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | CSNU7350295 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | TGBU8708394 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | TLLU4578117 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | TRHU4199271 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | COSCO FORTUNE | COSU6330265680 | SHTCS2204048 | UETU5947175 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-09 | 2022-05-10 |  | 2022-05-21 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120168 | HWNWY2204001 | ZCSU6761060 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120168 | HWNWY2204001 | ZCSU7870445 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120168 | HWNWY2204001 | ZCSU7655191 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120168 | HWNWY2204001 | ZCSU8978202 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120168 | HWNWY2204001 | FSCU8175154 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120169 | HWNWY2204002 | ZCSU7861952 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120169 | HWNWY2204002 | TLLU5316528 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120169 | HWNWY2204002 | BEAU5036765 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120169 | HWNWY2204002 | TLLU5798184 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120169 | HWNWY2204002 | ZCSU7326540 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120170 | HWNWY2204003 | ZCSU7970341 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120170 | HWNWY2204003 | ZCSU7902460 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120170 | HWNWY2204003 | ZCSU7702930 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120170 | HWNWY2204003 | TGBU5756629 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | GERDA MAERSK | ZIMUSEL7120170 | HWNWY2204003 | ZCSU8467054 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120171 | HWNWY2204004 | TCNU6133937 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120171 | HWNWY2204004 | TEMU6081387 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120171 | HWNWY2204004 | ZCSU7189961 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120171 | HWNWY2204004 | BSIU9424769 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120171 | HWNWY2204004 | ZCSU7224363 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120172 | HWNWY2204005 | ZCSU7149444 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120172 | HWNWY2204005 | TEMU6769410 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120172 | HWNWY2204005 | CRSU9080430 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120172 | HWNWY2204005 | ZCSU7233196 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120172 | HWNWY2204005 | TCNU5641614 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120173 | HWNWY2204006 | ZCSU7988504 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120173 | HWNWY2204006 | ZCSU7331166 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120173 | HWNWY2204006 | ZCSU7375550 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120173 | HWNWY2204006 | ZCSU7887772 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | GERDA MAERSK | ZIMUSEL7120173 | HWNWY2204006 | TGBU5779162 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-12 | 2022-05-14 |  | 2022-05-25 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | FSCU8289223 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MRKU3241941 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MRKU5037650 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MRSU4302710 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MSKU0704005 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MSKU8192332 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | MVIU0019505 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | TCKU7751956 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100132 | ALS APOLLO | MAEU217282139 | SDSKNWK003 | TCKU7911170 | Q.PEAK DUO XL-G11C.3/BFG_J 580 | 30391592 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282100 | SDSKNWK004 | MRSU6152305 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | CAIU9640171 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | CIPU5022864 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | MRSU3690354 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | MRSU5298492 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | MSKU0096991 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | MSKU0126186 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | PONU8129319 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | TCKU6005150 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | TCKU7075297 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282166 | SDSKNWK005 | TCKU7646550 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | BEAU6291960 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | BEAU6389577 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | HASU4926341 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | MRKU3933560 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | MRSU6114521 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | MSKU0695840 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | PONU7664814 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | SUDU6862418 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | TGHU7945691 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100148 | ALS APOLLO | MAEU217282154 | SDSKNWK006 | TRHU4147534 | Q.PEAK DUO XL-G11C.3/BFG_J 575 | 30391591 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | HASU5037020 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MRKU5523820 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MRKU5723243 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MRSU3545490 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MRSU4631546 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MRSU5960607 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MSKU0017689 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MSKU8322210 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | MSKU9257720 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | TCKU7103634 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | TCNU6683430 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100117 | ALS APOLLO | MAEU217219045 | SDSKNWK001 | TLLU5861311 | Q.PEAK DUO XL-G11C.3/BFG_E 575 | 30391491 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | GESU6557214 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | HASU4306525 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | HASU5173540 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | MRKU3741103 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | MRKU4251137 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | MRKU4619569 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | MSKU8666977 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100135 | ALS APOLLO | MAEU217223949 | SDSKNWK002 | TCNU7061467 | Q.PEAK DUO XL-G11C.3/BFG_E 580 | 30391492 | 0 | 464 | 16 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314093 | SDSKNWK007 | TORU5304226 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314093 | SDSKNWK007 | MSKU1928653 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314093 | SDSKNWK007 | MRSU5824658 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314093 | SDSKNWK007 | SUDU6753654 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314093 | SDSKNWK007 | MRKU3547227 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314118 | SDSKNWK008 | CAAU5067114 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314118 | SDSKNWK008 | MRKU4580657 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314118 | SDSKNWK008 | MRSU6161164 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314118 | SDSKNWK008 | PONU7988897 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72100145 | ALS APOLLO | MAEU217314118 | SDSKNWK008 | TCKU6996044 | Q.PEAK DUO XL-G10C.3.2/BFG 480 | 30392472 | 0 | 580 | 20 | 2022-04-01 | 2022-05-20 |  | 2022-05-31 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | OOCL CHONGQING | COSU6330232300 | YHTUC0000819 | DFSU7335036 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-04-04 | 2022-05-24 |  | 2022-06-04 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | OOCL CHONGQING | COSU6330232300 | YHTUC0000819 | TEMU6190834 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-04-04 | 2022-05-24 |  | 2022-06-04 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | OOCL CHONGQING | COSU6330232300 | YHTUC0000819 | FCIU9824069 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-04-04 | 2022-05-24 |  | 2022-06-04 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | OOCL CHONGQING | COSU6330232300 | YHTUC0000819 | CSNU7921922 | Q.PEAK DUO XL G10.3/BFG 485 | 12005831 | 0 | 600 | 20 | 2022-04-04 | 2022-05-24 |  | 2022-06-04 | [8 empty] | On Vessel | PIONEERNB
PIONEER | 72101040 | OOCL CHONGQING | COSU6330232300 | YHTUC0000819 | OOCU7764629 | Q.PEAK DUO XL G10.3/BFG 480 | 12005832 | 0 | 600 | 20 | 2022-04-04 | 2022-05-24 |  | 2022-06-04 | [8 empty] | On Vessel | PIONEERNB
Formulas:
WH ETA = [ETA/ATA]+11

## Savannah, GA Inbound
WH | PO# | VESSEL | MBL # | HBL # | Container | Model | Item Code | Tariff (%) | PCS | PLT | ETD | ETA/ATA | Updated ETA | WH ETA | DO received | Discharging Date | Discharging lead time | LFD | Outgated | Pickup lead time | Unloaded date | Delivery lead time | Current status/drayage plan | Remark
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU7003357 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | TCLU6621030 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | TCNU4558280 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | TLLU4763809 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU6512452 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-20 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU7130367 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU8592288 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU8681805 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU8904133 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | ALBERT MAERSK | ZIMUSEL7010083 | SDSKSAV309 | ZCSU8943968 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-21 | 2020-01-16 |  |  | 2020-01-06 |  |  | 2020-01-22 |  |  | 2020-01-17 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | BEAU5162887 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | BMOU4503638 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | BSIU9683733 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | BSIU9684370 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | CAAU5239173 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | CAAU5457452 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | DFSU6536437 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | DFSU6715371 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | DRYU9336302 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | FCIU9069461 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | FSCU8155815 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | GAOU6271588 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | GCXU5001722 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | RFCU4041596 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | SEGU5779280 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-27 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TCNU2504454 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TCNU4048693 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TCNU5368691 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TEMU6681490 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU5366533 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU5773312 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU5774833 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU7127820 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU7192317 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | TGBU7211398 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU6546637 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU7027240 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-28 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU7063891 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU7096724 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8480631 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8568152 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8631297 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8677662 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8841945 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | LAS VEGAS | ZIMUSEL7010082 | SDSKSAV318 | ZCSU8984139 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2019-12-28 | 2020-01-25 |  |  | 2020-01-15 |  |  | 2020-01-30 |  |  | 2020-01-29 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | AXIU1488848 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | BMOU5905415 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | CAIU4291544 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | CAXU8223827 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | CRSU9050842 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | DFSU6305947 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | DRYU9657160 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | FSCU6893954 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | FSCU8116320 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | FSCU8172371 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | GAOU6088047 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | GCXU5000916 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | SEGU5335644 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCKU6645311 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCNU4634436 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCNU4764260 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCNU5351718 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCNU5787928 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-03 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TCNU8705116 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-04 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TEMU6748042 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TEMU6773960 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TGBU5483355 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TGBU7210339 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TGBU7236272 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | TLLU5923497 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | WFHU5174302 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU6522661 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU6535709 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU6549338 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU7031240 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU7060547 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU7084370 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU7085334 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8480436 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8618016 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-05 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8636684 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8643683 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8769291 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8920582 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 71900097 | MSC JULIE | ZIMUSEL7010088 | SDSKSAV322 | ZCSU8990595 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-06 | 2020-02-01 |  |  | 2020-01-24 |  |  | 2020-02-06 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | BEAU5346694 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | BMOU4910572 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | CAIU9230500 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | CRSU9044984 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | CRSU9049013 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | FCIU8646851 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | FSCU8219545 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | FSCU8225450 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | GAOU6271799 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-06 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | GVCU5325984 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | HNSU5024009 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | SEGU5204032 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | SEGU5759426 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TCNU2313416 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TCNU4251226 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TCNU5414251 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TGBU5414478 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TGBU5760151 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TGBU7163962 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TGBU7206473 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TGHU6853374 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-07 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TLLU4770557 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TLLU4884272 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | TRLU6928175 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU7016591 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU7102914 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8567238 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8591980 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8628570 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8630855 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8736282 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8836511 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8858655 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8883982 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8967907 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000001 | CPO BREMEN | ZIMUSEL7010085 | SDSKSAV326 | ZCSU8969411 | Q.PEAK DUO L G5.2.1.V 400 | 30361456A | 25 | 638 | 22 | 2020-01-10 | 2020-02-03 |  |  | 2020-01-28 |  |  | 2020-02-10 |  |  | 2020-02-10 |  | DELIVERED | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | BMOU4550028 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | DFSU6236363 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | GESU4798130 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | TCNU2712442 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | TCNU8932038 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | TLLU4441470 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU7000208 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8424371 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8443345 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (FNS20) | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8445100 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8448938 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-18 |  | DELIVERED CLOSE IN CELLO 2/19 - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8540704 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (FNS20) | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8651272 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (FNS20) | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8684173 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (FNS20) | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | ZIM ANTWERP | ZIMUSEL7013339 | NEDFSEATSSE53446 | ZCSU8859245 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-23 | 2020-02-15 |  |  | 2020-02-07 |  |  | 2020-02-20 |  |  | 2020-02-19 |  | DELIVERED (FNS20) | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | BMOU4509770 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | BMOU4521035 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | CAIU4348640 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | CAIU4426300 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | CAXU8038388 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | DRYU9106995 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | FCIU8639657 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | FSCU6831567 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | GAOU6041570 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | GAOU6433420 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | SEGU5764042 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-24 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU2505698 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU2756224 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU5363576 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU5369698 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU5500323 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TCNU5641851 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TGBU5367479 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TGBU5490652 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TGBU5768390 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TGBU5968192 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TGHU9754800 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | TLLU5316364 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU7053867 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-25 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU7088333 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-27 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8669570 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8699337 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8769711 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8866938 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8902465 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8934740 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | TIANJIN | ZIMUSEL7013340 | NEDFSEATSSE53676 | ZCSU8957339 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-01-29 | 2020-02-21 |  |  | 2020-02-13 |  |  | 2020-02-27 |  |  | 2020-02-26 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | BSIU9129336 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | BSIU9538571 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | BSIU9611733 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | CAAU5285950 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | CAAU5458633 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | DRYU9641749 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | FSCU8099291 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | INKU6647362 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TCNU1060674 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TCNU4580896 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-02-28 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TCNU4860069 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TCNU5327882 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TCNU5409194 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TEMU6767994 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TEMU6795213 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TEMU6795790 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TGBU5767259 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TGBU5770967 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TGBU5777344 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TGBU5956611 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TLLU4305956 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TLLU4863686 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | TLLU5384456 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | UETU5270973 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU7041315 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU7058067 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU7066843 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-04 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU7080287 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-04 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU7085102 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8252098 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8476544 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8529428 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-04 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8755683 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8809157 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | CAPE AKRITA | ZIMUSEL7013535 | NEDFSEATSSE53796 | ZCSU8817337 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-03 | 2020-02-26 |  |  | 2020-02-20 |  |  | 2020-03-03 |  |  | 2020-03-04 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | BMOU4925417 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | BSIU9703655 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | FCIU8746491 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | FSCU8172406 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | GAOU6087842 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | SEGU5754698 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TCNU6840082 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TGBU5495356 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TGBU7157419 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TGBU7216147 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TGBU7235234 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TGBU7242130 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TLLU4594226 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TLLU4884159 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | TLLU5916630 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU7011706 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU7048080 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8211308 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8277455 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8453955 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-10 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8497721 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-12 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8502073 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-11 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8516360 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8638727 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8718930 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | MAERSK SOFIA | ZIMUSEL7016293 | NEDFSEATSSE53918 | ZCSU8974594 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-07 | 2020-03-04 |  |  | 2020-02-25 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU6644244 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU6556821 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU6585666 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU6967735 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU7030554 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | APHU7398037 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | BEAU4750090 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | BMOU4252152 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CAIU9271108 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU4215697 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU4467153 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU4728447 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU4919422 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU5246820 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU5962233 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU7267652 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU7909937 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | CMAU7924314 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | FSCU8371060 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | GESU5691173 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | GESU6795300 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | GVTU5016532 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | SEGU4823080 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | SEGU6218832 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TCKU6355689 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TCLU9109990 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TCNU8135440 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TCNU8401480 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TEMU7447763 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TEMU7454870 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TGHU6298970 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0936752 | NEDFSEATSSE53870 | TRLU7345510 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-09 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | APHU6692957 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | APHU7295194 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | BMOU6982376 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU4757888 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU5239733 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU5708825 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU7189122 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU7317820 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU7732179 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | CMAU7741057 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | ECMU9241921 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | GLDU7367088 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | MAGU5339964 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | SEGU4958491 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | SEGU6059936 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | SEGU6287535 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TCLU1492388 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TCLU6565682 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TGHU9514970 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TGHU9611097 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TLLU5191518 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TRLU7348783 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000005 | APL CHALESTON | CMDUSEL0937225 | NEDFSEATSSE53871 | TTNU9535110 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-08 | 2020-03-04 |  |  | 2020-02-26 |  |  | 2020-03-10 |  |  | 2020-03-05 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | DFSU6196620 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-13 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | GAOU6169874 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | GAOU6343991 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | KOCU4299642 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | KOCU4304008 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-13 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | TCLU8397377 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | TCNU5706850 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | TCNU5875037 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | TGBU6478796 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | HDMUBUWB4976455 | NEDFSEATSSE54175 | TLLU5285411 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-19 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | CAIU9230650 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | CRSU9051936 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | TGBU7089870 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | ZCSU8210261 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | ZCSU8513709 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | ZCSU8524621 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016476 | NEDFSEATSSE54153 | ZCSU8650548 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-13 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | CAIU4348151 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | CAIU9221220 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | DRYU9331553 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | FCIU8748581 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | FCIU8921697 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-16 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | FSCU8214991 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | GAOU6037097 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | GAOU6140649 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | GLDU7407690 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | SEGU5810976 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU2300851 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU2308976 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU2500398 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU2765735 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU4557237 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU4581001 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU5417409 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU7258292 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TCNU8780320 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TGBU5765174 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-17 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TGBU7239029 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TLLU4303146 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | TLLU4307769 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU6540351 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU7019100 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU7047252 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU7121597 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8647380 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8677343 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8857582 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8898616 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8934586 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | CAPE KORTIA | ZIMUSEL7016474 | NEDFSEATSSE54197 | ZCSU8939654 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-16 | 2020-03-12 |  |  | 2020-03-06 |  |  | 2020-03-18 |  |  | 2020-03-18 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ZIM ROTTERDAM | ZIMUSEL7017970 | NEDFSEATSSE54326 | TLLU5795251 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-19 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ZIM ROTTERDAM | ZIMUSEL7017970 | NEDFSEATSSE54326 | FCIU9039106 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-02-23 | 2020-03-18 |  |  | 2020-03-12 |  |  | 2020-03-24 |  |  | 2020-03-19 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | BEAU5022930 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | CAAU5458720 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | FCIU8639873 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | FSCU8151569 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | GAOU6109875 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | GAOU6442783 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | GCXU5062013 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | GLDU7407658 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCKU7152304 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU2300050 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-01 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU2525499 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU4556863 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU4564350 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU4576788 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU5407191 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TCNU8774626 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TGBU5414375 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | TLLU4951072 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU7043806 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8241283 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8257530 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-02 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8429199 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-03 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8537357 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8634505 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8664876 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8706246 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8708038 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000012 | ALBERT MAERSK | ZIMUSEL7017908 | NEDFSEATSSE54613 | ZCSU8871404 | Q.PEAK DUO L G5.2.1.V 400 | 30361456R | 20 | 638 | 22 | 2020-03-06 | 2020-03-31 |  |  | 2020-03-23 |  |  | 2020-04-06 |  |  | 2020-04-06 |  | DELIVERED - FNS20 | FNS WAREHOUSE-NEXTERA PROJECT
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | GCXU5060330 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | TGBU7159406 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | TLLU4856049 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU6526121 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU7094845 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU7169353 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU8515553 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU8635029 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU8635245 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-05 |  | DELIVERED CLOSED IN CELLO ON 6/8 (FNS20) | Sillicon Ranch Project
GA | 72000038 | ZIM ROTTERDAM | ZIMUSEL7025694 | PTIK20S05602 | ZCSU8928388 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-10 | 2020-06-03 |  |  | 2020-05-29 |  |  | 2020-06-09 |  |  | 2020-06-08 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | BMOU4020959 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | CAIU9059697 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | DFSU6490090 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | DFSU6603453 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | FSCU8167544 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | SEGU5194269 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | TCNU4238498 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | TCNU7261953 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | TLLU4776555 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU6548183 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU7032890 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-12 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU7034851 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU7155133 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU7174766 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-10 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU7185689 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU8727336 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | COLUMBINE MAERSK | ZIMUSEL7025756 | PTIK20S05604 | ZCSU8741967 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-15 | 2020-06-08 |  |  | 2020-06-03 |  |  | 2020-06-12 |  |  | 2020-06-11 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | BMOU4521333 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | BMOU4523193 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | BMOU4523362 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | BSIU9699690 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | CAAU5287124 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | DFSU6941872 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | DRYU9112025 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | FCIU8914018 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | FCIU9036869 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | FCIU9041989 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | GAOU6459615 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TCLU9263027 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TCNU4764281 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TCNU8607803 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TDRU6733096 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TGBU5958234 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TLLU4586684 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TLLU4857338 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | TLLU5883408 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | UETU5935683 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | UETU5937177 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU7076630 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU7121679 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU7157753 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8447443 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8465853 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8600697 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8678144 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8686659 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8705682 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8722170 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8729920 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7025698 | PTIK20S05607 | ZCSU8894204 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-17 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | BMOU4506940 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | BMOU4562820 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | CAIU4332622 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | CAIU4433799 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | GAOU6437730 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | GCXU5081950 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TCNU2756707 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TCNU4561200 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TCNU6463163 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TCNU6952138 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TCNU8551113 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TGBU7088827 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | TLLU4859937 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU6538159 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU6545060 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU7155853 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU7195096 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-18 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8584723 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8622320 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8643003 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-19 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8709158 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8800870 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8820120 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8866202 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | ALBERT MAERSK | ZIMUSEL7026535 | PTIK20S05608 | ZCSU8907770 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-22 | 2020-06-16 |  |  | 2020-06-11 |  |  | 2020-06-22 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | BMOU4509451 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | BSIU9611327 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | CAAU5455845 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | CAIU4333228 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | GAOU6041029 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-22 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | GCXU5081055 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TCNU4235673 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TCNU5370805 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TCNU5418880 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TGBU5480356 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TGBU5960530 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TGBU7180595 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TGBU7227537 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TLLU4736980 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-23 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | TLLU4892215 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | UESU5260797 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | WFHU5179407 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | ZCSU7169250 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | ZCSU7193956 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | SANTA LORETTA | ZIMUSEL7025697 | PTIK20S05610 | ZCSU8871699 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-24 | 2020-06-17 |  |  | 2020-06-11 |  |  | 2020-06-23 |  |  | 2020-06-24 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | DFSU6960825 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | DRYU9065155 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | FCIU8919236 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | FSCU8091937 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | GAOU6442335 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | TCNU4245898 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | TCNU4260758 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | TCNU4401835 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | TCNU4439152 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | TCNU4637667 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU6545970 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU6552199 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU7151143 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU7181180 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU7183310 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU8615070 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU8848744 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU8916730 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU8918667 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025696 | PTIK20S05611 | ZCSU8955866 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | BSIU9543182 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | CAIU4346550 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | CAIU4352784 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | CAIU9220796 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | DRYU9635284 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | FCIU8914002 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | FSCU8253766 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-30 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | GAOU6109828 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-29 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | GLDU7421234 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | SEGU5275421 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TCKU6014553 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TCNU1832382 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TCNU2301251 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TCNU4408383 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TCNU5092514 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TGBU5412222 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-06-26 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TGBU5775721 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-06 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | TGBU7220131 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | ZCSU8601266 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-06 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE SOUNIO | ZIMUSEL7025984 | PTIK20S05612 | ZCSU8723011 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-05-31 | 2020-06-24 |  |  | 2020-06-18 |  |  | 2020-06-30 |  |  | 2020-07-01 |  | Direct shipment to SR EPC, LLC - DELIVERED | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | CAIU4416976 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | CRSU9077648 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | DRYU9140897 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | FSCU8224520 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | GAOU6140588 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TCNU4247648 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TCNU4952062 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TCNU6822936 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TCNU8394652 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TGBU7219716 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TGBU7260052 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | TLLU4783615 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | WFHU5195476 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | ZCSU8651734 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025985 | PTIK20S06001 | ZCSU8786719 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-07-01 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | BMOU4058933 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | CAAU5004857 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | FCIU8919278 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TCNU4428440 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TCNU4870787 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TCNU5274416 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-07 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TCNU5355436 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TCNU8112321 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TLLU5272060 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | TLLU5310094 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU6519605 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU7007389 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-08 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU7178340 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8563171 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8623455 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8705403 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8711659 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-09 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8759816 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8817527 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC | Sillicon Ranch Project
GA | 72000038 | CAPE TAINARO | ZIMUSEL7025703 | PTIK20S06602 | ZCSU8932496 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-07 | 2020-07-01 |  |  | 2020-06-30 |  |  | 2020-07-08 |  |  | 2020-07-06 |  | DELIVERED CLOSED IN CELLO ON 7/9 (FNS20) | Sillicon Ranch Project
GA | 72000048 | CPO BREMEN | ZIMUSEL7025991 | PTIK20S06605 | GAOU6115482 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-12 | 2020-07-07 |  |  | 2020-07-02 |  |  | 2020-07-13 |  |  | 2020-07-13 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | CPO BREMEN | ZIMUSEL7025991 | PTIK20S06605 | TCNU5833005 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-12 | 2020-07-07 |  |  | 2020-07-02 |  |  | 2020-07-13 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | CPO BREMEN | ZIMUSEL7025991 | PTIK20S06605 | GAOU6118590 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-12 | 2020-07-07 |  |  | 2020-07-02 |  |  | 2020-07-13 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | CPO BREMEN | ZIMUSEL7025991 | PTIK20S06605 | CAIU4418074 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-12 | 2020-07-07 |  |  | 2020-07-02 |  |  | 2020-07-13 |  |  | 2020-07-10 |  | DELIVERED Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | DRYU9229243 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | GCXU5002483 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | GCXU5068372 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | SEGU5423616 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TCKU7152794 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TCNU8393872 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TCNU8724414 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TEMU6746121 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-21 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TGBU7129510 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TLLU4451550 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | TLLU4590874 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | ZCSU7023651 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | ZCSU7129432 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | ZCSU8644247 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | ZCSU8655616 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000038 | SEAMAX NEW HAVEN | ZIMUSEL7025753 | PTIK20S06604 | ZCSU8822631 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | BSIU9144963 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | BSIU9217680 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | CAAU5456667 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | DFSU6537156 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | FSCU8222791 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | GAOU6447912 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | SEGU5333467 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TCNU2310340 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TCNU4582369 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TCNU5357531 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TCNU6836858 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TCNU8676070 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TGBU5497683 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-24 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TGBU7240457 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TGHU9789520 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TLLU4770238 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-23 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TLLU4939992 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-24 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | TLLU5793639 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-24 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU7069890 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8254871 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8486054 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8527512 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-22 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8615001 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-24 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8725138 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-24 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8738310 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-29 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8789533 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8815817 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-28 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8829615 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-28 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8845067 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8856987 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8879658 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8890744 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-27 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8924130 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-28 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8924633 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-29 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | SEAMAX NEW HAVEN | ZIMUSEL7025757 | PTIK20S06606 | ZCSU8969480 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-19 | 2020-07-17 |  |  | 2020-07-09 |  |  | 2020-07-23 |  |  | 2020-07-30 |  | DELIVERED --> Direct shipment to SR EPC, LLC 591 Bill May Road Moultrie, GA 31788 | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | BEAU5037798 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-23 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | BMOU4512223 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | BMOU4940068 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | BSIU9714897 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | CAIU4303347 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | DRYU9115127 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | DRYU9644856 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | FCIU8638060 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | FCIU8747477 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | FCIU8918585 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | FSCU8148499 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | GAOU6086980 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-08-12 |  |  | 2020-08-07 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | GCXU5059920 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | SEGU5277424 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | SEGU5283704 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU4295651 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU4562491 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU6395496 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-24 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU7094856 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU8389804 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU8703875 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TCNU8937301 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TEMU6766350 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TEMU6796436 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TGBU7220717 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TLLU4863433 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | TLLU4888431 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU7137715 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU7140771 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU8422316 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU8566680 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-27 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU8708589 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU8769352 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72000048 | ARTHUR MAERSK | ZIMUSEL7025760 | PTIK20S06608 | ZCSU8812588 | Q.PEAK DUO L-G5.2.2.V 400 | 30361556R | 20 | 638 | 22 | 2020-06-26 | 2020-07-21 |  |  | 2020-07-15 |  |  | 2020-07-27 |  |  | 2020-07-28 |  | DELIVERED (FNS20) | Sillicon Ranch Project
GA | 72001052 | AL QIBLA | HLCUKUL201230278 | YASVPKG0026029 | HAMU1310448 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2020-12-30 | 2021-02-08 |  |  | 2021-02-01 |  |  | 2021-02-16 |  |  | 2021-02-12 |  | DELIVERED | CLOSED IN CELLO 02/17 (JIT18) NextEra
GA | 72001052 | AL QIBLA | HLCUKUL201230278 | YASVPKG0026029 | HLXU8158592 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2020-12-30 | 2021-02-08 |  |  | 2021-02-01 |  |  | 2021-02-16 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (JIT18) NextEra
GA | 72001052 | AL QIBLA | HLCUKUL201230278 | YASVPKG0026029 | HLXU8439521 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2020-12-30 | 2021-02-08 |  |  | 2021-02-01 |  |  | 2021-02-16 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (JIT18) NextEra
GA | 72001052 | AL QIBLA | HLCUKUL201230278 | YASVPKG0026029 | TCLU5680779 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2020-12-30 | 2021-02-08 |  |  | 2021-02-01 |  |  | 2021-02-16 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/12 (JIT18) NextEra
GA | 72001052 | AL QIBLA | HLCUKUL201230278 | YASVPKG0026029 | UACU5405478 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2020-12-30 | 2021-02-08 |  |  | 2021-02-01 |  |  | 2021-02-16 |  |  | 2021-02-11 |  | DELIVERED | CLOSED IN CELLO 02/15 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | BEAU4171117 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/24 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | CLHU8433040 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | FCIU7337288 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | FSCU6477480 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | HAMU1327163 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-22 |  | DELIVERED | CLOSED IN CELLO 02/24 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | HLBU2209458 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | HLXU6405918 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-24 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | HLXU8216425 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | HLXU8252314 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-23 |  | DELIVERED | CLOSED IN CELLO 02/24 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | SEGU5107747 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | TCNU6695929 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | TCNU8850304 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | TEMU7558685 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | TGBU5906122 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | UACU5106902 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | UACU5280956 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | UACU5449877 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | UACU5791180 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-26 |  | DELIVERED | (JIT18) NextEra
GA | 72001052 | DALIAN EXPRESS | HLCUKUL201227990 | YASVPKG0026017 | UACU5869740 | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 638 | 22 | 2021-01-13 | 2021-02-19 |  |  | 2021-02-10 |  |  | 2021-02-26 |  |  | 2021-02-25 |  | DELIVERED | CLOSED IN CELLO 02/26 (JIT18) NextEra
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | BMOU5024964 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | CBHU9530446 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-08 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | CSNU6627847 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | FSCU8680053 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/27 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | GCXU5290625 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-08 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOCU7493018 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOCU7776790 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOLU8512968 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/19 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOLU8557068 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOLU8688319 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | OOLU8832848 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/19 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | TCNU1794127 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-08 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | TCNU2549459 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/19 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | TCNU6876064 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/19 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | CMA CGM THALASSA | COSU6300052230 | SDSMY20210218-02 | TGHU6844599 | Q.PEAK DUO L-G8.2 425 | 12004246F | 18 | 660 | 22 | 2021-02-24 | 2021-04-02 |  |  | 2021-03-22 |  |  | 2021-04-09 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CBHU7086796 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CBHU8808743 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CBHU9543649 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CCLU7229583 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CCLU7615462 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CCLU7666177 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CCLU7773920 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CSLU6311039 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | CSNU6413866 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/27 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | FCIU9127568 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | FCIU9604399 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/27 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | FSCU8889927 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | FSCU8915820 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | FSCU9315116 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | OOCU8156710 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | OOLU8601453 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | TCNU3491217 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | TCNU3867475 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | TCNU6308151 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-14 |  |  | 2021-04-14 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | COSU6291645290 | SDSMY20210225-03 | UETU5190878 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18) CUSTOMER (DUKE)
GA | 72101002 | APL DUBLIN | CMDUAYN0677125 | SDSMY20210225-05 | CAIU8930113 | Q.PEAK DUO L-G8.2 430 | 12004245F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-12 |  |  | 2021-04-09 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | APHU6658504 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | BMOU5567616 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | CMAU5180403 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | CMAU7053732 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/20 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | FSCU7130480 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-12 |  |  | 2021-04-12 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | GESU6540525 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/27 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | MAGU5754902 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | TCNU2246112 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/21 (JIT18)
GA | 72101002 | APL DUBLIN | CMDUAYN0672414 | SDSMY20210225-04 | TEMU6225247 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-02-27 | 2021-04-06 |  |  | 2021-03-23 |  |  | 2021-04-13 |  |  | 2021-04-13 |  | DELIVERED | CLOSED IN CELLO 04/27 (JIT18)
GA | 72101002 | COSCO DEVELOPMENT | COSU6292312750 | SDSMY20210227-01 | CAIU4795503 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-02 | 2021-05-10 |  |  | 2021-04-29 |  |  | 2021-05-17 |  |  | 2021-05-14 |  | DELIVERED | CLOSED IN CELLO 05/20 (JIT18)
GA | 72101002 | COSCO DEVELOPMENT | COSU6292312750 | SDSMY20210227-01 | DFSU7290498 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-02 | 2021-05-10 |  |  | 2021-04-29 |  |  | 2021-05-17 |  |  | 2021-05-14 |  | DELIVERED | CLOSED IN CELLO 05/20 (JIT18)
GA | 72101002 | COSCO DEVELOPMENT | COSU6292312750 | SDSMY20210227-01 | FCIU9534497 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-02 | 2021-05-10 |  |  | 2021-04-29 |  |  | 2021-05-17 |  |  | 2021-05-17 |  | DELIVERED | CLOSED IN CELLO 05/20 (JIT18)
GA | 72101002 | COSCO DEVELOPMENT | COSU6292312750 | SDSMY20210227-01 | OOCU8067742 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-02 | 2021-05-10 |  |  | 2021-04-29 |  |  | 2021-05-18 |  |  | 2021-05-17 |  | DELIVERED | CLOSED IN CELLO 05/20 (JIT18)
GA | 72101002 | COSCO DEVELOPMENT | COSU6292312750 | SDSMY20210227-01 | OOLU8285801 | Q.PEAK DUO L-G8.2 420 | 12004247F | 18 | 660 | 22 | 2021-03-02 | 2021-05-10 |  |  | 2021-04-29 |  |  | 2021-05-18 |  |  | 2021-05-17 |  | DELIVERED | CLOSED IN CELLO 05/20 (JIT18)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | APHU6500843 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | APHU6860897 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | APHU7180472 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | APHU7312516 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | CAIU9694861 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | CMAU4201163 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | CMAU4378380 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | CMAU5975800 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/25 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | GESU5617026 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | SEGU4083764 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | TCNU7805168 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-07 |  |  | 2021-06-04 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | TCNU8053912 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | TCNU8998708 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-07 |  |  | 2021-06-04 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101007 | CMA CGM CHILE | CMDUAYN0683865 | SDSMY20210421-02 | TGHU6294614 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-04-27 | 2021-06-01 |  |  | 2021-05-25 |  |  | 2021-06-08 |  |  | 2021-06-07 |  | DELIVERED | CLOSED IN CELLO 06/10 (JIT18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | BEAU5678256 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/15 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | BSIU9589666 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-07 |  | DELIVERED | CLOSED IN CELLO 07/15 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | CSNU7171474 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-13 |  | DELIVERED | CLOSED IN CELLO 07/15 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | CSNU7510691 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/13 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | FFAU2328239 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-05 |  | DELIVERED | CLOSED IN CELLO 07/13 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | OOCU6494848 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-05 |  | DELIVERED | CLOSED IN CELLO 07/13 (DGM18) CUSTOMER (SUNNOVA)
GA | 72101016 | APL SENTOSA | COSU6299713279 | SDSMY20210513-04 | UETU5413225 | Q.PEAK DUO-G8+ 350 | 12005041FPLUS | 18 | 832 | 26 | 2021-05-18 | 2021-07-01 |  |  | 2021-06-22 |  |  | 2021-07-08 |  |  | 2021-07-05 |  | DELIVERED | CLOSED IN CELLO 07/15 (DGM18) CUSTOMER (SUNNOVA)
GA | 72100038 | EVER LEADING | EGLV040100239501 | PTIK21S06102 | FCIU9318712 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-17 | 2021-07-17 |  |  | 2021-07-09 |  |  | 2021-07-24 |  |  | 2021-07-21 |  | DELIVERED | CLOSED IN CELLO 08/02 (DGM18) Duke (Bay Trail project)
GA | 72100038 | EVER LEADING | EGLV040100239501 | PTIK21S06102 | EITU1110900 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-17 | 2021-07-17 |  |  | 2021-07-09 |  |  | 2021-07-24 |  |  | 2021-07-20 |  | DELIVERED | CLOSED IN CELLO 08/02 (DGM18) Duke (Bay Trail project)
GA | 72100038 | EVER LEADING | EGLV040100239501 | PTIK21S06102 | EISU9186745 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-17 | 2021-07-17 |  |  | 2021-07-09 |  |  | 2021-07-24 |  |  | 2021-07-25 |  | DELIVERED | CLOSED IN CELLO 08/02 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM17173100 | PTIK21S06103 | KOCU4457265 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM17173100 | PTIK21S06103 | KOCU4619134 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM17173100 | PTIK21S06103 | TCNU8403815 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM08569600 | PTIK21S06104 | BSIU9628037 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM08569600 | PTIK21S06104 | CAIU7164559 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM08569600 | PTIK21S06104 | CAIU7482605 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | CAIU4561378 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | CAIU7218911 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | CAIU7457372 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | HDMU6709145 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-30 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | HMMU6055891 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | KOCU4399507 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | KOCU4676113 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-30 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | KOCU4743280 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | KOCU4753230 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-30 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ULSAN EXPRESS | HDMUSELM44326900 | PTIK21S06105 | KOCU4845213 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-20 | 2021-07-24 |  |  | 2021-07-12 |  |  | 2021-07-29 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | BMOU4071874 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | BSIU9617731 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | CAAU5135693 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | CAIU7233201 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-02 |  | DELIVERED | CLOSED IN CELLO 08/03 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | CAIU7515756 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | CAIU7637380 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-04 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | GAOU6338790 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | HDMU6659682 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | HDMU6674141 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | HMMU6043308 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-05 |  |  | 2021-08-04 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | HMMU6152485 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-05 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | KOCU4449758 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-05 |  |  | 2021-08-04 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | KOCU4685521 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | TCNU7317918 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM93353300 | PTIK21S06097 | TCNU8503563 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-04 |  |  | 2021-08-03 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ONE WREN | HDMUSELM95840701 | PTIK21S06098 | KOCU4546676 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-25 |  |  | 2021-07-12 |  |  | 2021-08-05 |  |  | 2021-08-05 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | COSCO DEVELOPMENT | EGLV040100239497 | PTIK21S06100 | OCGU8074085 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-30 |  |  | 2021-07-20 |  |  | 2021-08-07 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | COSCO DEVELOPMENT | EGLV040100239497 | PTIK21S06100 | DRYU9862415 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-30 |  |  | 2021-07-20 |  |  | 2021-08-07 |  |  | 2021-08-06 |  | DELIVERED | CLOSED IN CELLO 08/07 (DGM18) Duke (Bay Trail project)
GA | 72100038 | COSCO DEVELOPMENT | EGLV040100239497 | PTIK21S06100 | TGBU6488958 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-16 | 2021-07-30 |  |  | 2021-07-20 |  |  | 2021-08-07 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | EVER LEGION | CMDUSEL1162365 | HW2107004 | FFAU2119054 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-08 | 2021-08-05 |  |  | 2021-07-29 |  |  | 2021-08-09 |  |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | CAIU7203470 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | CAIU7341377 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | CAIU7342012 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | CAIU7670665 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | CAIU9980757 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | HDMU6468080 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | HDMU6753195 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | HDMU6852264 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/18 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | KOCU4012644 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | KOCU4052035 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | KOCU4538691 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | SEGU5694500 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | TCLU8611961 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | TCNU4446212 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM62950600 | PTIK21S06108 | TCNU5604903 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM33305100 | PTIK21S06107 | CAIU7156126 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM33305100 | PTIK21S06107 | KOCU4073790 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM33305100 | PTIK21S06107 | KOCU4585055 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM33305100 | PTIK21S06107 | TCNU8676722 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | ESSEN EXPRESS | HDMUSELM33305100 | PTIK21S06107 | TCNU8993711 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-06-29 | 2021-08-12 |  |  | 2021-07-26 |  |  | 2021-08-18 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 CELL (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | CAIU9974815 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | DFSU6947567 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | HDMU6717752 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | HDMU6763341 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | HDMU6792123 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | HMMU6234011 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | KOCU4018175 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | KOCU4176714 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | KOCU4504897 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TCNU7239688 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TCNU7271340 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TCNU8505294 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TEMU6068575 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TLLU5296400 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-23 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM00261400 | PTIK21S07111 | TLLU5303897 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM46659100 | PTIK21S06109 | CAIU7688582 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-23 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM46659100 | PTIK21S06109 | GAOU6200630 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-23 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM46659100 | PTIK21S06109 | HMMU6056096 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-23 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM46659100 | PTIK21S06109 | HMMU6117205 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM46659100 | PTIK21S06109 | HMMU6249011 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-23 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | FCIU8967830 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/18 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | HDMU6838800 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/18 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | HMMU6038997 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4517451 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4520901 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4668890 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4783955 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4821973 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | KOCU4946857 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035000 | PTIK21S07114 | TCNU9644545 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | BMOU5183328 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | HDMU6540327 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | HMMU6234916 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-16 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4004504 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4224303 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4413375 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4460530 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4559610 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/17 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | KOCU4728829 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035001 | PTIK21S07115 | TCNU6282910 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/18 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | BSIU9943949 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | CAIU7491382 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | CAIU7657914 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | DFSU6835171 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | GAOU6209977 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | DELIVERED CLOSED IN CELLO 08/25 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | HMMU6269337 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-27 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/30 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | KOCU4415491 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-27 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/30 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | KOCU4593533 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/24 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | KOCU4659482 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/23 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035002 | PTIK21S07118 | TGBU5887845 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | DELIVERED CLOSED IN CELLO 08/25 (DGM18) Duke (Bay Trail project)
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | BSIU9204722 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | CAIU7658947 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | CAIU9973830 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-17 |  | DELIVERED | CLOSED IN CELLO 08/18 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | GAOU6343918 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | HDMU6578960 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | HMMU6122480 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | KOCU4237620 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | KOCU4694312 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | TCNU8683188 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-18 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035003 | PTIK21S07124 | TEMU7307020 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035004 | PTIK21S07116 | CAIU9824040 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035004 | PTIK21S07116 | HMMU6000224 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-19 |  | DELIVERED | CLOSED IN CELLO 08/19 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035004 | PTIK21S07116 | HMMU6247493 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035004 | PTIK21S07116 | HMMU6312958 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI GOODWILL | HDMUSELM08035004 | PTIK21S07116 | KOCU4199793 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-05 | 2021-08-13 |  |  | 2021-07-26 |  |  | 2021-08-19 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164097 | HW2107031 | BEAU6085595 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-23 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164097 | HW2107031 | CMAU4501767 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-23 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164097 | HW2107031 | CMAU5561056 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-23 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164097 | HW2107031 | TCLU8653925 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-23 |  | DELIVERED | CLOSED IN CELLO 08/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | CAIU9578727 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-25 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/25 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | CMAU7565364 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-27 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | TCKU6212306 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-27 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | TCKU6310914 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-19 |  |  | 2021-08-25 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/25 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | TCNU2396004 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/25 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100052 | EVER LENIENT | CMDUSEL1164343 | HW2107032 | TCNU4431594 | Q.PEAK DUO XL-G10B.C 480 | 30397372F | 18 | 580 | 20 | 2021-07-20 | 2021-08-15 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-26 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 08/27 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | HYUNDAI HOPE | HDMUSELM68471301 | PTIK21S07125 | BSIU9234054 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-17 |  |  | 2021-08-02 |  |  | 2021-08-24 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100048 | HYUNDAI HOPE | HDMUSELM68471301 | PTIK21S07125 | CAIU4387245 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-17 |  |  | 2021-08-02 |  |  | 2021-08-23 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100048 | HYUNDAI HOPE | HDMUSELM68471301 | PTIK21S07125 | HMMU6270024 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-17 |  |  | 2021-08-02 |  |  | 2021-08-25 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | SANTA LINEA | ZIMUSEL7081923 | PTIK21S07134 | ZCSU8472678 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-18 | 2021-08-16 |  |  | 2021-08-06 |  |  | 2021-08-20 |  |  | 2021-08-20 |  | DELIVERED | CLOSED IN CELLO 08/20 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI SPEED | HDMUSELM68471300 | PTIK21S07122 | HMMU6299244 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-25 |  |  | 2021-08-04 |  |  | 2021-09-01 |  |  | 2021-08-30 |  | DELIVERED | CLOSED IN CELLO 08/30 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI SPEED | HDMUSELM68471300 | PTIK21S07122 | KOCU4061654 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-25 |  |  | 2021-08-04 |  |  | 2021-09-01 |  |  | 2021-08-30 |  | DELIVERED | CLOSED IN CELLO 08/30 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI SPEED | HDMUSELM68471300 | PTIK21S07122 | KOCU4528991 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-25 |  |  | 2021-08-04 |  |  | 2021-09-01 |  |  | 2021-08-31 |  | DELIVERED | CLOSED IN CELLO 08/31 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100038 | HYUNDAI SPEED | HDMUSELM68471300 | PTIK21S07122 | TCNU1765746 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-07-09 | 2021-08-25 |  |  | 2021-08-04 |  |  | 2021-09-01 |  |  | 2021-08-31 |  | DELIVERED | CLOSED IN CELLO 08/31 (FNS18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | CRSU9031971 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | HASU4452160 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | HASU4466159 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | HASU4650720 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | HASU4889818 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MIEU0033939 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MRKU2868285 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MRKU5323490 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MRKU6276622 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MRSU4237661 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MSKU0161016 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MSKU0404815 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-17 |  | DELIVERED | CLOSED IN CELLO 09/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MSKU8688636 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/22 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | MSKU9103290 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/22 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | TCKU7760990 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/22 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | TGBU6653137 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | TRHU4995387 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | MAEU212468928 | GLVSKR0003686 | TRHU5085545 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-10-15 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | BMOU4513180 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) SILICON RANCH 475 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | FSCU8153582 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 09/24 (FNS18) SILICON RANCH 475 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | TCNU4256233 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 09/24 (FNS18) SILICON RANCH 475 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | TLLU4864281 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | ZCSU8970829 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 564 | 20 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-24 |  | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 09/24 (FNS18) SILICON RANCH 475 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | ZCSU8976806 | Q.PEAK DUO XL-G10.3/BFG 470 | 30397270F | 18 | 205 | 8 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) CED 470 PW
GA | 72100048 | ZIM WILMINGTON | ZIMUSEL7085133 | PTIK21S08163 | ZCSU8976806 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 43 | 2 | 2021-08-11 | 2021-09-15 |  |  | 2021-08-25 |  |  | 2021-09-22 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | GAOU6375140 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | HDMU6656770 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | HDMU6692886 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 & 9/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | HDMU6845183 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | HMMU6232343 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | KOCU4132676 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | KOCU4421365 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | KOCU4918557 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | KOCU5083431 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSE IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM44813500 | PTIK21S08175 | TLLU5819327 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-23 |  | DELIVERED | CLOSE IN CELLO 09/24 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | KOCU4850518 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | KOCU4703965 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | TGBU6350465 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | KOCU4105069 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | CAIU9980865 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | KOCU4155049 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/23 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | SEGU5146487 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | HDMU6815770 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | KOCU5045914 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM82098600 | PTIK21S08176 | TCNU5316213 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/22 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM19182200 | SHTCS2108112 | CAIU7482673 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM19182200 | SHTCS2108112 | HMMU6273975 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM19182200 | SHTCS2108112 | KOCU4804913 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-20 |  | DELIVERED | CLOSED IN CELLO 09/21 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | CAIU4385999 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | GAOU6207320 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | HMMU6141351 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | HMMU6237812 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | HMMU6472540 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | HYUNDAI ANTWERP | HDMUSELM07397400 | PTIK21S08172 | KOCU4253554 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-17 |  |  | 2021-08-25 |  |  | 2021-09-23 |  |  | 2021-09-21 |  | DELIVERED | CLOSED IN CELLO 09/24 (DGM18) SILICON RANCH 475 PW
GA | 72100054 | AKINADA BRIDGE | MAEU212675207 | GLVSKR0004034 | MSKU9796770 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-18 |  |  | 2021-08-25 |  |  | 2021-10-18 |  |  | 2021-09-23 |  | DELIVERED | CLOSE IN CELLO 09/24 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA | 72100054 | AKINADA BRIDGE | MAEU212675207 | GLVSKR0004034 | TGBU5383417 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-18 |  |  | 2021-08-25 |  |  | 2021-10-18 |  |  | 2021-09-23 |  | DELIVERED | CLOSED IN CELLO 09/24 (FNS18) SILICON RANCH 475 PW
GA | 72100054 | AKINADA BRIDGE | MAEU212675207 | GLVSKR0004034 | TGHU6867280 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-18 |  |  | 2021-08-25 |  |  | 2021-10-18 |  |  | 2021-09-24 |  | DELIVERED | CLOSED IN CELLO 09/24 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | DRYU9651670 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-04 | 8 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/04 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | JZPU8016249 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-04 | 8 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/04 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | TGBU5773333 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-04 | 8 | 2021-10-05 | 1 | DELIVERED | CLOSED IN CELLO 10/6 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | ZCSU7013910 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-04 | 8 | 2021-10-05 | 1 | DELIVERED | CLOSED IN CELLO 10/6 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | ZCSU7331530 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-05 | 9 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/6 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | TIANJIN | ZIMUSEL7085138 | PTIK21S08180 | ZCSU8988880 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-26 | 2021-09-19 |  | 2021-09-30 | 2021-09-14 | 2021-09-26 | 7 | 2021-09-30 | 2021-10-05 | 9 | 2021-10-05 | 0 | DELIVERED | CLOSED IN CELLO 10/6 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | ZCSU7423982 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-07 | 9 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | CAIU4417334 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-07 | 9 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | TCNU2314578 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-07 | 9 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | ZCSU7388156 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | TCNU8756411 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | TLLU5313874 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | ZCSU8538292 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | TCNU6292538 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | ZCSU8589290 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088181 | PTIK21S08164 | GAOU6098913 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | GAOU6041266 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 CELL (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | GAOU6139798 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 CELL (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | TCNU5559548 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | TGBU7087780 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | TLLU5320390 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | TLLU5386823 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | ZCSU7339594 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | ZCSU7509535 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/12(FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | ZCSU8685668 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 CELL (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088182 | PTIK21S08167 | ZCSU8948086 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 CELL (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | DRYU9024808 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCLU5940562 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCNU2755700 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCNU4249403 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCNU4766221 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCNU8539822 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | TCNU8770507 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | ZCSU7755272 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | ZCSU7755816 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-FNS | 72100048 | CORNELIA MAERSK | ZIMUSEL7088183 | PTIK21S08168 | ZCSU8242187 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-03 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) SILICON RANCH 475 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | SEGU5275798 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | SEGU5781902 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | TCKU6164574 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | TCNU4241552 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-11 | 3 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | TCNU5487160 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-08 | 10 | 2021-10-12 | 4 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | TLLU5794701 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100048 | CORNELIA MAERSK | ZIMUSEL7088184 | PTIK21S08169 | ZCSU8756653 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | BSIU9715487 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | CAIU9224430 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | FCIU8954324 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | FSCU8095850 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | MAGU5619604 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | TCKU6161404 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | ZCSU6535416 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-01 | 2021-10-04 | 6 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/04 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | ZCSU7445620 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-13 | 1 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | ZCSU7448933 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-13 | 15 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL7088187 | PTIK21S08165 | ZCSU8435951 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-13 | 15 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/17 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL200222742 | PTIK21S08170 | BMOU4522730 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL200222742 | PTIK21S08170 | ZCSU7287700 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-11 | 13 | 2021-10-12 | 1 | DELIVERED | CLOSED IN CELLO 10/ 13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | CORNELIA MAERSK | ZIMUSEL200222742 | PTIK21S08170 | ZCSU7452996 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-15 | 2021-09-27 |  | 2021-10-08 | 2021-09-20 | 2021-09-28 | 1 | 2021-10-04 | 2021-10-12 | 14 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW; PORT CONGESTION
GA-DGM | 72100054 | HAMBURG EXPRESS | HDMUSELM47757900 | SHTCS2108185 | CAIU9876151 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-31 | 2021-09-27 |  | 2021-10-08 | 2021-09-29 | 2021-10-05 | 8 | 2021-10-11 | 2021-10-06 | 1 | 2021-10-07 | 1 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | GAOU6113089 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | TEMU6647598 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | TGBU7220208 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | TLLU4589805 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | TLLU4857209 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-07 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | ZIMUSEL7085222 | PTIK21S09186 | ZCSU7299070 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-20 | 2021-10-01 | 0 | 2021-10-07 | 2021-10-07 | 6 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ZIM ANTWERP | SUDUN1SOL0189911 | HW2108054 | MRSU3012188 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-21 | 2021-10-03 | 2 | 2021-10-07 | 2021-10-04 | 1 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/04 (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | ZIM ANTWERP | SUDUN1SOL0189911 | HW2108054 | MIEU2000533 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-29 | 2021-10-01 |  | 2021-10-12 | 2021-09-21 | 2021-10-03 | 2 | 2021-10-07 | 2021-10-04 | 1 | 2021-10-04 | 0 | DELIVERED | CLOSED IN CELLO 10/04 (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | EGHU9628710 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-06 | 1 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | EISU8234387 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-06 | 1 | 2021-10-07 | 1 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | EMCU8270078 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-06 | 1 | 2021-10-07 | 1 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | EMCU9485044 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-07 | 2 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TGBU4443419 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-08 | 3 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TGBU8630320 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-13 | 8 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TRHU5242731 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-13 | 8 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TRHU5657297 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-13 | 8 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TRHU5805028 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-13 | 8 | 2021-10-14 | 1 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | CAAU5447027 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-06 | 1 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | EGHU9136536 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-06 | 1 | 2021-10-06 | 0 | DELIVERED | CLOSED IN CELLO 10/8 (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | FFAU2088797 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-07 | 2 | 2021-10-08 | 1 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) CELL (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TCLU7831895 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-08 | 3 | 2021-10-08 | 0 | DELIVERED | CLOSED IN CELLO 10/11 (DGM18) CELL (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | EVER FAST | EGLV040100433480 | TWSC21080790 | TRHU7188516 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-08-23 | 2021-10-04 |  | 2021-10-15 | 2021-09-29 | 2021-10-05 | 1 | 2021-10-12 | 2021-10-13 | 8 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) SILICON RANCH 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | JZPU8034957 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-11 | 2 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | TLLU4307579 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-11 | 2 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | TLLU4456741 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-12 | 3 | 2021-10-12 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | ZCSU7017941 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-11 | 2 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | ZCSU8504374 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-11 | 2 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100054 | ADONIS | ZIMUSEL7087939 | PTIK21S09188 | GAOU6079512 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-08 | 2021-10-05 |  | 2021-10-16 | 2021-09-29 | 2021-10-09 | 4 | 2021-10-14 | 2021-10-11 | 2 | 2021-10-11 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (DGM18) EMPIRE VALORIZE, ORDEN, DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | BMOU5210763 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | CAIU7349249 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-13 | 2 | 2021-10-14 | 1 | DELIVERED | CLOSED IN CELLO 10/14 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | DFSU6195665 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | DFSU6721754 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-13 | 2 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/13 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | HDMU6753657 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | HMMU6087780 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | KOCU4611961 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | KOCU4842560 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-18 | 6 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | TCLU4844461 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-15 | 1 | DELIVERED | CLOSED IN CELLO 10/15 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-FNS | 72100048 | ONE HAWK | HDMUSELM18353101 | PTIK21S08160 | TCNU8505210 | Q.PEAK DUO XL-G10.3/BFG 475 | 30397271F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-03 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (FNS18) DUKE(BAY TRAIL) 475 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754300 | PTIK21S08161 | HDMU6835884 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-13 | 2 | 2021-10-13 | 0 | DELIVERED | CLOSE IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754300 | PTIK21S08161 | HDMU6840263 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754300 | PTIK21S08161 | KOCU4239643 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754300 | PTIK21S08161 | KOCU4267286 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754300 | PTIK21S08161 | TGBU6485244 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754301 | PTIK21S08162 | HDMU6711883 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754301 | PTIK21S08162 | KOCU4198539 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-13 | 2 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754301 | PTIK21S08162 | KOCU4949666 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-13 | 2 | 2021-10-13 | 0 | DELIVERED | CLOSED IN CELLO 10/14(DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754301 | PTIK21S08162 | SEGU6033309 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-12 | 1 | 2021-10-18 | 2021-10-14 | 2 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100048 | ONE HAWK | HDMUSELM34754301 | PTIK21S08162 | TCNU7273759 | Q.PEAK DUO XL-G10.3/BFG 480 | 30397272F | 18 | 580 | 20 | 2021-08-11 | 2021-10-11 |  | 2021-10-22 | 2021-09-29 | 2021-10-11 | 0 | 2021-10-15 | 2021-10-14 | 3 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SEAMAX FAIRFIELD | MAEU213047311 | HW2109003 | PONU7842881 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-11 | 2021-10-12 |  | 2021-10-23 | 2021-09-27 | 2021-10-13 | 1 | 2021-10-19 | 2021-10-14 | 1 | 2021-10-14 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | JXLU7848056 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-15 | 0 | 2021-10-21 | 2021-10-18 | 3 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | TEMU7093490 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-15 | 0 | 2021-10-21 | 2021-10-18 | 3 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | TGBU5480510 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-16 | 1 | 2021-10-21 | 2021-10-18 | 2 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | TLLU5887321 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-16 | 1 | 2021-10-21 | 2021-10-18 | 2 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | ZCSU7035143 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-15 | 0 | 2021-10-21 | 2021-10-18 | 3 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | SANTA LORETTA | ZIMUSEL7090068 | PTIK21S09195 | ZCSU8925413 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-10-15 |  | 2021-10-26 | 2021-10-05 | 2021-10-16 | 1 | 2021-10-21 | 2021-10-18 | 2 | 2021-10-18 | 0 | DELIVERED | CLOSED IN CELLO 10/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | COSCO DEVELOPMENT | CMDUSEL1211122 | HW2109015 | CMAU5734450 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-11 | 2021-10-16 |  | 2021-10-27 | 2021-10-04 | 2021-10-16 | 0 | 2021-10-21 | 2021-10-18 | 2 | 2021-10-19 | 1 | DELIVERED | CLOSED IN CELLO 10/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | COSCO DEVELOPMENT | CMDUSEL1211122 | HW2109015 | CMAU7956775 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-11 | 2021-10-16 |  | 2021-10-27 | 2021-10-04 | 2021-10-16 | 0 | 2021-10-21 | 2021-10-18 | 2 | 2021-10-19 | 1 | DELIVERED | CLOSED IN CELLO 10/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | COSCO DEVELOPMENT | CMDUSEL1211122 | HW2109015 | TGBU5081633 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-11 | 2021-10-16 |  | 2021-10-27 | 2021-10-04 | 2021-10-16 | 0 | 2021-10-21 | 2021-10-19 | 3 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | COSCO DEVELOPMENT | EGLV040100364887 | SHTCS2109089 | TRHU5639436 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-11 | 2021-10-16 |  | 2021-10-27 | 2021-10-05 | 2021-10-16 | 0 | 2021-10-25 | 2021-10-19 | 3 | 2021-10-19 | 0 | DELIVERED | CLOSED IN CELLO 10/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | MADRID EXPRESS | YMLUE360788318 | HW2109006 | BMOU6318310 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-13 | 2021-10-19 |  | 2021-10-30 | 2021-10-04 | 2021-10-20 | 1 | 2021-10-29 | 2021-10-21 | 1 | 2021-10-21 | 0 | DELIVERED | CLOSED IN CELLO 10/22 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | MADRID EXPRESS | YMLUE360788318 | HW2109006 | YMMU6291739 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-13 | 2021-10-19 |  | 2021-10-30 | 2021-10-04 | 2021-10-20 | 1 | 2021-10-29 | 2021-10-21 | 1 | 2021-10-22 | 1 | DELIVERED | CLOSED IN CELLO 10/22 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093108 | HW2109048 | DRYU9277426 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-27 | 0 | 2021-10-28 | 1 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093108 | HW2109048 | DRYU9642051 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-26 | 1 | 2021-11-01 | 2021-10-27 | 1 | 2021-10-28 | 1 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093108 | HW2109048 | TCKU6759000 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-26 | 1 | 2021-11-01 | 2021-10-28 | 2 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093108 | HW2109048 | TGHU6277026 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093108 | HW2109048 | ZCSU8501225 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093107 | HW2109047 | ZCSU7270749 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-26 | 1 | 2021-11-01 | 2021-10-28 | 2 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093107 | HW2109047 | ZCSU7311154 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093107 | HW2109047 | ZCSU7388794 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093107 | HW2109047 | ZCSU8604250 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-28 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7093107 | HW2109047 | ZCSU8705569 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-28 | 1 | 2021-10-29 | 1 | DELIVERED | CLOSED IN CELLO 11/03 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7092504 | SHTCS2109193 | FCIU8928583 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-26 | 1 | 2021-11-01 | 2021-10-27 | 1 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7092504 | SHTCS2109193 | TCNU2523325 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-27 | 2 | 2021-11-01 | 2021-10-27 | 0 | 2021-10-28 | 1 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7092504 | SHTCS2109193 | TCNU8395031 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-26 | 1 | 2021-11-01 | 2021-10-27 | 1 | 2021-10-27 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7092504 | SHTCS2109193 | TGBU7162312 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-25 | 0 | 2021-10-29 | 2021-10-26 | 1 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | CEZANNE | ZIMUSEL7092504 | SHTCS2109193 | ZCSU7399910 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-10-25 |  | 2021-11-05 | 2021-10-18 | 2021-10-25 | 0 | 2021-10-29 | 2021-10-26 | 1 | 2021-10-26 | 0 | DELIVERED | CLOSED IN CELLO 10/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | BSIU9216929 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | CAAU5455871 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | TCNU2753082 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-02 | 1 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | TLLU8343316 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | TRHU5479174 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-FNS | 72100054 | ZIM SAN DIEGO | ZIMUSEL7087941 | PTIK21S09198 | ZCSU7537990 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-25 | 2021-10-28 |  | 2021-11-08 | 2021-10-05 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/03 (FNS18) DUKE PROJECT
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | GAOU6104370 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | GAOU6271021 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | MAGU5431962 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-01 | 1 | 2021-11-01 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | TCNU8547432 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-10-29 | 1 | 2021-11-01 | 3 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | TLLU4862099 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-02 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | ZCSU7008894 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-01 | 1 | 2021-11-02 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | ZCSU7409161 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-10-29 | 1 | 2021-11-01 | 3 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | ZCSU7683254 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-03 | 5 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | ZCSU8454191 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-05 | 7 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/15 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093340 | PTIK21S09209 | ZCSU8683731 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-10-29 | 1 | 2021-10-29 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | BSIU9584690 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | JXLU7849350 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | TCNU4555189 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | TGBU5366298 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-09 | 11 | 2021-11-09 | 0 | DELIVERED | CLOSED IN CELLO 11/12 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | TGBU6265580 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-03 | 5 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | ZCSU7124770 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | ZCSU7219747 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-03 | 5 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | ZCSU7281492 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-28 | 0 | 2021-11-03 | 2021-11-03 | 6 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | ZCSU7374255 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-04 | 6 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ZIM SAN DIEGO | ZIMUSEL7093339 | PTIK21S09208 | ZCSU7613597 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-28 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-04 | 6 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/05 DGM18 Duke Charlie Creek Only
GA-DGM | 72100054 | EVER LADEN | CMDUSEL1218742 | HW2109055 | TEMU8340580 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-03 | 5 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/05 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | EVER LADEN | CMDUSEL1218742 | HW2109055 | TCNU4213308 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-10-28 |  | 2021-11-08 | 2021-10-15 | 2021-10-29 | 1 | 2021-11-04 | 2021-11-04 | 6 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/05 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | BMOU4129739 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | CAIU7154571 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | CLKU5000670 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | HDMU6548776 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/10 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | HDMU6819292 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/10 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | KOCU4861934 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | TCNU5131267 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI FORWARD | HDMUSELM74979000 | PTIK21S09206 | TLLU5770314 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-15 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/10 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | BMOU4147795 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | BSIU9263793 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | DFSU6947660 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | HDMU6697825 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | HDMU6716170 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | HMMU6069895 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-03 | 1 | 2021-11-03 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | HMMU6208898 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | KOCU4629580 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-05 | 2 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | KOCU5028922 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-03 | 1 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM55071700 | PTIK21S09204 | KOCU5176149 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-03 | 2 | 2021-11-04 | 1 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | CAAU5044130 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | CAAU5047139 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | CAIU7295728 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | CAIU9844637 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | DFSU7357499 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-02 | 0 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | HMMU6488818 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-03 | 1 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4267882 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-03 | 1 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4409647 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-03 | 1 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4421128 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-03 | 1 | DELIVERED | CLOSED IN CELLO 11/ 15 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4438687 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-02 | 1 | 2021-11-03 | 1 | DELIVERED | CLOSED IN CELLO 11/09 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4676535 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-01 | 1 | 2021-11-04 | 3 | DELIVERED | CLOSED IN CELLO 11/08FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4746503 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | KOCU4769345 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | SEGU5703181 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM30447700 | EGSAV2109074 | TLLU5839745 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-05 | 1 | DELIVERED | CLOSE IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM52241001 | HW2109066 | DRYU9208087 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100070 | HYUNDAI FORWARD | HDMUSELM79291500 | HW2109070 | HDMU6660338 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | HYUNDAI FORWARD | HDMUSELM79291500 | HW2109070 | DFSU6617307 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-05 | 1 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 Duke Charlie Creek Only
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM32298700 | HW2109064 | DRYU9189238 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM32298700 | HW2109064 | HDMU6665685 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-04 | 1 | 2021-11-04 | 0 | DELIVERED | CLOSED IN CELLO 11/08 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM32298700 | HW2109064 | KOCU5072838 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | BSIU9947008 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | CAIU7135925 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-08 | 6 | 2021-11-09 | 1 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | DFSU6940080 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-08 | 6 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | FSCU8503248 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-05 | 3 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | GCXU5020147 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | HMMU6252993 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-08 | 6 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | KOCU4044111 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-08 | 7 | 2021-11-09 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | KOCU4092681 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | KOCU4172262 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI FORWARD | HDMUSELM43383500 | PTIK21S09205 | KOCU4593873 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-05 | 0 | DELIVERED | CLOSED IN CELLO 11/10 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | CAIU7525883 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | CAIU9843266 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-05 | 4 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | GAOU6168040 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-08 | 7 | 2021-11-08 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4166547 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-08 | 7 | 2021-11-09 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSE IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4194472 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-08 | 7 | 2021-11-09 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSE IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4215908 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-10 | 9 | 2021-11-11 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4216571 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-09 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4662450 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-11 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | KOCU4728752 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-02 | 1 | 2021-11-08 | 2021-11-08 | 6 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM91152500 | PTIK21S09201 | TGBU6362450 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-09 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | BSIU9632654 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-09 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/15 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | CAIU7386094 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | DFSU6696076 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | GAOU6364274 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | HMMU6256284 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | HMMU6323870 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | HMMU6333101 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-09 | 8 | 2021-11-10 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | KOCU4175282 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-10 | 9 | 2021-11-10 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | KOCU4515130 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-10 | 9 | 2021-11-10 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100054 | HYUNDAI FORWARD | HDMUSELM64336300 | PTIK21S09200 | KOCU5114907 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-24 | 2021-11-01 |  | 2021-11-12 | 2021-10-05 | 2021-11-01 | 0 | 2021-11-05 | 2021-11-10 | 9 | 2021-11-10 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | BEAU5117229 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | CAIU4416019 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | GAOU6354300 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | JXLU7846583 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | TCNU5402435 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | TCNU8673549 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | TCNU8720872 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | ZCSU7347265 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | ZCSU8762168 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | ZIMUSEL7093231 | PTIK21S09203 | ZCSU8908669 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 DUKE PROJECT
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | SLSU8049179 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | TCKU7334016 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | TCNU6886735 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11 FNS18 DUKE PROJECT
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | TEMU6664173 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-18 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | TGBU5412916 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/15 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | TGBU7217729 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | ZCSU7612292 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | ZCSU8521767 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7094030 | PTIK21S09215 | ZCSU8933384 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | BEAU6305494 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-23 | 18 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | MRKU3102761 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-23 | 18 | 2021-11-29 | 6 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | MRKU3535329 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-23 | 18 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | MRKU4739076 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-23 | 18 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | MRKU4956636 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | MRSU5521543 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-26 | 21 | 2021-11-29 | 3 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | SUDU5907668 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | TCNU2621928 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-24 | 19 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/29 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | TLLU6918181 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-30 | 25 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/04 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ALBERT MAERSK | MAEU213447998 | GLVSKR0006882 | TRHU5636910 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-05 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-30 | 25 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/04 FNS18 DUKE PROJECT
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | BMOU4832485 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/12 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | FSCU8154275 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | FSCU8216778 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | GAOU6080730 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | GCXU5342061 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | SEGU5279598 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | TCNU2303510 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | TCNU2756203 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | TCNU4562146 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093338 | PTIK21S09214 | ZCSU7124831 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | JZPU8019823 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | TGBU7263200 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU7179860 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU7351199 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU7606664 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU7611629 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU7742193 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU8260811 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU8276361 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-15 | 10 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | ALBERT MAERSK | ZIMUSEL7093337 | PTIK21S09213 | ZCSU8537260 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-05 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-12 | 8 | 2021-11-16 | 4 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 FNS18 Duke Charlie Creek Only
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | BMOU4536267 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-05 | 0 | 2021-11-08 | 3 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | BSIU9772044 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | JZPU8019628 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-08 | 3 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | TCNU4296880 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | TCNU4565567 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-08 | 3 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | TGBU7245150 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | ZCSU7025232 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | ZCSU7392840 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | ZCSU7508903 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ALBERT MAERSK | ZIMUSEL7090987 | PTIK21S09199 | ZCSU8611726 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | BHCU4962900 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-08 | 4 | 2021-11-09 | 1 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | BMOU4584223 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-08 | 4 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | FCIU8640576 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | GCXU5072222 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-08 | 4 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | GLDU7420367 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | TCKU6023112 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-08 | 3 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | TCKU6643704 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | TCNU5366214 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-12 | 1 | DELIVERED | CLOSED IN CELLO 11/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | TGBU5759612 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | Gated-out; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093234 | PTIK21S09202 | TGHU6260888 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-28 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | Gated-out; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | BSIU9536115 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-09 | 4 | 2021-11-09 | 0 | DELIVERED | CLOSED IN CELLO 11/12 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | GAOU6459235 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED | CLOSED IN CELLO 11/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | SEGU5191803 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-12 | 2021-11-08 | 4 | 2021-11-08 | 0 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | TCKU7331505 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-12 | 2021-11-08 | 4 | 2021-11-09 | 1 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | TCNU5265190 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-15 | 10 | 2021-11-15 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | TRHU5470238 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-15 | 10 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | ZCSU7157809 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-15 | 10 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | ZCSU7180028 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-15 | 10 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | ZCSU7291844 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-12 | 2021-11-08 | 4 | 2021-11-09 | 1 | DELIVERED | CLOSED IN CELLO 11/11 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | ZIMUSEL7093144 | HW2109067 | ZCSU8808058 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-12 | 2021-11-15 | 10 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | GCXU5673706 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-22 | 17 | 2021-11-29 | 7 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | HASU4008217 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-22 | 17 | 2021-11-23 | 1 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU2748150 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU3448190 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-12-07 | 13 | DELIVERED | HOT CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU4360035 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRSU4719827 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MSKU1796109 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCKU6934401 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCKU7384470 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-24 | 19 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCLU5598254 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCNU2850230 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-24 | 19 | 2021-11-26 | 2 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCNU4045014 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-24 | 19 | 2021-12-03 | 9 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TGHU9721875 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-24 | 19 | 2021-11-29 | 5 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TRHU4389712 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TRHU5637156 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-11-29 | 24 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | HASU4540810 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-29 | 24 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/04 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | HASU5148656 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-30 | 25 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU2155767 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU2750409 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MRKU6434800 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-11-29 | 24 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MSKU0955660 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MSKU0991590 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | MSKU9411250 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-04 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-04 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TCKU6737927 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-12-03 | 28 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ALBERT MAERSK | MAEU213340490 | GLVSKR0006878 | TRHU7446246 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-29 | 2021-11-04 |  | 2021-12-05 | 2021-10-25 | 2021-11-05 | 1 | 2021-12-05 | 2021-12-03 | 28 | 2021-12-06 | 3 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TCNU2304250 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TCNU4762632 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-08 | 4 | 2021-11-11 | 3 | DELIVERED | CLOSED IN CELLO 11/12 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TCNU6544630 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-09 | 4 | 2021-11-10 | 1 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TCNU8545023 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-09 | 4 | 2021-11-09 | 0 | DELIVERED | CLOSED IN CELLO 11/15 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TGBU5491221 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | TLLU4858036 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-09 | 5 | 2021-11-10 | 1 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | ZCSU7268660 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-11 | 6 | 2021-11-11 | 0 | DELIVERED | CLOSED IN CELLO 11/12 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | ZCSU7394354 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | ZCSU8524107 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093233 | PTIK21S09211 | ZCSU8750022 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | BSIU9614970 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-09 | 5 | 2021-11-10 | 1 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | CAXU8015891 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | TCNU4401943 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-10 | 5 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | TEMU7986451 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-10 | 0 | DELIVERED | CLOSED IN CELLO 11/11, DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | TGBU5773061 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-12 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | TGBU7214294 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/15 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | ZCSU7112240 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/12 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | ZCSU7146424 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-10 | 6 | 2021-11-11 | 1 | DELIVERED | CLOSED IN CELLO 11/12 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | ZCSU8650949 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-05 | 1 | 2021-11-11 | 2021-11-12 | 7 | 2021-11-15 | 3 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100070 | ALBERT MAERSK | ZIMUSEL7093235 | PTIK21S09210 | ZCSU8733302 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-04 |  | 2021-11-15 | 2021-10-25 | 2021-11-04 | 0 | 2021-11-10 | 2021-11-11 | 7 | 2021-11-12 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/17 DGM18 Duke Charlie Creek Only
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | CAIU7668164 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | DFSU6940520 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-16 | 8 | 2021-11-16 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | GAOU6170160 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-15 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | GAOU6337432 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-15 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | GAOU6346162 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-16 | 8 | 2021-11-17 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HDMU6657479 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HDMU6765344 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-16 | 8 | 2021-11-17 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/20 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HMMU6110031 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-17 | 9 | 2021-11-17 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HMMU6132175 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-16 | 8 | 2021-11-17 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HMMU6235867 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-16 | 8 | 2021-11-17 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | HMMU6473633 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-17 | 9 | 2021-11-17 | 0 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | KOCU4027140 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | KOCU4267028 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-17 | 9 | 2021-11-23 | 6 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | KOCU5158947 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-15 | 7 | 2021-11-17 | 2 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ANTWERPEN EXPRESS | HDMUSELM29511700 | PTIK21S09190 | SEGU5845144 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-09-12 | 2021-11-08 |  | 2021-11-19 | 2021-10-21 | 2021-11-08 | 0 | 2021-11-12 | 2021-11-17 | 9 | 2021-11-18 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE AND EXCESSIVE # OF CONTAINERS ON SAME VESSEL | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ULSAN EXPRESS | HDMUSELM19718600 | PTIK21S09189 | HDMU6709510 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-27 | 2021-11-09 |  | 2021-11-20 | 2021-10-21 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-16 | 6 | 2021-11-16 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ULSAN EXPRESS | HDMUSELM19718600 | PTIK21S09189 | HMMU6469952 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-27 | 2021-11-09 |  | 2021-11-20 | 2021-10-21 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-15 | 5 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ULSAN EXPRESS | HDMUSELM19718600 | PTIK21S09189 | KOCU4161632 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-27 | 2021-11-09 |  | 2021-11-20 | 2021-10-21 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-15 | 5 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ULSAN EXPRESS | HDMUSELM19718600 | PTIK21S09189 | KOCU4319939 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-27 | 2021-11-09 |  | 2021-11-20 | 2021-10-21 | 2021-11-10 | 1 | 2021-11-16 | 2021-11-15 | 5 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | ULSAN EXPRESS | HDMUSELM19718600 | PTIK21S09189 | TGBU6359610 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-27 | 2021-11-09 |  | 2021-11-20 | 2021-10-21 | 2021-11-09 | 0 | 2021-11-15 | 2021-11-15 | 6 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100070 | BASLE EXPRESS | HDMUPUSM61346600 | HW2109089 | KOCU5163692 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-10-04 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-15 | 1 | 2021-11-19 | 2021-11-16 | 1 | 2021-11-17 | 1 | DELIVERED | CLOSED IN CELLO 11/21 DGM18 Duke Charlie Creek Only
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | BMOU4595531 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-16 | 2 | 2021-11-22 | 2021-11-19 | 3 | 2021-11-19 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | CAIU7366210 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-16 | 2 | 2021-11-22 | 2021-11-19 | 3 | 2021-11-29 | 10 | DELIVERED | CLOSE IN CELLO 11/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | CLKU5001851 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-14 | 0 | 2021-11-18 | 2021-11-15 | 1 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | HDMU6709422 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-17 | 3 | 2021-11-23 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | HMMU6153563 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-14 | 0 | 2021-11-18 | 2021-11-15 | 1 | 2021-11-15 | 0 | DELIVERED | CLOSED IN CELLO 11/18 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | KOCU4389788 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-14 | 0 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-17 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | KOCU4505620 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-16 | 2 | 2021-11-22 | 2021-11-19 | 3 | 2021-11-22 | 3 | DELIVERED | CLOSED IN CELLO 11/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | KOCU5049144 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-16 | 2 | 2021-11-22 | 2021-11-19 | 3 | 2021-11-22 | 3 | DELIVERED | CLOSED IN CELLO 12/04 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | KOCU5107195 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-14 | 0 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100054 | BASLE EXPRESS | HDMUSELM47906200 | PTIK21S09194 | TGBU6356099 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-09-16 | 2021-11-14 |  | 2021-11-25 | 2021-10-28 | 2021-11-14 | 0 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-18 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | NORTHERN JASPER | MAEU213735931 | GLVSKR0007460 | MRKU4840815 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-10-06 | 2021-11-15 |  | 2021-12-15 | 2021-10-28 | 2021-11-15 | 0 | 2021-12-15 | 2021-12-09 | 24 | 2021-12-10 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/13 - DGM18 CUSTOMER EMPIRE VALORIZE
GA-DGM | 72100072 | NORTHERN JASPER | MAEU213735931 | GLVSKR0007460 | MRSU4507129 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-10-06 | 2021-11-15 |  | 2021-12-15 | 2021-10-28 | 2021-11-15 | 0 | 2021-12-15 | 2021-12-09 | 24 | 2021-12-09 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/09 - DGM18 CUSTOMER EMPIRE VALORIZE
GA-DGM | 72100072 | NORTHERN JASPER | MAEU213735931 | GLVSKR0007460 | MRSU5120216 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-10-06 | 2021-11-15 |  | 2021-12-15 | 2021-10-28 | 2021-11-15 | 0 | 2021-12-15 | 2021-12-10 | 25 | 2021-12-10 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/13 - DGM18 CUSTOMER EMPIRE VALORIZE
GA-DGM | 72100072 | NORTHERN JASPER | MAEU213735931 | GLVSKR0007460 | MSKU0994898 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-10-06 | 2021-11-15 |  | 2021-12-15 | 2021-10-28 | 2021-11-15 | 0 | 2021-12-15 | 2021-12-10 | 25 | 2021-12-10 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/13 - DGM18 CUSTOMER EMPIRE VALORIZE
GA-DGM | 72100072 | NORTHERN JASPER | MAEU213735931 | GLVSKR0007460 | TCLU1594163 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-10-06 | 2021-11-15 |  | 2021-12-15 | 2021-10-28 | 2021-11-15 | 0 | 2021-12-15 | 2021-12-10 | 25 | 2021-12-10 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/13 - DGM18 CUSTOMER EMPIRE VALORIZE
GA-DGM | 72100069 | NORTHERN JASPER | ZIMUSEL200235646 | PTIK21S10224 | DRYU9631798 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-15 |  | 2021-11-26 | 2021-10-28 | 2021-11-15 | 0 | 2021-11-19 | 2021-11-19 | 4 | 2021-11-19 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | NORTHERN JASPER | ZIMUSEL200235646 | PTIK21S10224 | GCXU5059621 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-15 |  | 2021-11-26 | 2021-10-28 | 2021-11-15 | 0 | 2021-11-19 | 2021-11-19 | 4 | 2021-11-19 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-FNS | 72100069 | NORTHERN JASPER | ZIMUSEL7095197 | HW2110006 | TGBU7126845 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-12 | 2021-11-15 |  | 2021-11-26 | 2021-10-28 | 2021-11-15 | 0 | 2021-11-19 | 2021-11-19 | 4 | 2021-11-23 | 4 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100069 | NORTHERN JASPER | ZIMUSEL7095197 | HW2110006 | ZCSU7229426 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-12 | 2021-11-15 |  | 2021-11-26 | 2021-10-28 | 2021-11-15 | 0 | 2021-11-19 | 2021-11-19 | 4 | 2021-11-23 | 4 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | BEAU5209201 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-11-30 | 16 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | BEAU5815317 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-11-30 | 16 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/14 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | GCXU5823982 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-01 | 17 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MAGU5191455 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-01 | 17 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MRKU2666561 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-01 | 17 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MRKU4772881 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-07 | 1 | DELIVERED | CLOSED IN CELLO 12/14 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MRSU3606596 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-07 | 23 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/14 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MRSU3940031 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-08 | 2 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MRSU4368609 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-11 | 27 | 2021-12-13 | 2 | DELIVERED | CLOSED IN CELLO 12/14 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | MSKU9331664 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-11 | 27 | 2021-12-14 | 3 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | MAERSK SIRAC | MAEU213763286 | GLVSKR0007532 | TCNU7550658 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-11 | 27 | 2021-12-14 | 3 | DELIVERED | CLOSED IN CELLO 12/14 FNS18 DUKE PROJECT
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | BSIU9541174 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-19 | 3 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | BSIU9715548 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-16 | 2 | 2021-11-19 | 3 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | FCIU9038331 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-15 | 1 | 2021-11-16 | 1 | DELIVERED | CLOSED IN CELLO 11/18 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | TCNU2506375 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-18 | 1 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | TCNU4341274 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-15 | 1 | 2021-11-16 | 1 | DELIVERED | CLOSED IN CELLO 11/18 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | TLLU4735936 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-19 | 2 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | ZCSU7102787 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-19 | 2 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | ZCSU7462361 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | ZCSU8491003 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-19 | 2 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-FNS | 72100070 | MAERSK SIRAC | ZIMUSEL7093230 | PTIK21S09212 | ZCSU8907071 | Q.PEAK DUO L-G6C.2 430 | 30384562F | 18 | 638 | 22 | 2021-09-30 | 2021-11-13 |  | 2021-11-24 | 2021-10-05 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-17 | 3 | 2021-11-19 | 2 | DELIVERED | CLOSED IN CELLO 11/21 FNS18 Duke Charlie Creek Only
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | TCKU6746359 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | FSCU8091557 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-22 | 4 | DELIVERED | CLOSED IN CELLO 11/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | ZCSU7291227 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-22 | 4 | DELIVERED | CLOSED IN CELLO 11/24 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | TCNU5645477 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | TGBU5491324 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | ZCSU7051329 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-18 | 0 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | ZCSU8779129 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-23 | 5 | DELIVERED | CLOSED IN CELLO 11/29 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | CAAU5472708 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | ZCSU8362813 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MAERSK SIRAC | ZIMUSEL7090988 | PTIK21S10222 | ZCSU7223346 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572F | 18 | 580 | 20 | 2021-10-08 | 2021-11-13 |  | 2021-11-24 | 2021-11-08 | 2021-11-14 | 1 | 2021-11-18 | 2021-11-18 | 4 | 2021-11-19 | 1 | DELIVERED | CLOSED IN CELLO 11/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | CAAU6463850 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | CAAU6669688 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | MAGU5455590 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | MRKU3277097 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-08 | 24 | 2021-12-09 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | MSKU1470869 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-06 | 22 | 2021-12-07 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213674907 | GLVSKR0007526 | TRHU7937717 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-08 | 24 | 2021-12-10 | 2 | DELIVERED | HOT CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | CAAU6394913 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-08 | 24 | 2021-12-09 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | MRKU2236370 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-08 | 24 | 2021-12-09 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | MRSU3224248 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-08 | 24 | 2021-12-09 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | MSKU0416185 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-08 | 24 | 2021-12-08 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | MSKU8253968 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-14 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-14 | 2021-12-09 | 25 | 2021-12-09 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MAERSK SIRAC | MAEU213749739 | GLVSKR0007527 | SUDU6950273 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571F | 18 | 580 | 20 | 2021-10-10 | 2021-11-13 |  | 2021-12-13 | 2021-11-04 | 2021-11-14 | 1 | 2021-12-13 | 2021-12-08 | 24 | 2021-12-08 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/15 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | EVER FAITH | EGLV040100482391 | SHTCS2110108 | EMCU9783537 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-21 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-29 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | EVER FAITH | EGLV040100482391 | SHTCS2110108 | TGBU6280835 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-21 | 2021-11-20 |  | 2021-12-01 | 2021-11-11 | 2021-11-20 | 0 | 2021-11-29 | 2021-11-23 | 3 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72100069 | CMA CGM MAGELLAN | CMDUSEL1231453 | TWSC21100266 | APHU7020936 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-10 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-26 | 3 | 2021-12-01 | 2021-11-29 | 3 | 2021-11-29 | 0 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM MAGELLAN | CMDUSEL1231453 | TWSC21100266 | APHU7186378 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-10 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-26 | 3 | 2021-12-02 | 2021-11-29 | 3 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM MAGELLAN | CMDUSEL1231453 | TWSC21100266 | CMAU4946135 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-10 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-25 | 2 | 2021-12-01 | 2021-11-29 | 4 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM MAGELLAN | CMDUSEL1231453 | TWSC21100266 | TCLU5055489 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-10 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-25 | 2 | 2021-12-01 | 2021-11-29 | 4 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-DGM | 72100069 | CMA CGM MAGELLAN | CMDUSEL1231453 | TWSC21100266A | TCNU5538695 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-10 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-24 | 1 | 2021-12-01 | 2021-11-24 | 0 | 2021-11-24 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE PROJECT
GA-DGM | 72100069 | HYUNDAI VICTORY | HDMUSELM90975800 | SDSKSAV706 | CAIU7230497 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-22 | 2021-11-26 |  | 2021-12-07 | 2021-11-08 | 2021-11-27 | 1 | 2021-12-02 | 2021-11-29 | 2 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI VICTORY | HDMUSELM90975800 | SDSKSAV706 | DFSU6675089 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-22 | 2021-11-26 |  | 2021-12-03 | 2021-11-08 | 2021-11-29 | 3 | 2021-12-03 | 2021-11-30 | 1 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI VICTORY | HDMUSELM90975800 | SDSKSAV706 | GCXU5051908 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-22 | 2021-11-26 |  | 2021-12-07 | 2021-11-08 | 2021-11-27 | 1 | 2021-12-02 | 2021-11-29 | 2 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI VICTORY | HDMUSELM90975800 | SDSKSAV706 | HDMU6850488 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-22 | 2021-11-26 |  | 2021-12-07 | 2021-11-08 | 2021-11-27 | 1 | 2021-12-02 | 2021-11-29 | 2 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI VICTORY | HDMUSELM90975800 | SDSKSAV706 | HMMU6098390 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-22 | 2021-11-26 |  | 2021-12-07 | 2021-11-08 | 2021-11-27 | 1 | 2021-12-02 | 2021-11-29 | 2 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100054 | ONE WREN | YMLUE360788194 | HW2109026 | TGCU5035267 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-09-24 | 2021-11-17 |  | 2021-11-28 | 2021-11-04 | 2021-11-17 | 0 | 2021-11-29 | 2021-11-22 | 5 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24, DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | APHU6733531 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24, DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | BEAU4028467 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-30 | 8 | DELIVERED | CLOSED IN CELLO 11/30 DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | CAIU8287162 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24, DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | CMAU4419160 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24, DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | CMAU4912140 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-24 | 2 | DELIVERED | CLOSED IN CELLO 11/30 DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | CMAU5011907 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-24 | 2 | DELIVERED | CLOSED IN CELLO 11/30 DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | CMAU5941729 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-23 | 1 | DELIVERED | CLOSED IN CELLO 11/30 DGM18
GA-DGM | 72101024 | CMA CGM LEO | CMDUAYN0807536 | SDSMY20211003-02 | TRLU8255601 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-11-18 |  | 2021-11-29 | 2021-11-04 | 2021-11-18 | 0 | 2021-11-24 | 2021-11-22 | 4 | 2021-11-22 | 0 | DELIVERED | CLOSED IN CELLO 11/24, DGM18
GA-DGM | 72100070 | HYUNDAI HOPE | HDMUPUSM12329100 | HW2109079 | HMMU6037516 | Q.PEAK DUO L-G6C.2 430 | 30384562C | 15 | 638 | 22 | 2021-10-16 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-19 | 0 | 2021-11-26 | 2021-11-23 | 4 | 2021-11-23 | 0 | DELIVERED | CLOSED IN CELLO 11/29 DGM18 Duke Charlie Creek Only
GA-DGM | 72100069 | HYUNDAI HOPE | YMLUE360787734 | HW2110021 | MAGU5658160 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-16 | 2021-11-19 |  | 2021-11-30 | 2021-11-04 | 2021-11-19 | 0 | 2021-12-01 | 2021-11-23 | 4 | 2021-11-24 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-FNS | 72100069 | ZIM ROTTERDAM | SUDUN1SOL0228161 | TWSC21100558 | SUDU6653980 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-23 | 0 | 2021-12-01 | 2021-11-29 | 6 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ZIM ROTTERDAM | SUDUN1SOL0228161 | TWSC21100558 | MRSU3934445 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-23 |  | 2021-12-04 | 2021-11-04 | 2021-11-24 | 1 | 2021-11-30 | 2021-11-29 | 5 | 2021-11-30 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-DGM | 72100069 | HYUNDAI VICTORY | YMLUE360789152 | HW2110052 | SEGU5250341 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-22 | 2021-11-26 |  | 2021-12-07 | 2021-11-12 | 2021-11-27 | 1 | 2021-12-06 | 2021-12-03 | 6 | 2021-12-06 | 3 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ZIM WILMINGTON | MAEU214102166 | GLVSKR0008709 | MRKU3625649 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-09 | 9 | 2021-12-10 | 1 | DELIVERED | CLOSED IN CELLO 12/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ZIM WILMINGTON | MAEU214102166 | GLVSKR0008709 | MRKU4698526 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-10 | 10 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/13 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ZIM WILMINGTON | MAEU214102166 | GLVSKR0008709 | MRKU5155288 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-10 | 10 | 2021-12-13 | 3 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ZIM WILMINGTON | MAEU214102166 | GLVSKR0008709 | TCKU7262071 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-10 | 10 | 2021-12-13 | 3 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ZIM WILMINGTON | MAEU214102166 | GLVSKR0008709 | TCLU9375156 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-13 | 13 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | RFCU4033780 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-01 | 1 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | TCNU4860840 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-01 | 1 | 2021-12-02 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | TGHU6606970 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-02 | 2 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | TLLU4591130 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-02 | 2 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | TLLU4771825 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-11-30 | 0 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | ZCSU7025079 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-02 | 2 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | ZCSU7117540 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-11-30 | 0 | 2021-12-01 | 1 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | ZCSU7172146 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-01 | 1 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | ZCSU7460179 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-03 | 2021-12-01 | 1 | 2021-12-01 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | ZIMUSEL7093742 | PTIK21S10230 | ZCSU7634840 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-10-21 | 2021-11-29 |  | 2021-12-10 | 2021-11-19 | 2021-11-30 | 1 | 2021-12-06 | 2021-12-06 | 6 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/07 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | FFAU2350572 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-13 | 14 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | HASU4214877 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-13 | 14 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | MRKU5297467 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-17 | 18 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | MRKU6426152 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-20 | 20 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | MRSU5106542 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-20 | 21 | 2021-12-21 | 1 | DELIVERED | CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | MRSU5119175 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-27 | 27 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | MSKU1655137 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-27 | 28 | 2021-12-29 | 2 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | SUDU5682772 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-27 | 27 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | SUDU8883805 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-29 | 2021-11-23 | 2021-11-29 | 0 | 2021-12-29 | 2021-12-27 | 28 | 2021-12-27 | 0 | DELIVERED | CLOSE IN CELLO 12/31 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | MSC BILBAO | MAEU213979148 | GLVSKR0008351 | TRHU5159231 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-26 | 2021-11-29 |  | 2021-12-30 | 2021-11-23 | 2021-11-30 | 1 | 2021-12-30 | 2021-12-27 | 27 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1217189 | HW2110045 | TCLU9747187 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-07 | 2021-11-05 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-03 | 2 | 2021-12-06 | 3 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1217189 | HW2110045 | CMAU4242985 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-07 | 2021-11-05 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-02 | 1 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | OOLU2681665900 | HW2110054 | FFAU3405480 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-09 | 2021-11-05 | 2021-12-01 | 1 | 2021-12-09 | 2021-12-03 | 2 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | OOLU2681665900 | HW2110054 | CSNU6894648 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-09 | 2021-11-05 | 2021-12-01 | 1 | 2021-12-09 | 2021-12-02 | 1 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | OOLU2681665900 | HW2110054 | CSLU6159604 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-09 | 2021-11-05 | 2021-12-01 | 1 | 2021-12-09 | 2021-12-02 | 1 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07 FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1224524 | TWSC21100563 | CMAU5125828 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-18 | 2021-11-30 |  | 2021-12-07 | 2021-11-04 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-03 | 2 | 2021-12-03 | 0 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | OOLU2681672430 | HW2110059 | CCLU7744243 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-10 | 2021-11-05 | 2021-12-02 | 2 | 2021-12-10 | 2021-12-03 | 1 | 2021-12-06 | 3 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | OOLU2681672430 | HW2110059 | FCIU9143297 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-10 | 2021-11-05 | 2021-12-02 | 2 | 2021-12-10 | 2021-12-03 | 1 | 2021-12-06 | 3 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1232253 | TWSC21100562 | CMAU6921711 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-07 | 2021-11-04 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-04 | 3 | 2021-12-07 | 3 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1232253 | TWSC21100562 | CMAU7225071 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-07 | 2021-11-04 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-06 | 5 | 2021-12-06 | 0 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1232253 | TWSC21100562 | TCLU6538476 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-07 | 2021-11-04 | 2021-12-01 | 1 | 2021-12-07 | 2021-12-06 | 5 | 2021-12-07 | 1 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1232253 | TWSC21100562 | TCNU2956583 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-06 | 2021-11-04 | 2021-11-30 | 0 | 2021-12-06 | 2021-12-02 | 2 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-FNS | 72100069 | CMA CGM ARGENTINA | CMDUSEL1232253 | TWSC21100562 | TGHU9149815 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-20 | 2021-11-30 |  | 2021-12-06 | 2021-11-04 | 2021-11-30 | 0 | 2021-12-06 | 2021-12-02 | 2 | 2021-12-03 | 1 | DELIVERED | CLOSED IN CELLO 12/07, FNS18 DUKE PROJECT
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | CAAU5242114 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | CAIU4303476 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | DFOU8031814 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | DFSU6303081 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | GAOU6092089 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-07 | 0 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | TCNU4341823 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | TEMU7824717 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | ZCSU7163123 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | ZCSU7302260 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-07 | 3 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | BREMEN | ZIMUSEL7093743 | PTIK21S11239 | ZCSU7721122 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-03 |  | 2021-12-09 | 2021-11-23 | 2021-12-04 | 1 | 2021-12-09 | 2021-12-08 | 4 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | MEDU7448453 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-07 | 1 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | MSCU5461357 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-07 | 1 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | TCLU5258275 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-07 | 1 | 2021-12-08 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | BMOU5575381 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-08 | 2 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | BMOU5908538 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-08 | 2 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | BSIU9626749 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-08 | 2 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | CRSU9130892 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-08 | 2 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | CXDU2068612 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-08 | 2 | 2021-12-09 | 1 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | FCIU8990949 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | GLDU7408382 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | MEDU4774991 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | MEDU7713325 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | MSDU7435520 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-09 | 0 | DELIVERED | CLOSED IN CELLO 12/09, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | TCNU1267147 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-09 | 3 | 2021-12-10 | 1 | DELIVERED | CLOSED IN CELLO 12/11, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | TCNU8996011 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-10 | 4 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/11, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | TGHU6511957 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-10 | 4 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/11, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | TGHU7307249 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-10 | 4 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/11, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | XINU8158210 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-10 | 4 | 2021-12-10 | 0 | DELIVERED | CLOSED IN CELLO 12/11, FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | CARU9772322 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-11 | 5 | 2021-12-13 | 2 | DELIVERED | CLOSED IN CELLO 12/14 FNS18
GA-FNS | 72101024 | CCNI ANGOL | MEDUP9343195 | PKG0030503 | GLDU7438793 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 660 | 22 | 2021-10-08 | 2021-12-06 |  | 2021-12-13 | 2021-11-04 | 2021-12-06 | 0 | 2021-12-13 | 2021-12-10 | 4 | 2021-12-13 | 3 | DELIVERED | CLOSED IN CELLO 12/14 FNS18
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MRKU2102411 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-13 | 6 | 2021-12-13 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MSKU1147861 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-13 | 6 | 2021-12-13 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MSKU1971921 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MSKU8919057 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-16 | 9 | 2021-12-17 | 1 | DELIVERED | HOT - CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MSKU9137622 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-17 | 10 | 2021-12-17 | 0 | DELIVERED | HOT - CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | MSKU9566519 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-28 | 21 | 2021-12-28 | 0 | DELIVERED | CLOSE IN CELLO 12/31 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | PONU8243949 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2022-01-04 | 28 | 2022-01-13 | 9 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | SUDU6622314 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2022-01-05 | 29 | 2022-01-13 | 8 | DELIVERED | CLOSE IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | TIANJIN | MAEU214254541 | GLVSKR0009162 | TRHU4339814 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-10-31 | 2021-12-07 |  | 2021-12-18 | 2021-11-23 | 2021-12-07 | 0 | 2022-01-06 | 2022-01-05 | 29 | 2022-01-13 | 8 | DELIVERED | CLOSE IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ARTHUR MAERSK | MAEU214345004 | GLVSKR0009454 | CLHU8644249 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-18 | 2021-12-02 | 2021-12-08 | 1 | 2022-01-07 | 2021-12-17 | 9 | 2021-12-20 | 3 | DELIVERED | HOT CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ARTHUR MAERSK | MAEU214345004 | GLVSKR0009454 | MRKU3086491 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-18 | 2021-12-02 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-17 | 10 | 2021-12-17 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ARTHUR MAERSK | MAEU214345004 | GLVSKR0009454 | MRSU3731638 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-18 | 2021-12-02 | 2021-12-07 | 0 | 2022-01-06 | 2021-12-17 | 10 | 2021-12-17 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ARTHUR MAERSK | MAEU214345004 | GLVSKR0009454 | TRHU4149901 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-18 | 2021-12-02 | 2021-12-08 | 1 | 2022-01-07 | 2021-12-17 | 9 | 2021-12-17 | 0 | DELIVERED | HOT CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRKU6281510 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-10 | 3 | 2021-12-13 | 3 | DELIVERED | HOT CLOSED IN CELLO 12/14; 12/15 - FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRKU6374125 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/16 - FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU1501960 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/16 - FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU8394816 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-10 | 3 | 2021-12-13 | 3 | DELIVERED | HOT CLOSED IN CELLO 12/14; 12/15 - FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | TCLU5070884 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | HOT CLOSED IN CELLO 12/16 - FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | HASU4097425 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | HASU5042387 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRKU3140437 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRKU4360740 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRSU3073840 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRSU3516240 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRSU3705259 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MRSU4214033 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU0477154 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU1869036 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU9134855 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MSKU9210132 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | MVIU0025426 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | PONU8124240 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | PONU8133242 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-15 | 8 | 2021-12-16 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | SUDU6956841 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-13 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED; DEMURRAGE INCURRED DUE TO PORT CONGESTION/CHASSIS SHORTAGE | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | TCNU6663731 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | TRHU4003938 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-14 | 2021-11-19 | 2021-12-08 | 1 | 2021-12-14 | 2021-12-14 | 6 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | ARTHUR MAERSK | MAEU214224573 | SDSKSAV711 | TRLU8070212 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-06 | 2021-12-07 |  | 2021-12-13 | 2021-11-19 | 2021-12-07 | 0 | 2021-12-13 | 2021-12-13 | 6 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/15 FNS18 DUKE PROJECT
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | CAIU7235781 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-13 | 3 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | CAIU9931433 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-13 | 3 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | CAIU9972469 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | GAOU6171146 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | HMMU6200006 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | HMMU6267632 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | KOCU4304311 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | KOCU4770259 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-16 | 2 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | KOCU4955463 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | KOCU4971660 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | TCNU7408601 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUSELM83156001 | SDSKSAV702 | TGBU6487735 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-14 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | CAIU7687842 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | DFSU6616126 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-17 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-20 | 6 | DELIVERED | CLOSED IN CELLO 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | GAOU6372979 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-14 | 4 | 2021-12-15 | 1 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | HMMU6063963 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-16 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | HMMU6077329 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | HMMU6309701 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | KOCU4114203 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | KOCU4255310 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | KOCU4378891 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | KOCU4848763 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-15 | 0 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | KOCU5030597 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-15 | 5 | 2021-12-16 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100072 | YM WARRANTY | HDMUSELM83156000 | SDSKSAV701 | TCNU7402060 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 435 | 15 | 2021-10-16 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUPUSM78990000 | HW2110030 | BMOU4141626 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 377 | 13 | 2021-10-18 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUPUSM78990000 | HW2110030 | DFSU6480826 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 377 | 13 | 2021-10-18 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUPUSM78990000 | HW2110030 | KOCU4249596 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 377 | 13 | 2021-10-18 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-20 | 4 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUPUSM78990000 | HW2110030 | TCNU7038750 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 377 | 13 | 2021-10-18 | 2021-12-09 |  | 2021-12-15 | 2021-12-02 | 2021-12-09 | 0 | 2021-12-15 | 2021-12-13 | 4 | 2021-12-14 | 1 | DELIVERED | CLOSED IN CELLO 12/16 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | YM WARRANTY | HDMUPUSM78990000 | HW2110030 | TCNU7455202 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 377 | 13 | 2021-10-18 | 2021-12-09 |  | 2021-12-16 | 2021-12-02 | 2021-12-10 | 1 | 2021-12-16 | 2021-12-16 | 6 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ONE APUS | HLCUSEL210959326 | HW2110075 | HLXU8345361 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-12-12 |  | 2021-12-17 | 2021-12-09 | 2021-12-12 | 0 | 2021-12-17 | 2021-12-13 | 1 | 2021-12-13 | 0 | DELIVERED | CLOSED IN CELLO 12/14 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM57025600 | HW2110076 | KOCU4262284 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM57025600 | HW2110076 | HMMU6029017 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-12-12 |  | 2021-12-17 | 2021-12-02 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM57025600 | HW2110076 | KOCU4607811 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-12-12 |  | 2021-12-17 | 2021-12-02 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-20 | 4 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72101024 | ONE APUS | HDMUSELM03584101 | SHTCS2110141 | CAIU7371622 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-24 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | CAIU7229032 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | CAIU7446064 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | HDMU6818510 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | HMMU6072878 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/20, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | KOCU4226585 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | KOCU4886589 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100069 | ONE APUS | HDMUSELM61193800 | SDSKSAV704 | KOCU4893926 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 435 | 15 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-12-02 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | BMOU5168072 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | GAOU6163639 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-14 | 2 | 2021-12-20 | 2021-12-17 | 3 | 2021-12-21 | 4 | DELIVERED | CLOSED IN CELLO ON 12/22, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6574559 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6747593 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-11-04 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-15 | 3 | 2021-12-16 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6789670 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6818716 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6834506 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-17 | 4 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HDMU6868949 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HMMU6028197 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-11-04 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-15 | 3 | 2021-12-16 | 1 | DELIVERED | CLOSED IN CELLO 12/16 FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HMMU6056481 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-23 | 2021-11-04 | 2021-12-14 | 2 | 2021-12-20 | 2021-12-17 | 3 | 2021-12-21 | 4 | DELIVERED | CLOSED IN CELLO ON 12/22, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HMMU6075780 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-14 | 2 | 2021-12-20 | 2021-12-17 | 3 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO ON 12/21, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HMMU6332595 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/19, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | HMMU6366450 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-17 | 4 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO ON 12/21, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | KOCU4873410 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-16 | 2021-11-04 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-20 | 4 | DELIVERED | CLOSED IN CELLO ON 12/21, FNS18 DUKE PROJECT
GA-FNS | 72100069 | HYUNDAI DRIVE | HDMUSELM29924500 | PTIK21S10228 | KOCU5219528 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-12 |  | 2021-12-17 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-17 | 4 | 2021-12-21 | 4 | DELIVERED | CLOSED IN CELLO ON 12/22, FNS18 DUKE PROJECT
GA-DGM | 72100069 | HYUNDAI DRIVE | YMLUE360787627 | HW2111021 | YMMU6058985 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-12 |  | 2021-12-22 | 2021-12-07 | 2021-12-13 | 1 | 2021-12-22 | 2021-12-17 | 4 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI DRIVE | ONEYSELBC8573300 | SHTCS2111046 | TLLU5702480 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-12 |  | 2021-12-16 | 2021-12-07 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-16 | 0 | DELIVERED | CLOSED IN CELLO ON 12/19 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI DRIVE | ONEYSELBC8570700 | SHTCS2111045 | TCLU7800507 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-12 |  | 2021-12-16 | 2021-12-07 | 2021-12-12 | 0 | 2021-12-16 | 2021-12-16 | 4 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/21, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | HYUNDAI DRIVE | HDMUSELM08003400 | SDSKSAV716 | TLLU5291939 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-12 |  | 2021-12-17 | 2021-12-07 | 2021-12-13 | 1 | 2021-12-17 | 2021-12-16 | 3 | 2021-12-17 | 1 | DELIVERED | CLOSED IN CELLO ON 12/21, (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CARU9656805 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 90 | 3 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CARU9656805 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 510 | 18 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001556189(4 PCS) / 100000001558168(26 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CARU9656805 | Q.PEAK DUO L-G8.2 420 | 12005805C | 15 | 60 | 3 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001562225 (3 PCS) / 100000001562226 (27 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CAIU4403578 | Q.PEAK DUO L-G8.2 420 | 12005805C | 15 | 2 | 1 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001562405 (2 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CAIU4403578 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 18 | 1 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001562403 (18 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CAIU4403578 | Q.PEAK DUO L-G8.2 430 | 12005803C | 15 | 309 | 13 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001560307(3 PCS) / 100000001562404 (6 PCS) / 100000001562228(8 PCS) / 100000001562229 (22 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CAIU4403578 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 39 | 2 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO 12/23 FNS18 (100000001553496 (9 PCS))
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | MEDU7414406 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 300 | 10 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-17 | 4 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO 12/23 FNS18
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | MEDU7414406 | Q.PEAK DUO L-G8.2 435 | 12005802C | 15 | 360 | 12 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-17 | 4 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO 12/23 FNS18
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | FFAU2395134 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 660 | 22 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-18 | 5 | 2021-12-21 | 3 | DELIVERED | CLOSED IN CELLO ON 12/21, FNS18
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | CAIU7722666 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 660 | 22 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-18 | 5 | 2021-12-21 | 3 | DELIVERED | CLOSED IN CELLO 12/23 FNS18
GA-FNS | 72101024 | CSAV TOCONAO | MEDUP9350497 | PKG0030576 | TCNU7725437 | Q.PEAK DUO L-G8.2 425 | 12005804C | 15 | 660 | 22 | 2021-10-15 | 2021-12-12 |  | 2021-12-20 | 2021-11-04 | 2021-12-13 | 1 | 2021-12-20 | 2021-12-20 | 7 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21, FNS18
GA-DGM | 72100069 | APL SOUTHAMPTON | CMDUSEL1232309 | EXKR21100020 | SEGU4784379 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-14 |  | 2021-12-25 | 2021-12-06 | 2021-12-16 | 2 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-20 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | APL SOUTHAMPTON | CMDUSEL1232309 | EXKR21100020 | TCKU6334789 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-14 |  | 2021-12-25 | 2021-12-06 | 2021-12-16 | 2 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO ON 12/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | APL SOUTHAMPTON | CMDUSEL1232309 | EXKR21100020 | SEGU4621828 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-14 |  | 2021-12-25 | 2021-12-06 | 2021-12-16 | 2 | 2021-12-21 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSED IN CELLO ON 12/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100069 | APL SOUTHAMPTON | CMDUSEL1232309 | EXKR21100020 | APHU6792196 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-10-19 | 2021-12-14 |  | 2021-12-25 | 2021-12-06 | 2021-12-16 | 2 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-20 | 3 | DELIVERED | CLOSED IN CELLO ON 12/21 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 480 PW
GA-DGM | 72100082 | APL SOUTHAMPTON | COSU6315635350 | HW2111017 | OOCU8227120 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-14 |  | 2021-12-25 | 2021-12-08 | 2021-12-16 | 2 | 2021-12-23 | 2021-12-20 | 4 | 2021-12-21 | 1 | DELIVERED | HOT - CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ZIM ANTWERP | MAEU214401131 | GLVSKR0009689 | GCXU5528230 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-10 | 2021-12-14 |  | 2022-01-13 | 2021-12-07 | 2021-12-14 | 0 | 2022-01-13 | 2022-01-10 | 27 | 2022-01-11 | 1 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM ANTWERP | MAEU214401131 | GLVSKR0009689 | MRSU4572675 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-10 | 2021-12-14 |  | 2022-01-13 | 2021-12-07 | 2021-12-14 | 0 | 2022-01-13 | 2022-01-11 | 28 | 2022-01-14 | 3 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM ANTWERP | MAEU214401131 | GLVSKR0009689 | MSKU1727432 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-10 | 2021-12-14 |  | 2022-01-14 | 2021-12-07 | 2021-12-15 | 1 | 2022-01-14 | 2022-01-11 | 27 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM ANTWERP | MAEU214401131 | GLVSKR0009689 | TCKU7691923 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-10 | 2021-12-14 |  | 2022-01-13 | 2021-12-07 | 2021-12-14 | 0 | 2022-01-13 | 2022-01-11 | 28 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM ANTWERP | MAEU214401131 | GLVSKR0009689 | TCKU9837196 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-10 | 2021-12-14 |  | 2022-01-14 | 2021-12-07 | 2021-12-15 | 1 | 2022-01-14 | 2022-01-11 | 27 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM ANTWERP | ZIMUSEL7099372 | HW2111032 | TCNU8898400 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-14 |  | 2021-12-20 | 2021-12-07 | 2021-12-14 | 0 | 2021-12-20 | 2021-12-20 | 6 | 2021-12-20 | 0 | DELIVERED | HOT - CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ZIM ANTWERP | ZIMUSEL7099569 | HW2111033 | TCNU2526113 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-14 |  | 2021-12-21 | 2021-12-07 | 2021-12-15 | 1 | 2021-12-21 | 2021-12-20 | 5 | 2021-12-20 | 0 | DELIVERED | HOT - CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ZIM ANTWERP | ZIMUSEL7099699 | HW2111035 | ZCSU7255580 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-14 |  | 2021-12-21 | 2021-12-07 | 2021-12-15 | 1 | 2021-12-21 | 2021-12-20 | 5 | 2021-12-21 | 1 | DELIVERED | HOT - CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | ZIM ANTWERP | ZIMUSEL7099699 | HW2111035 | BEAU5150844 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-14 |  | 2021-12-20 | 2021-12-07 | 2021-12-14 | 0 | 2021-12-20 | 2021-12-20 | 6 | 2021-12-20 | 0 | DELIVERED | HOT - CLOSED IN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN) 475 PW
GA-DGM | 72100082 | HYUNDAI RESPECT | HDMUPUSM46012200 | HW2111039 | CLKU5003140 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-12 | 2021-12-15 |  | 2021-12-22 | 2021-12-07 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-17 | 0 | DELIVERED | CLOSEDIN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | HYUNDAI RESPECT | HDMUPUSM08938700 | HW2111041 | TCKU6101220 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-12 | 2021-12-15 |  | 2021-12-22 | 2021-12-07 | 2021-12-16 | 1 | 2021-12-22 | 2021-12-17 | 1 | 2021-12-20 | 3 | DELIVERED | CLOSEDIN CELLO ON 12/23 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7096772 | PTIK21S11249 | GAOU6081593 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-22 | 2021-12-13 | 2021-12-16 | 0 | 2021-12-22 | 2021-12-20 | 4 | 2021-12-21 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, AGAIN DUE TO TARIFF (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | ZIM TAMPA | ZIMUSEL7099110 | HW2111051 | TCNU2299811 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | ZIM TAMPA | ZIMUSEL7099110 | HW2111051 | JZPU8023340 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-29 | 6 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100069 | ZIM TAMPA | ZIMUSEL7099110 | HW2111051 | ZCSU7371180 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-23 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, AGAIN DUE TO TARIFF (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | CRSU9049097 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | JXLU7828609 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-22 | 2021-12-14 | 2021-12-16 | 0 | 2021-12-22 | 2021-12-21 | 5 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, AGAIN DUE TO TARIFF (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU7030120 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU7727753 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-22 | 2021-12-14 | 2021-12-16 | 0 | 2021-12-22 | 2021-12-21 | 5 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, AGAIN DUE TO TARIFF (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8244370 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8257000 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8417813 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-27 | 10 | 2021-12-28 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8452671 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8538857 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-22 | 2021-12-14 | 2021-12-16 | 0 | 2021-12-22 | 2021-12-21 | 5 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, AGAIN DUE TO TARIFF (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | ZIMUSEL7100533 | HW2111059 | ZCSU8920068 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-11-18 | 2021-12-16 |  | 2021-12-27 | 2021-12-14 | 2021-12-17 | 1 | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | GESU5474624 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-15 | 2022-01-12 | 26 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU2006336 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-12 | 26 | 2022-01-13 | 1 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU2827060 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-13 | 27 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU4218817 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-11 | 25 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU5748410 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-12 | 27 | 2022-01-12 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU5957827 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-12 | 27 | 2022-01-13 | 1 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU5977438 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-15 | 2022-01-12 | 26 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRKU6166142 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-13 | 28 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRSU3949229 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-13 | 27 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MRSU4525626 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-13 | 28 | 2022-01-18 | 5 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | MSKU8352209 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-13 | 28 | 2022-01-17 | 4 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | SUDU6550739 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-13 | 27 | 2022-01-13 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | SUDU6892829 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-13 | 27 | 2022-01-14 | 1 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | SUDU8712905 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-13 | 27 | 2022-01-14 | 1 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TCLU5705028 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-14 | 28 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TCNU2055564 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-15 | 2022-01-14 | 28 | 2022-01-17 | 3 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TCNU8224213 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-16 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-16 | 2022-01-14 | 28 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TLLU5967089 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-14 | 29 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TLLU5989581 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-17 | 1 | 2022-01-15 | 2022-01-14 | 28 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM TAMPA | MAEU214624351 | GLVSKR0010406 | TRHU5168130 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-18 | 2021-12-16 |  | 2022-01-15 | 2021-12-13 | 2021-12-16 | 0 | 2022-01-15 | 2022-01-14 | 29 | 2022-01-14 | 0 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM22220800 | HW2111015 | BMOU4165058 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-04 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM22220800 | HW2111015 | HMMU6114063 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-04 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | SHANGHAI EXPRESS | YMLUE360789768 | HW2110074 | YMMU6020296 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-04 | 2021-12-17 |  | 2021-12-27 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-27 | 2021-12-21 | 4 | 2021-12-21 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | HDMU6385473 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | HDMU6847308 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | HDMU6863103 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | HMMU6112097 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | HMMU6471733 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | KOCU4188119 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-21 | 4 | 2021-12-22 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | KOCU4468254 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | TCNU6333365 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-27 | 5 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | TGBU6342752 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM92762700 | PTIK21S11241 | TLLU5775912 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM19467400 | PTIK21S11240 | CLKU5017971 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-22 | 0 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM19467400 | PTIK21S11240 | HDMU6712426 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM19467400 | PTIK21S11240 | KOCU4495455 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-23 | 6 | 2021-12-27 | 4 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM19467400 | PTIK21S11240 | KOCU4848948 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100072 | SHANGHAI EXPRESS | HDMUSELM19467400 | PTIK21S11240 | SEGU6039499 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-11-03 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | SHANGHAI EXPRESS | HLCUSEL2109ASQH6 | TWSC21110103 | HLBU3368135 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-17 |  | 2021-12-27 | 2021-12-13 | 2021-12-18 | 1 | 2021-12-27 | 2021-12-27 | 9 | 2021-12-28 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | SHANGHAI EXPRESS | HLCUSEL2109ASQH6 | TWSC21110103 | HLBU1976748 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-17 |  | 2021-12-27 | 2021-12-13 | 2021-12-18 | 1 | 2021-12-27 | 2021-12-27 | 9 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | SHANGHAI EXPRESS | HLCUSEL2109ASQH6 | TWSC21110103 | HLXU8324754 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-02 | 2021-12-17 |  | 2021-12-27 | 2021-12-13 | 2021-12-17 | 0 | 2021-12-27 | 2021-12-27 | 10 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | SHANGHAI EXPRESS | HLCUSEL211078376 | HW2111013 | UACU5808663 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-04 | 2021-12-17 |  | 2021-12-27 | 2021-12-13 | 2021-12-18 | 1 | 2021-12-27 | 2021-12-27 | 9 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | SHANGHAI EXPRESS | HDMUSELM41148202 | HW2111014 | HDMU6651017 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-04 | 2021-12-17 |  | 2021-12-23 | 2021-12-08 | 2021-12-17 | 0 | 2021-12-23 | 2021-12-22 | 5 | 2021-12-23 | 1 | DELIVERED | CLOSED IN CELLO 12/28 (DGM18) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | EVER FORE | EGLV040100483380 | PTIK21S11238 | TRHU6218067 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-23 | 3 | 2021-12-29 | 2021-12-27 | 4 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | EVER FORE | EGLV040100483380 | PTIK21S11238 | EISU9352321 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-21 | 1 | 2021-12-29 | 2021-12-27 | 6 | 2021-12-29 | 2 | DELIVERED | CLOSE IN CELLO ON 01/12 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100069 | EVER FORE | EGLV040100483380 | PTIK21S11238 | GAOU6158951 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-07 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-21 | 1 | 2021-12-29 | 2021-12-27 | 6 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | EVER FORE | EGLV040100576566 | PTIK21S11243 | BMOU5135700 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-23 | 3 | 2021-12-29 | 2021-12-27 | 4 | 2021-12-29 | 2 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | EVER FORE | EGLV040100576566 | PTIK21S11243 | EGHU9216138 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-21 | 1 | 2021-12-29 | 2021-12-28 | 7 | 2021-12-29 | 1 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | EVER FORE | EGLV040100576566 | PTIK21S11243 | EISU9259883 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-21 | 1 | 2021-12-29 | 2021-12-28 | 7 | 2021-12-29 | 1 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | EVER FORE | EGLV040100576566 | PTIK21S11243 | TGBU6960811 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-11 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-23 | 3 | 2021-12-29 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100069 | EVER FORE | EGLV040100482421 | SHTCS2111025 | EGHU9098436 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-12 | 2021-12-20 |  | 2021-12-31 | 2021-12-13 | 2021-12-23 | 3 | 2021-12-29 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-FNS | 72100082 | NEW YORK EXPRESS | HDMUSELM42969600 | PTIK21S11246 | KOCU4747855 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-15 | 2021-12-22 |  | 2022-01-02 | 2021-11-04 | 2021-12-23 | 1 | 2021-12-29 | 2021-12-24 | 1 | 2021-12-27 | 3 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | NEW YORK EXPRESS | HDMUSELM42969600 | PTIK21S11246 | TCNU8415821 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-15 | 2021-12-22 |  | 2022-01-02 | 2021-11-04 | 2021-12-23 | 1 | 2021-12-29 | 2021-12-27 | 4 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | BEAU5054558 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | BMOU4783729 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-28 | 4 | 2021-12-29 | 1 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | BSIU9215856 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | GAOU6043335 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-28 | 4 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | GAOU6047639 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | JXLU6638517 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | JXLU7804680 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | JZPU8012855 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | MAGU5169805 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-28 | 5 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TCKU6764075 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TCNU4344519 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-28 | 4 | 2021-12-29 | 1 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TCNU4767423 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-28 | 4 | 2021-12-29 | 1 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TEMU6747935 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TEMU6931618 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGBU5368069 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGBU7195912 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGBU7208178 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGBU7235825 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGBU7263299 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-30 | 2 | DELIVERED | CLOSED IN CELLO 01/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGHU6434510 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TGHU9662577 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU4442394 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU4858000 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-30 | 4 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU4951642 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU5306772 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU5796999 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TLLU8113139 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TRHU5473330 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2022-01-03 | 5 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | TRHU8310207 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2022-01-03 | 5 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU6543638 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/11 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7065066 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7187927 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7221723 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2022-01-03 | 5 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7226896 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7281851 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-30 | 4 | 2022-01-07 | 8 | DELIVERED | CLOSED IN CELLO 01/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7667417 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2022-01-03 | 5 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7727054 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-30 | 4 | 2022-01-07 | 8 | DELIVERED | CLOSED IN CELLO 01/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU7743179 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-07 | 8 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU8647170 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU8724229 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO 01/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU8731399 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU8860776 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-30 | 7 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101767 | GLVSKR0010685 | ZCSU8959075 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-11-22 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-07 | 8 | DELIVERED | CLOSED IN CELLO 01/24 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | FSCU8095151 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | SEGU5427993 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | TCNU5355924 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | TEMU6796230 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | TEMU7421413 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | TGBU7246286 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU6536618 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU7321569 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU7378116 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU7425218 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU7790972 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU8533367 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-29 | 5 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU8562318 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU8692923 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-23 | 0 | 2021-12-30 | 2021-12-29 | 6 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO 01/14 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7101800 | HW2111082 | ZCSU8741118 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2021-12-30 | 0 | DELIVERED | CLOSED IN CELLO 01/13 (DGM15) DUKE (BAY TRAIL/FORT GREEN) (WILL ADD IN JAN BILLING)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL200237118 | PTIK21S11254 | JXLU8656274 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-24 | 1 | 2021-12-30 | 2021-12-30 | 6 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL200237118 | PTIK21S11254 | TGBU5499259 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-30 | 4 | 2022-01-03 | 4 | DELIVERED | CLOSED IN CELLO ON 01/06 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM CHARLESTON | ZIMUSEL7100427 | HW2111077 | ZCSU7074514 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-23 |  | 2022-01-03 | 2021-12-16 | 2021-12-26 | 3 | 2021-12-30 | 2021-12-30 | 4 | 2022-01-07 | 8 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-FNS | 72100082 | ZIM CHARLESTON | MAEU214548555 | GLVSKR0010074 | MSKU8396613 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-15 | 2021-12-23 |  | 2022-01-03 | 11/4/2021; 12/13/2021 | 2021-12-23 | 0 | 2022-01-22 | 2021-12-24 | 1 | 2021-12-27 | 3 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | ZIM CHARLESTON | MAEU214548555 | GLVSKR0010074 | MSKU9584317 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-15 | 2021-12-23 |  | 2022-01-03 | 11/4/2021; 12/13/2021 | 2021-12-26 | 3 | 2022-01-25 | 2021-12-27 | 1 | 2021-12-27 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | ZIM CHARLESTON | MAEU214548555 | GLVSKR0010074 | TCNU8516128 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-15 | 2021-12-23 |  | 2022-01-03 | 11/4/2021; 12/13/2021 | 2021-12-23 | 0 | 2022-01-22 | 2021-12-24 | 1 | 2021-12-27 | 3 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | BSIU9310283 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | CAIU4482577 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | DFSU6214940 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | HMMU6230211 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | HMMU6433190 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-27 | 1 | 2021-12-31 | 2021-12-29 | 2 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | HMMU6494805 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | KOCU4528482 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | KOCU4748743 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | TGBU6156763 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM28267500 | PTIK21S11247 | TRLU7145127 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-21 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-29 | 3 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM96328700 | PTIK21S11252 | TCNU6876697 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-27 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-27 | 1 | 2021-12-31 | 2021-12-29 | 2 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM96328700 | PTIK21S11252 | KOCU4752131 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 580 | 20 | 2021-11-27 | 2021-12-26 |  | 2022-01-06 | 11/4/2021; 12/17/2021 | 2021-12-27 | 1 | 2021-12-31 | 2021-12-29 | 2 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM75776000 | KIMXSAV2111009S | HMMU6438735 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-26 | 2021-12-26 |  | 2022-01-06 | 2021-12-13 | 2021-12-28 | 2 | 2022-01-03 | 2021-12-29 | 1 | 2021-12-29 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM75776000 | KIMXSAV2111009S | TCKU6109366 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-26 | 2021-12-26 |  | 2022-01-06 | 2021-12-13 | 2021-12-27 | 1 | 2021-12-31 | 2021-12-29 | 2 | 2021-12-30 | 1 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM75776000 | KIMXSAV2111009S | TCNU7409629 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-26 | 2021-12-26 |  | 2022-01-06 | 2021-12-13 | 2021-12-27 | 1 | 2021-12-31 | 2021-12-28 | 1 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100082 | HYUNDAI DREAM | HDMUSELM75776000 | KIMXSAV2111009S | KOCU4469630 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-26 | 2021-12-26 |  | 2022-01-06 | 2021-12-13 | 2021-12-26 | 0 | 2021-12-30 | 2021-12-28 | 2 | 2021-12-28 | 0 | DELIVERED | CLOSED IN CELLO ON 12/30, FNS15 DUKE PROJECT
GA-FNS | 72100096 | EVER FIT | EGLV040100609367 | PTIK21S11258 | TCKU6104718 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 162 | 6 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-27 | 0 | 2022-01-04 | 2021-12-30 | 3 | 2021-12-30 | 0 | DELIVERED | CLOSED IN CELLO 12/31 FNS15 DUKE PROJECT (211118_J3_GXLN1D_475A_702 - 17 pcs)
GA-FNS | 72100096 | EVER FIT | EGLV040100609367 | PTIK21S11258 | TCKU6104718 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 162 | 6 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-27 | 0 | 2022-01-04 | 2021-12-30 | 3 | 2021-12-30 | 0 | DELIVERED | CLOSED IN CELLO 12/31 FNS15 DUKE PROJECT (211118_J3_GXLN1D_480A_702 - 17 pcs)
GA-FNS | 72100072 | EVER FIT | EGLV040100538036 | PTIK21S11257 | EGHU9703732 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 12/31 , FNS15 DUKE PROJECT
GA-FNS | 72100072 | EVER FIT | EGLV040100538036 | PTIK21S11257 | TCLU9325026 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 12/31 , FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100538028 | PTIK21S11259 | EISU9404235 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 12/31 , FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100538028 | PTIK21S11259 | FCIU9322688 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 12/31 , FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100538028 | PTIK21S11259 | TCLU4956034 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-30 | 2 | 2021-12-30 | 0 | DELIVERED | CLOSE IN CELLO 12/31 , FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100538028 | PTIK21S11259 | TCNU3747280 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-31 | 3 | 2022-01-03 | 3 | DELIVERED | CLOSED IN CELLO 01/04 FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100538028 | PTIK21S11259 | TXGU5777199 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-31 | 3 | 2022-01-03 | 3 | DELIVERED | CLOSED IN CELLO 01/04 FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FIT | EGLV040100531376 | SHTCS2112003 | EITU1027720 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2022-01-03 | 6 | 2022-01-04 | 1 | DELIVERED | CLOSED IN CELLO 01/07 FNS15 DUKE PROJECT (Container was under intensive customs exam, released on 12/30)
GA-FNS | 72100082 | EVER FIT | EGLV040100571921 | SHTCS2112002 | EGHU9289221 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2021-12-27 |  | 2022-01-04 | 12/13/21; 12/23/21 | 2021-12-28 | 1 | 2022-01-04 | 2021-12-31 | 3 | 2022-01-03 | 3 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL200237289 | PTIK21S12261 | TLLU4589507 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-10 | 5 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL200237289 | PTIK21S12261 | ZCSU7970779 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-11 | 6 | DELIVERED | CLOSED IN CELLO ON 01/12, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL200237289 | PTIK21S12261 | GAOU6460180 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-10 | 5 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7101421 | HW2111098 | BSIU9767900 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-04 | 0 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | BSIU9701800 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | TCNU4257610 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | TCNU5832689 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | TEMU7990488 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-06 | 1 | DELIVERED | CLOSED IN CELLO ON 01/07, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | TGBU5973202 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-04 | 6 | 2022-01-06 | 2 | DELIVERED | CLOSED IN CELLO ON 01/07, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | TGCU5079476 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-10 | 5 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | ZCSU7200000 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-06 | 12/13/2021; 12/21/21 | 2021-12-30 | 1 | 2022-01-06 | 2022-01-05 | 6 | 2022-01-07 | 2 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | ZCSU7628616 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-07 | 2 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | ZCSU7727630 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-07 | 2 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-FNS | 72100082 | SANTA LORETTA | ZIMUSEL7102351 | SHTCS2112004 | ZCSU7961910 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372C | 15 | 580 | 20 | 2021-12-01 | 2021-12-29 |  | 2022-01-05 | 12/13/2021; 12/21/21 | 2021-12-29 | 0 | 2022-01-05 | 2022-01-05 | 7 | 2022-01-10 | 5 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-DGM | 72100082 | CORNELIA MAERSK | ZIMUSEL7100250 | HW2111069 | TCNU8111264 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-30 |  | 2022-01-06 | 2021-12-20 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-05 | 3 | 2022-01-05 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | CORNELIA MAERSK | ZIMUSEL7100250 | HW2111069 | ZCSU7255301 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-30 |  | 2022-01-06 | 2021-12-20 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-05 | 3 | 2022-01-07 | 2 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | CORNELIA MAERSK | ZIMUSEL7100250 | HW2111069 | TCKU6022179 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-23 | 2021-12-30 |  | 2022-01-06 | 2021-12-20 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-05 | 3 | 2022-01-13 | 8 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | SEGU5758604 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | TEMU6165030 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-03 | 1 | 2022-01-04 | 1 | DELIVERED | CLOSED IN CELLO 01/05 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | TEMU6319897 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-03 | 1 | 2022-01-04 | 1 | DELIVERED | CLOSED IN CELLO 01/07 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | TGBU7154214 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-03 | 1 | 2022-01-04 | 1 | DELIVERED | CLOSED IN CELLO ON 01/05, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | TGHU6580310 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-03 | 1 | 2022-01-04 | 1 | DELIVERED | CLOSED IN CELLO 01/05 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | ZCSU6625757 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | ZCSU7356441 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | ZCSU7417824 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-05 | 1 | DELIVERED | CLOSED IN CELLO ON 01/06, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | ZCSU8524447 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-06 | 2 | DELIVERED | CLOSED IN CELLO ON 01/07, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CORNELIA MAERSK | ZIMUSEL7096386 | PTIK21S11248 | ZCSU8607428 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-11-19 | 2021-12-30 |  | 2022-01-06 | 11/4/2021; 12/20/21 | 2022-01-02 | 3 | 2022-01-06 | 2022-01-04 | 2 | 2022-01-07 | 3 | DELIVERED | CLOSED IN CELLO ON 01/11, FNS15 DUKE PROJECT
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | BEAU5550162 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | GAOU6041970 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | GAOU6104718 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | JXLU7820779 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | JXLU7822998 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | KSSU1008341 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-06 | 1 | 2022-01-07 | 1 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | TCNU4565000 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | TEMU7252226 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-12 | 2021-12-28 | 2022-01-06 | 1 | 2022-01-12 | 2022-01-07 | 1 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | TGBU5773333 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7098251 | PTIK21S12265 | UETU5903412 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7102586 | GLVSKR0011210 | TCLU5871760 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-14 | 7 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7102586 | GLVSKR0011210 | TCNU2483351 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7102586 | GLVSKR0011210 | ZCSU6656974 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7102586 | GLVSKR0011210 | ZCSU7226089 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 01/18 (DGM15)
GA-DGM | 72100082 | MSC MUMBAI | ZIMUSEL7102586 | GLVSKR0011210 | ZCSU8646384 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-05 | 2022-01-05 |  | 2022-01-11 | 2021-12-28 | 2022-01-05 | 0 | 2022-01-11 | 2022-01-07 | 2 | 2022-01-07 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15)
GA-DGM | 72100082 | ZIM SAN DIEGO | ZIMUSEL7102542 | HW2112010 | ZCSU7960786 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-09 | 2022-01-06 |  | 2022-01-13 | 2021-12-28 | 2022-01-08 | 2 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/17 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM SAN DIEGO | ZIMUSEL7099216 | PTIK21S12267 | ZCSU7369027 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-07 | 2022-01-06 |  | 2022-01-13 | 2021-12-28 | 2022-01-07 | 1 | 2022-01-13 | 2022-01-11 | 4 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 01/12 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM SAN DIEGO | ZIMUSEL7099216 | PTIK21S12267 | HNSU5015199 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-07 | 2022-01-06 |  | 2022-01-13 | 2021-12-28 | 2022-01-08 | 2 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/12 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM SAN DIEGO | ZIMUSEL7099216 | PTIK21S12267 | DRYU9555928 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-07 | 2022-01-06 |  | 2022-01-13 | 2021-12-28 | 2022-01-08 | 2 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/12; 2/1 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | ZIM SAN DIEGO | ZIMUSEL7099216 | PTIK21S12267 | BSIU9613438 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-07 | 2022-01-06 |  | 2022-01-13 | 2021-12-28 | 2022-01-08 | 2 | 2022-01-13 | 2022-01-11 | 3 | 2022-01-11 | 0 | DELIVERED | CLOSED IN CELLO 1/12 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | BSIU9234970 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-13 | 2 | 2022-01-18 | 5 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | BSIU9311124 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-13 | 2 | 2022-01-14 | 1 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | HDMU6708914 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-14 | 11/4/2021; 12/21 | 2022-01-10 | 0 | 2022-01-14 | 2022-01-12 | 2 | 2022-01-13 | 1 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | HMMU6294411 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-14 | 3 | 2022-01-18 | 4 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | HMMU6324619 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-12 | 1 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | KOCU4389767 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-12 | 1 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | KOCU4926336 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-12 | 1 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | KOCU5069881 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-12 | 1 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | TCNU7048932 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-13 | 2 | 2022-01-18 | 5 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100072 | HYUNDAI PRIDE | HDMUSELM54347000 | PTIK21S11245 | TGBU6225777 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-11-22 | 2022-01-10 |  | 2022-01-17 | 11/4/2021; 12/21 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-12 | 1 | 2022-01-14 | 2 | DELIVERED | CLOSED IN CELLO 01/18 FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FORTUNE | EGLV040100538010 | PTIK21S12262 | EITU1674602 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2022-01-10 |  | 2022-01-17 | 12/13/21; 01/04/22 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-15 | 4 | 2022-01-18 | 3 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FORTUNE | EGLV040100538010 | PTIK21S12262 | TCNU3372054 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2022-01-10 |  | 2022-01-17 | 12/13/21; 01/04/22 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-17 | 6 | 2022-01-19 | 2 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100082 | EVER FORTUNE | EGLV040100538010 | PTIK21S12262 | EGSU9190510 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-02 | 2022-01-10 |  | 2022-01-17 | 12/13/21; 01/04/22 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-15 | 4 | 2022-01-18 | 3 | DELIVERED | CLOSED IN CELLO ON 1/21, FNS15 DUKE PROJECT
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100614077 | PTIK21S12266 | TGBU7136946 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-10 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-17 | 6 | 2022-01-17 | 0 | DELIVERED | CLOSEDIN CELLO 1/20 (DGM15)
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100614077 | PTIK21S12266 | TCNU2890254 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-10 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-17 | 6 | 2022-01-18 | 1 | DELIVERED | CLOSEDIN CELLO 1/20 (DGM15)
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100614077 | PTIK21S12266 | BEAU4560839 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 580 | 20 | 2021-12-10 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-19 | 8 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15)
GA-DGM | 72100082 | EVER FORTUNE | CMDUSEL1261908 | HW2111118 | CMAU6801207 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-12-11 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-17 | 6 | 2022-01-17 | 0 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | EVER FORTUNE | CMDUSEL1261908 | HW2111118 | SEGU5730783 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 493 | 17 | 2021-12-11 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-17 | 2022-01-17 | 6 | 2022-01-18 | 1 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100531406 | SHTCS2112041 | GAOU6402060 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-11 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-17 | 6 | 2022-01-18 | 1 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100531406 | SHTCS2112041 | EISU9293764 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-11 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-18 | 7 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15)
GA-DGM | 72100082 | EVER FORTUNE | EGLV040100487326 | SHTCS2112009 | CAIU7071142 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-11 | 2022-01-10 |  | 2022-01-17 | 2022-01-04 | 2022-01-11 | 1 | 2022-01-19 | 2022-01-18 | 7 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 01/24 (DGM15)
GA-FNS | 72100082 | EVER LADEN | CMDUSEL1260342 | HW2111102 | TGBU4130796 | Q.PEAK DUO XL-G10C.3/BFG 480 | 30397572C | 15 | 464 | 16 | 2021-12-01 | 2022-01-12 |  | 2022-01-23 | 12/13/21; 01/04/22 | 2022-01-13 | 1 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO 01/24 FNS15 DUKE PROJECT
GA-DGM | 72100082 | EVER LADEN | EGLV040100531384 | SHTCS2112021 | TCLU6311862 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-03 | 2022-01-12 |  | 2022-01-23 | 2022-01-04 | 2022-01-13 | 1 | 2022-01-20 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 01/24 (DGM15)
GA-DGM | 72100082 | EVER LADEN | EGLV040100538052 | PTIK21S12264 | TCNU4517851 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-04 | 2022-01-13 | 1 | 2022-01-20 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO 1/20 (DGM15)
GA-DGM | 72100082 | EVER LADEN | EGLV040100538052 | PTIK21S12264 | EITU9455283 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-04 | 2022-01-13 | 1 | 2022-01-20 | 2022-01-18 | 5 | 2022-01-18 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15)
GA-DGM | 72100082 | EVER LADEN | EGLV040100538052 | PTIK21S12264 | BEAU4470611 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-14 | 2022-01-12 |  | 2022-01-23 | 2022-01-04 | 2022-01-13 | 1 | 2022-01-20 | 2022-01-19 | 6 | 2022-01-21 | 2 | DELIVERED | CLOSED IN CELLO 1/25 (DGM15) DUKE (BAY TRAIL/FORT GREEN)
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | BMOU5792469 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-17 | 4 | 2022-01-19 | 2 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | SEGU5760710 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-17 | 4 | 2022-01-19 | 2 | DELIVERED | CLOSED IN CELLO 1/20 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | TEMU7307083 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU6520653 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU6563948 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU6567732 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-20 | 1 | DELIVERED | CLOSED IN CELLO ON 1/21, FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU7153608 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-21 | 2 | DELIVERED | CLOSED IN CELLO 01/24 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU7307154 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-21 | 2 | DELIVERED | CLOSED IN CELLO 01/24 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU7371770 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-21 | 2 | DELIVERED | CLOSED IN CELLO 01/24 FNS15 DUKE PROJECT
GA-FNS | 72100082 | CEZANNE | ZIMUSEL7100546 | PTIK21S12269 | ZCSU7573658 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-13 |  | 2022-01-24 | 2022-01-05 | 2022-01-13 | 0 | 2022-01-19 | 2022-01-19 | 6 | 2022-01-21 | 2 | DELIVERED | CLOSED IN CELLO 01/24 FNS15 DUKE PROJECT
GA-DGM | 72100082 | SANTA LINEA | ZIMUSEL7103942 | SHTCS2112107 | JXLU7826289 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571C | 15 | 580 | 20 | 2021-12-13 | 2022-01-14 |  | 2022-01-25 | 2022-01-04 | 2022-01-14 | 0 | 2022-01-21 | 2022-01-19 | 5 | 2022-01-19 | 0 | DELIVERED | CLOSED IN CELLO ON 1/21 (DGM15)
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | BSIU9589286 | Q.PEAK DUO XL-G10C.D/BFG 480 | 30397872C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-22 | 0 | 2022-01-27 | 2022-01-24 | 2 | 2022-01-26 | 2 | DELIVERED | CLOSED IN CELLO ON 1/27, FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | ZCSU7640273 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-22 | 0 | 2022-01-27 | 2022-01-24 | 2 | 2022-01-26 | 2 | DELIVERED | CLOSED IN CELLO ON 1/27, FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | ZCSU7647914 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-23 | 0 | 2022-01-27 | 2022-01-25 | 2 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | ZCSU7764206 | Q.PEAK DUO XL-G10C.D/BFG 475 | 30397871C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-23 | 0 | 2022-01-27 | 2022-01-25 | 2 | 2022-01-25 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | ZCSU7964328 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-24 | 0 | 2022-01-28 | 2022-01-26 | 2 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO 01/28 FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | ZCSU8550739 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-24 | 0 | 2022-01-28 | 2022-01-26 | 2 | 2022-01-26 | 0 | DELIVERED | CLOSED IN CELLO ON 1/27, FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | CAAU5240087 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-24 | 0 | 2022-01-28 | 2022-01-26 | 2 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO 01/28 FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | RFCU5106520 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 573 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-24 | 0 | 2022-01-28 | 2022-01-26 | 2 | 2022-01-27 | 1 | DELIVERED | CLOSED IN CELLO 01/28 FNS15 DUKE PROJECT (211206_J3_GXBC10_475A_002 - 22 PCS)
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | TCNU5830330 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-24 | 0 | 2022-01-28 | 2022-01-27 | 3 | 2022-01-28 | 1 | DELIVERED | CLOSED IN CELLO 01/28 FNS15 DUKE PROJECT
GA-FNS | 72100072 | COLUMBINE MAERSK | ZIMUSEL7100545 | PTIK21S12270 | TGBU5366636 | Q.PEAK DUO XL-G10BC.C 475 | 30397471C | 15 | 580 | 20 | 2021-12-17 | 2022-01-22 |  | 2022-02-02 | 1/5/22; 1/14/22 | 2022-01-22 | 0 | 2022-01-27 | 2022-01-27 | 5 | 2022-01-27 | 0 | DELIVERED | CLOSED IN CELLO 01/28 FNS15 DUKE PROJECT
GA-DGM | 72100082 | CMA CGM CHRISTOPHE COLOMB | CMDUSEL1261850 | HW2111119 | APHU6419958 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2021-12-11 | 2022-02-08 |  | 2022-02-19 | 2022-01-27 | 2022-02-10 | 0 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSED IN CELLO 02/17 DGM0
GA-DGM | 72100082 | CMA CGM CHRISTOPHE COLOMB | CMDUSEL1261850 | HW2111119 | CMAU5523462 | Q.PEAK DUO XL-G10C.3.1/BFG 480 | 30390372 | 0 | 580 | 20 | 2021-12-11 | 2022-02-08 |  | 2022-02-19 | 2022-01-27 | 2022-02-10 | 0 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSED IN CELLO 02/17 DGM0
GA-DGM | 72100082 | CMA CGM CHRISTOPHE COLOMB | CMDUSEL1261850 | HW2111119 | TEMU6039941 | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371 | 0 | 580 | 20 | 2021-12-11 | 2022-02-08 |  | 2022-02-19 | 2022-01-27 | 2022-02-10 | 0 | 2022-02-16 | 2022-02-16 | 6 | 2022-02-16 | 0 | DELIVERED | CLOSED IN CELLO 02/17 DGM0
GA-FNS | 72100082 | CMA CGM CHRISTOPHE COLOMB | EGLV040100531198 | SHTCS2112014 | EISU8277692 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 580 | 20 | 2021-12-24 | 2022-02-08 |  | 2022-02-19 | 1/5/22; 1/28/22 | 2022-02-09 | 0 | 2022-02-17 | 2022-02-14 | 5 | 2022-02-14 | 0 | DELIVERED | CLOSED IN CELLO 02/15 FNS0 DUKE PROJECT
GA-DGM | 72100082 | COSCO SHIPPING LOTUS | CMDUSEL1261921 | HW2111117 | CMAU7337596 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 493 | 17 | 2021-12-11 | 2022-02-14 |  | 2022-02-25 | 2022-02-09 | 2022-02-15 | 0 | 2022-02-18 | 2022-02-16 | 1 | 2022-02-17 | 1 | DELIVERED | CLOSED IN CELLO 02/18 (DGM0) DUKE (BAY TRAIL/FORT GREEN)
GA-DGM | 72100082 | COSCO SHIPPING LOTUS | CMDUSEL1261921 | HW2111117 | TEMU8285610 | Q.PEAK DUO XL-G10C.3/BFG 475 | 30397571 | 0 | 493 | 17 | 2021-12-11 | 2022-02-14 |  | 2022-02-25 | 2022-02-09 | 2022-02-15 | 0 | 2022-02-21 | 2022-02-16 | 1 | 2022-02-17 | 1 | DELIVERED | CLOSED IN CELLO 02/18 (DGM0) DUKE (BAY TRAIL/FORT GREEN)
Formulas:
WH ETA = [ETA/ATA]+11

## Inbound Transfer (W02)
BOL | Origin | Service | Carrier | PIC | Customer Name | Incoterm | Destination Address | PO | Product | Item Code | Tariff (%) | Qty | Pallet | Pick Up Date | Pickup Appt | Delivery Date | Delivery Appt | STATUS | Remark
CA1002121201T | CA WH | FTL | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | 2018-701002 | Q.PLUS L G4.2 345 | 30112510BLINE | 30 | 638 | 22 | 2018-12-21 |  | 2019-01-03 |  | DELIVERED | PAPERWORK RCVD AND CLOSED IN CELLO ON 1/4 (PSS)
CA1301010702 | CA WH | FTL | NTGO | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | PVS-Homewood Suites | Q.PEAK DUO G5 320 | 30140005 | 0 | 512 | 16 | 2019-01-13 |  | 2019-01-15 |  | DELIVERED
CA0881021002 | CA WH | PN | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L G4.2 340 | 12000631 | 0 | 377 | 13 | 2019-02-25 |  | 2019-03-06 |  | DELIVERED
CA0881021002 | CA WH | PN | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L G4.2 340 | 12000670 | 0 | 406 | 14 | 2019-02-25 |  | 2019-03-06 |  | DELIVERED
CA0881021001 | CA WH | PN | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L G4.2 340 | 12000631 | 0 | 754 | 26 | 2019-02-25 |  | 2019-03-06 |  | DELIVERED
CA0881021003 | CA WH | PN | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L G4.2 340 | 12000670 | 0 | 754 | 26 | 2019-02-25 |  | 2019-03-11 |  | DELIVERED
CA0881021004 | CA WH | PN | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L G4.2 340 | 12000670 | 0 | 754 | 26 | 2019-02-25 |  | 2019-03-11 |  | DELIVERED
GA1241061401NJ | GA WH | FTL | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | 06122019_41201124_1 | Q.PEAK DUO BLK G5.F 320 | 41201124 | 0 | 960 | 30 | 2019-06-14 |  | 2019-06-17 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 6/20
GA1241061402NJ | GA WH | FTL | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | 06122019_41201124_1 | Q.PEAK DUO BLK G5.F 320 | 41201124 | 0 | 960 | 30 | 2019-06-14 |  | 2019-06-17 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 6/20
GASL206131326NJ | GA WH | FTL | Schneider | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | SL206131326 | Q.PEAK DUO L G5.2.F_A 395 | 41101139 | 0 | 493 | 17 | 2019-06-28 |  | 2019-07-01 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 7/12
GASL206131375NJ | GA WH | FTL | Schneider | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | SL206131375 | Q.PEAK DUO L G5.2.F_A 395 | 41101139 | 0 | 232 | 8 | 2019-06-27 |  | 2019-06-28 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 7/12
GASL206131375NJ | GA WH | FTL | Schneider | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | SL206131375 | Q.PEAK DUO L G5.2.V_A 395 | 43101139 | 0 | 435 | 15 | 2019-06-27 |  | 2019-06-28 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 7/12
GA0701000001NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F_A 395 | 41101139 | 0 | 754 | 26 | 2019-07-03 |  | 2019-07-05 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/8
GA0701000002NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F_A 395 | 41101139 | 0 | 754 | 26 | 2019-07-03 |  | 2019-07-05 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/8
GA0701000003NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F_A 395 | 41101139 | 0 | 754 | 26 | 2019-07-03 |  | 2019-07-05 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/8
GA0701000004NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-08 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000005NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F 395 | 41101539 | 0 | 754 | 26 | 2019-07-08 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000006NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-08 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000008NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F 395 | 41101539 | 0 | 754 | 26 | 2019-07-08 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000007NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-09 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000010NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-09 |  | 2019-07-10 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000009NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.F 395 | 41101539 | 0 | 754 | 26 | 2019-07-08 |  | 2019-07-11 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000012NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-09 |  | 2019-07-11 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000013NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-09 |  | 2019-07-11 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
GA0701000014NJ | GA WH | FT | FQCI | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-07-09 |  | 2019-07-11 |  | DELIVERED | DELIVERED (PIONEER-NEW) CLOSED IN CELLO ON 7/19
CA0371071506TNJ | CA WH | LTL | HJBT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | NA | Q.PLUS DUO L-G5.2 360 | 12002140 | 25 | 29 | 1 | 2019-07-26 |  | 2019-07-30 |  | DELIVERED | General Electric (110000371) Quantity Issue - DO# CA0371071506T
VATRANS081901A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-19 |  | 2019-08-20 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/21
VATRANS081902A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-19 |  | 2019-08-20 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/21
VATRANS081903A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-19 |  | 2019-08-20 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/21
VATRANS081904A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-19 |  | 2019-08-20 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/21
VATRANS081905A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-19 |  | 2019-08-20 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/21
VATRANS082006A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-20 |  | 2019-08-21 |  | DELIVERED
VATRANS082007A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-20 |  | 2019-08-21 |  | DELIVERED
VATRANS082008A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-20 |  | 2019-08-21 |  | DELIVERED
VATRANS082009A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-20 |  | 2019-08-21 |  | DELIVERED
VATRANS082010A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-20 |  | 2019-08-21 |  | DELIVERED
VATRANS082111A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-21 |  | 2019-08-22 |  | DELIVERED
VATRANS082112A | VA WH | FT | PNCT | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 754 | 26 | 2019-08-21 |  | 2019-08-22 |  | DELIVERED
VATRANS082113A | VA WH | LTL | XPO | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Warehouse transfer | Q.PLUS L-G4.2.5.A.F 345 | 30340710A | 25 | 58 | 2 | 2019-08-21 |  | 2019-08-23 |  | DELIVERED
299530337 | CHR WH | LTL | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | PO-90363 PT1 | Q.PEAK DUO BLK G5.V 315 | 43202123 | 0 | 288 | 9 | 2019-08-21 |  | 2019-08-23 |  | DELIVERED | CH Robinson currently has 9 Pallets (Some damaged) in their warehouse in NJ
GA302605482 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-08-27 |  | 2019-08-28 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/30
GA302605484 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-08-27 |  | 2019-08-28 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/30
GA302605481 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-08-27 |  | 2019-08-28 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/30
GA302605479 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-08-28 |  | 2019-08-29 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/30
GA302605477 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 754 | 26 | 2019-08-28 |  | 2019-08-29 |  | DELIVERED | DELIVERED (PSS) CLOSED IN CELLO ON 8/30
GA302605488 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V_A 395 | 43101139 | 0 | 145 | 5 | 2019-08-28 |  | 2019-08-30 |  | DELIVERED
GA302605488 | GA WH | FT | CHR | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V 395 | 43101539 | 0 | 406 | 14 | 2019-08-28 |  | 2019-08-30 |  | DELIVERED
GA309259338 | GA WH | LTL | FedEx | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WH Transfer | Q.PEAK DUO L G5.2.V_A 395 | 43101139 | 0 | 29 | 1 | 2019-11-18 |  | 2019-11-21 |  | DELIVERED | DELIVERED (PSS) PAPERWORK RCVD AND CLOSED IN CELLO 11/22
GA312436346 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436347 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436351 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436352 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436348 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436349 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436350 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312436353 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-20 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312523194 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312523193 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312523196 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312523199 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (CELL# PIONEERNBNEW0)
GA312523192 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (CELL# PIONEERNBNEW0)
GA312523197 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-23 |  | 2019-12-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/27 (CELL# PIONEERNBNEW0)
GA312523201 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0); PALLET ID 191207_E1_410300_365A_742 ON HOLD AS NO-VALUE INVENTORY
GA312523200 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED
GA312523198 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED
GA312523195 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED | DELIVERED (CELL# PIONEERNBNEW0) PALLET ID 191207_E1_410300_365A_793 ON HOLD AS NO VALUE INVENTORY
GA312523191 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED
CJLQCELL122719 | CJ WH | LTL | 3R LOGISTICS GROUP | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | CJ TRANSFER | Q.PEAK DUO BLK G5.V 315 | 43202123 | 0 | 128 | 4 | 2019-12-27 |  | 2019-12-30 |  | DELIVERED | DELIVERED CELOSED IN CELLO 12/31 (11CZEROT)
GA312537830 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED
GA312537688 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537692 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537687 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED
GA312537696 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537677 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537685 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED
GA312537697 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537695 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537681 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED
GA312537686 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED
GA312537682 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537684 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537693 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA312537689 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0); PALLET ID 191207_E1_410300_365A_740 ON HOLD AS NO-VALUE INVENTORY
GA312537676 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254953 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 355 | 44101131 | 0 | 435 | 15 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254954 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 355 | 44101131 | 0 | 754 | 26 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED
GA313254957 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 355 | 44101131 | 0 | 754 | 26 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED
GA313254963 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 355 | 44101131 | 0 | 754 | 26 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254962 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 355 | 44101131 | 0 | 754 | 26 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254959 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 V 360 | 44101132 | 0 | 754 | 26 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254958 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 V 360 | 44101132 | 0 | 725 | 25 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED
GA313254956 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 V 360 | 44101132 | 0 | 609 | 21 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/7 (CELL# PIONEERNBNEW0)
GA313254955 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 V 360 | 44101132 | 0 | 377 | 13 | 2020-01-04 |  | 2020-01-06 |  | DELIVERED
GA312537680 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-07 |  | DELIVERED
GA312537679 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-14 |  | DELIVERED
GA312537678 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-03 |  | 2020-01-08 |  | DELIVERED
GA312537699 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-06 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA312537683 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 435 | 15 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA312537691 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA312537694 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA312537698 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA312537690 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PLUS DUO L G5.2 365 | 44103133 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | NEED TO PUT 191214_E1_410300_365A_743 ON HOLD AS NO VALUE INVENTORY DUE TO FTD WITH ZERO VALUE - PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395705 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395708 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395711 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395727 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/15 (PIONEERNBNEW0)
GA313395718 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395724 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395713 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-08 |  | 2020-01-09 |  | DELIVERED | PAPERWORK RCVD CLOSED IN CELLO ON 1/13 (PIONEERNBNEW0)
GA313395704 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395706 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-09 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395707 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395709 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395710 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395712 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395714 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313395715 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/15 (PIONEERNBNEW0)
GA313395717 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-10 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313588244 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO L G5.2 400 | 43103140 | 0 | 754 | 26 | 2020-01-09 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/14 (PIONEERNBNEW0)
GA313587266 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-09 |  | 2020-01-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/15 (PIONEERNBNEW0)
GA313587456 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-09 |  | 2020-01-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/15 (PIONEERNBNEW0)
GA313590110 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-09 |  | 2020-01-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO 1/15 (PIONEERNBNEW0)
GA314615056 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/28 (PIONEERNB)
GA314615057 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/28 (PIONEERNB)
GA314615058 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/28 (PIONEERNB)
GA314615059 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/28 (PIONEERNB)
GA314615060 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/28 (PIONEERNB)
GA314615061 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-28 |  | DELIVERED
GA314615062 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (320W BLK) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-01-24 |  | 2020-01-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 1/29 (PIONEERNB) (191002_E1_320200_320A_701 need to put this pallet on hold for "No value" inventory due to wattage issue)
GA315361391 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361392 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361393 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361397 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361398 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361399 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361400 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361402 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 2/5 (CELL# 11CZEROT)
GA315361404 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361405 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 2/5 (CELL# 11CZEROT)
GA315361407 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-03 |  | DELIVERED
GA315361408 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 2/5 (CELL# 11CZEROT)
GA315361409 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-01-31 |  | 2020-02-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 2/5 (CELL# 11CZEROT)
GA315361410 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-02-03 |  | 2020-02-04 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 2/5 (CELL# 11CZEROT)
GA315361395 | GA WH | FT | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Samsung SDS / PSS Warehouse (Stock Transfer-315W) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 | 2020-02-04 |  | 2020-02-06 |  | DELIVERED
GA319861067 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/08 - (GTGSS0)
GA319861098 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861099 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861102 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861104 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861105 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-30 |  | 2020-04-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861100 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-31 |  | 2020-04-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861101 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-31 |  | 2020-04-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861103 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-31 |  | 2020-04-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
GA319861106 | GA WH | FT | CH Robinson | Hanwha | GTG |  | 340 South Stiles Street Linden, NJ 07036 (GTGSS0) | Warehouse Transfer (320W) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 | 2020-03-31 |  | 2020-04-03 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 04/07 - (GTGSS0)
CA0422042201T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 754 | 26 | 2020-04-24 |  | 2020-04-30 |  | DELIVERED
CA0422042202T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 754 | 26 | 2020-04-23 |  | 2020-04-29 |  | DELIVERED
CA0422042203T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 754 | 26 | 2020-04-24 |  | 2020-04-30 |  | DELIVERED
CA0422042204T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 754 | 26 | 2020-04-23 |  | 2020-04-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/29 (PIONEERNBNEW20)
CA0422042205T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 754 | 26 | 2020-04-24 |  | 2020-04-29 |  | DELIVERED
CA0422042206T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.1.V 415 | 30382759R | 20 | 725 | 25 | 2020-04-27 |  | 2020-04-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNBNEW20)
CA0422042207T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.3.2.V 415 | 30383059R | 20 | 754 | 26 | 2020-04-27 |  | 2020-04-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNBNEW20)
CA0422042208T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.3.2.V 415 | 30383059R | 20 | 116 | 4 | 2020-04-27 |  | 2020-04-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNBNEW20)
CA0422042208T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.2.V 415 | 30382959R | 20 | 638 | 22 | 2020-04-27 |  | 2020-04-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/01 (PIONEERNBNEW20)
CA0422042209T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.2.V 415 | 30382959R | 20 | 754 | 26 | 2020-04-24 |  | 2020-04-30 |  | DELIVERED
CA0422042210T | CA WH | FT | HJBT | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L-G8.2.2.V 415 | 30382959R | 20 | 754 | 26 | 2020-04-24 |  | 2020-04-29 |  | DELIVERED
GA323618861 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 832 | 26 | 2020-05-15 |  | 2020-05-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 5/19 (PIONEERNB)
GA324103009 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 5/27 (PIONEERNB) SIP for IMPA
GA324103005 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324102999 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 5/27 (PIONEERNB) SIP for IMPA
GA324103015 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103003 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103007 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103113 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103115 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103084 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324110597 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324110598 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-26 |  | DELIVERED | SIP for IMPA
GA324103075 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-27 |  | DELIVERED | SIP for IMPA
GA324103004 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-22 |  | 2020-05-27 |  | DELIVERED | SIP for IMPA
GA324110595 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324103000 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324103008 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324103006 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324103140 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324110601 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324110604 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324110591 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | SIP for IMPA
GA324203802 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (405W) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/29 (PIONEERNB); SIP for Summit Ridge Energy
GA324203581 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (405W) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/29 (PIONEERNB); SIP for Summit Ridge Energy
GA324203033 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (405W) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/29 (PIONEERNB); SIP for Summit Ridge Energy
GA324103094 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-26 |  | 2020-05-28 |  | DELIVERED | DELIVERED (PIONEERNB); SIP for IMPA
GA324204270 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (405W) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for Summit Ridge Energy
GA324204769 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (405W) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 609 | 21 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for Summit Ridge Energy
GA324103001 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110593 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324103010 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324103002 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324103016 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324103091 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324103110 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110603 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110602 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110592 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110607 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA324110606 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 377 | 13 | 2020-05-27 |  | 2020-05-29 |  | DELIVERED | SIP for IMPA
GA325680090 | GA WH | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (405W Additional) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-06-11 |  | 2020-06-17 |  | DELIVERED | SIP for Summit Ridge Energy (need label)
GA325680091 | GA WH | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (405W Additional) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-06-11 |  | 2020-06-17 |  | DELIVERED | SIP for Summit Ridge Energy (need label)
GA325680092 | GA WH | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (405W Additional) | Q.PEAK DUO L G5.2 405 | 43101141 | 0 | 754 | 26 | 2020-06-11 |  | 2020-06-17 |  | DELIVERED | SIP for Summit Ridge Energy (need label)
GAIMPAWT061201 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-12 |  | 2020-06-15 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061202 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-12 |  | 2020-06-15 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061203 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-12 |  | 2020-06-15 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061204 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-12 |  | 2020-06-15 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061501 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-15 |  | 2020-06-17 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061502 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-15 |  | 2020-06-17 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061503 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-15 |  | 2020-06-17 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061504 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-15 |  | 2020-06-17 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061601 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GAIMPAWT061602 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/19 (PIONEERNB); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GAIMPAWT061603 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061604 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061701 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061702 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061703 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061704 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061901 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061902 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GAIMPAWT061903 | GA WH | FTL | NOLAN | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (400W IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 319 | 11 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061601 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061602 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061603 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061701 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061702 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061703 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/22 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061704 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/22 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061705 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/22 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061801 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061802 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061803 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061804 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061805 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061806 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W061807 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-18 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062201 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 6/18/20 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062202 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 6/18/20 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062203 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 6/18/20 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062204 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 6/18/20 |  | 2020-06-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/24 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062301 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-23 |  | 2020-06-25 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062302 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-06-23 |  | 2020-06-25 |  | DELIVERED | Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
GA335W062303 | GA WH | FTL | TQL | Hanwha | ROMARK |  | 145 TALMADGE ROAD EDISON, NJ 08817 | Warehouse Transfer (335 W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 384 | 12 | 2020-06-23 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/25 (ROMARK145TR); Transfer from New Buffer Warehouse - 201 Princeton Boulevard, Adairsville, GA 30103
CA2020060501T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-11 |  | 2020-06-22 |  | DELIVERED | SIP for Kearsarge
CA2020060502T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-11 |  | 2020-06-22 |  | DELIVERED | SIP for Kearsarge
CA2020060503T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 348 | 12 | 2020-06-11 |  | 2020-06-24 |  | DELIVERED | SIP for Kearsarge
CA2020060503T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 348 | 12 | 2020-06-11 |  | 2020-06-24 |  | DELIVERED | SIP for Kearsarge
CA2020060504T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 261 | 9 | 2020-06-11 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge; SIP for Kearsarge
CA2020060504T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 435 | 15 | 2020-06-11 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/23 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge; SIP for Kearsarge
CA2020060505T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-11 |  | 2020-06-23 |  | DELIVERED | SIP for Kearsarge
CA2020060506T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-11 |  | 2020-06-24 |  | DELIVERED | SIP for Kearsarge
CA2020060507T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-12 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060508T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-12 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060508T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-12 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060509T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-12 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060510T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-12 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060511T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-12 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060512T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-12 |  | 2020-06-23 |  | DELIVERED | SIP for Kearsarge
CA2020060513T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 435 | 15 | 2020-06-15 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060513T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 261 | 9 | 2020-06-15 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060514T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 29 | 1 | 2020-06-15 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060514T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 667 | 23 | 2020-06-15 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060515T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 87 | 3 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060515T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 609 | 21 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060516T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 174 | 6 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060516T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 522 | 18 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060517T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 348 | 12 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060517T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 348 | 12 | 2020-06-15 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060518T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 667 | 23 | 2020-06-15 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060518T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 29 | 1 | 2020-06-15 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060519T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060520T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060520T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060521T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | SIP for Kearsarge
CA2020060522T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-16 |  | 2020-06-24 |  | DELIVERED | SIP for Kearsarge
CA2020060522T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-16 |  | 2020-06-24 |  | DELIVERED | SIP for Kearsarge
CA2020060523T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060523T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-16 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060524T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-16 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/25 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060525T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060525T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060526T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 522 | 18 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060526T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 174 | 6 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | SIP for Kearsarge
CA2020060527T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060528T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 406 | 14 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060528T1 | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 29 | 1 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20) / Horizontal Packaging; SIP for Kearsarge
CA2020060529T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 696 | 24 | 2020-06-17 |  | 2020-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20); SIP for Kearsarge
CA2020060530T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 696 | 24 | 2020-06-17 |  | 2020-07-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/09 (PIONEERNB20); SIP for Kearsarge
CA2020060531T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20); SIP for Kearsarge
CA2020060532T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20); SIP for Kearsarge
CA2020060533T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/01 (PIONEERNB20); SIP for Kearsarge
CA2020060534T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (420W) | Q.PEAK DUO L-G8.3 420 | 30383060R | 20 | 377 | 13 | 2020-06-18 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (PIONEERNB20); SIP for Kearsarge
GA326211400 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-16 |  | 2020-06-18 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211406 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-16 |  | 2020-06-19 |  | DELIVERED | DELIVERED (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211414 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-16 |  | 2020-06-19 |  | DELIVERED | DELIVERED (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211422 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-16 |  | 2020-06-17 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211405 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211396 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211407 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211421 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211416 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211399 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-19 |  | DELIVERED | DELIVERED (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211397 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-18 |  | 2020-06-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211402 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211398 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211411 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211412 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-17 |  | 2020-06-18 |  | DELIVERED | DELIVERED, CLOSED IN CELLO 6/19 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211420 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211417 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211415 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211419 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 832 | 26 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211418 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 448 | 14 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211413 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-18 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/25 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211404 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-18 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/25 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211403 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-18 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/25 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
GA326211401 | GA WH | FTL | CH Robinson | Hanwha | GTG |  | GTG-340 South Stiles (GTGSS0) | Warehouse Transfer (315W 700plts) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-06-18 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 6/25 (GTGSS0); Transfer from External Warehouse 3551 Corporate DR, Dalton, GA 30721
CA2020061701T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 58 | 2 | 2020-06-18 |  | 2020-06-23 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061701T1 | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 638 | 22 | 2020-06-18 |  | 2020-06-23 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061702T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-25 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061703T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-25 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061704T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-25 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061705T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-23 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061706T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-25 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061707T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-18 |  | 2020-06-24 |  | DELIVERED | For Independence Solar - PO# 202005281
CA2020061708T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 06/23 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061709T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061710T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061711T | CA WH | FTL | NHCS | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-24 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061712T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-24 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061713T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061714T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-25 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061715T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-19 |  | 2020-06-25 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061716T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/25 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061717T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061718T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061719T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/29 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061720T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-22 |  | 2020-06-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 6/26 (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061721T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 696 | 24 | 2020-06-23 |  | 2020-06-26 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061722T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 725 | 25 | 2020-06-23 |  | 2020-06-26 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061723T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 725 | 25 | 2020-06-23 |  | 2020-06-26 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
CA2020061724T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (420W Independence Solar) | Q.PEAK DUO L-G8.2 420 | 30382960R | 20 | 725 | 25 | 2020-06-23 |  | 2020-06-26 |  | DELIVERED | DELIVERED (PIONEERNB20) / Horizontal Packaging; For Independence Solar - PO# 202005281
GA327042331 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042284 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042300 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042303 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042313 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042317 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042320 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042326 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/29 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042327 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-25 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042302 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042325 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042332 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 06/30 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042334 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042336 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042337 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042341 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD) - 1 PLT potential damage : 200621_E1_310100_395A_847; SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042342 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-06-30 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042366 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-26 |  | 2020-06-29 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042285 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042287 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-07-01 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/02 (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042305 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-06-30 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042316 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-06-29 |  | 2020-06-30 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042283 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 406 | 14 | 2020-06-29 |  | 2020-06-30 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327042286 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | WHSE Transfer (395) June | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 406 | 14 | 2020-06-29 |  | 2020-06-30 |  | DELIVERED | DELIVERED (ROMARKMD); SIP - Summit Ridge / 6/30 per Kristine, it will not sure for Summit Ridge, will be regular stock for July outbound
GA327260422 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260423 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260424 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260425 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260426 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260427 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260428 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-06 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/07 (11CZEROT)
GA327260429 | GA WH | FTL | CH Robinson | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | WHSE Transfer (395) 8 trucks | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-03 |  | 2020-07-07 |  | DELIVERED | DELIVERED (11CZEROT)
CA2020070101T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (395W for SRE) | Q.PEAK DUO L-G7.2 395 | 30367455 | 20 | 696 | 24 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/15 (PIONEERNB20)/ potential damaged: 200401_K2_PDLT72_395A_795; SIP / PO# HNW2020-03 as of 7/15
CA2020070102T | CA WH | FTL | NTGO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (395W for SRE) | Q.PEAK DUO L-G7.2 395 | 30367455 | 20 | 696 | 24 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/15 (PIONEERNB20); SIP / PO# HNW2020-03 as of 7/15
GA327992760 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992748 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 864 | 27 | 2020-07-10 |  | 2020-07-14 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992746 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 416 | 13 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992758 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992756 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 416 | 13 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992745 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992757 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992759 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992762 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992770 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 800 | 25 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 7/14 (PIONEERNB)
GA327992761 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992768 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992743 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 960 | 30 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992744 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/15 (PIONEERNB)
GA327992747 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992755 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/15 (PIONEERNB)
GA327992765 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 |  |  | 2020-07-14 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/15 (PIONEERNB)
GA327992750 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 960 | 30 | 2020-07-10 |  | 2020-07-14 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992776 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 768 | 24 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED (PIONEERNB)
GA327992777 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6P+ 340 | 46202128 | 0 | 896 | 28 | 2020-07-14 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/22 (PIONEERNB)
GA327992754 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6P+ 340 | 46202128 | 0 | 896 | 28 | 2020-07-15 |  | 2020-07-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 07/22 (PIONEERNB)
GA327992766 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | [Stock Transfer] OF2 NJWH | Q.PEAK DUO BLK G6P+ 340 | 46202128 | 0 | 384 | 12 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
GA328225935 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225938 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225948 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225947 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225965 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-10 |  | 2020-07-13 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225966 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328225936 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD) potential damaged plt (H packaging) - 200702_E1_310100_395A_712 / 200702_E1_310100_395A_711
GA328225934 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328225937 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328225957 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328225959 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328225962 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328225942 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-21 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328225946 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328225954 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328225956 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-16 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225958 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225952 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328225943 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225955 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225961 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225963 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225964 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225967 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225949 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-16 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225953 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-16 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328225951 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer (395W NJWH) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 696 | 24 | 2020-07-16 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (ROMARKMD)
GA328433393 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-14 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328433463 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328435296 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433537 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433516 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433510 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-13 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)potential damaged plt (H paclagomg) - 200629_E1_310100_395A_745 / 200629_E1_310100_395A_750
GA328433460 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433461 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328434529 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433483 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433480 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433473 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-14 |  | 2020-07-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328433484 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328433488 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328434625 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328434718 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-16 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/17 (ROMARKMD)
GA328434807 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328434039 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-16 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328433520 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328433394 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/20 (ROMARKMD)
GA328433458 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-21 |  | DELIVERED | DELIVERED (ROMARKMD)
GA328433471 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328434848 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328433514 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328435169 | GA WH | FTL | CH Robinson | Hanwha | ROMARK |  | 23 MACK DR. EDISON, NJ 08817 | Stock Transfer 395W 7.4MW | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 580 | 20 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/21 (ROMARKMD)
GA328680516 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED (PIONEERNB)
GA328680520 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680523 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED (PIONEERNB)
GA328680530 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680495 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680496 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-15 |  | 2020-07-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680461 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680468 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680517 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680460 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680527 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
GA328680525 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680533 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680534 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680535 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680478 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680549 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680504 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-17 |  | 2020-07-20 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680518 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED (PIONEERNB)
GA328680511 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 7/22 (PIONEERNB)
GA328680500 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
GA328680529 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-21 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
GA328680528 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED (PIONEERNB)
GA328680532 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED (PIONEERNB)
GA328680489 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
GA328680526 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (IMPA) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 348 | 12 | 2020-07-20 |  | 2020-07-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 07/23 (PIONEERNB)
CA0095062205TRET | CA WH | FT | NTGO | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | NW-800095 | Q.PEAK DUO G5 330 | 12002818A | 25 | 320 | 10 |  |  | 2020-08-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/21 (11C25)
GA330675739 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675749 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 |  |  | 2020-08-11 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675753 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675756 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 754 | 26 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675738 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 439 | 14 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB) (PARTIAL PALLET (23 PCS) 200513_E1_320200_315A_724)
GA330675725 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 640 | 20 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675742 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO G5 325 | 43204125 | 0 | 768 | 24 |  |  | 2020-08-13 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/14 (PIONEERNB)
GA330675727 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 |  |  | 2020-08-17 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675733 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 |  |  | 2020-08-17 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675745 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 |  |  | 2020-08-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 8/19 (PIONEERNB)
GA330675752 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43202123 | 0 | 960 | 30 |  |  | 2020-08-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 8/19 (PIONEERNB)
GA330675724 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675730 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675737 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 |  |  | 2020-08-10 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675740 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43202124 | 0 | 960 | 30 |  |  | 2020-08-11 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330646459 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO L G5.2 395 | 43101139 | 0 | 464 | 16 |  |  | 2020-08-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 8/13 (PIONEERNB)
GA330646459 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 41202123 | 0 | 32 | 1 |  |  | 2020-08-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 8/13 (PIONEERNB)
GA330675734 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 480 | 15 |  |  | 2020-08-18 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675759 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 480 | 15 |  |  | 2020-08-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/20 (PIONEERNB)
GA330675757 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 315 | 43205123 | 0 | 640 | 20 |  |  | 2020-08-18 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675751 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G5 320 | 43205124 | 0 | 832 | 26 |  |  | 2020-08-21 |  | DELIVERED | DELIVERED (PIONEERNB)
GA330675723 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G6+ 330 | 45201126 | 0 | 416 | 13 |  |  | 2020-08-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/20 (PIONEERNB)
GA330675755 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G6+ 330 | 45201126 | 0 | 576 | 18 |  |  | 2020-08-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 08/20 (PIONEERNB)
GA330675758 | GA WH | FT | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Buffer Transfer) | Q.PEAK DUO BLK G6+ 330 | 45201126 | 0 | 896 | 28 |  |  | 2020-08-19 |  | DELIVERED | DELIVERED (PIONEERNB)
GA335923364 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923370 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923371 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 448 | 14 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923372 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 576 | 18 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923373 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923375 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923376 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923379 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 480 | 15 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923381 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923382 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923383 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923384 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923385 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923386 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923387 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G6+ 335 | 45201127 | 0 | 896 | 28 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923389 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-03 |  | 2020-10-05 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 10/06 (PIONEERNB)
GA335923374 | GA WH | FTL | CH Robinson | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (320W, 335W) | Q.PEAK DUO BLK G5.V 320 | 47203124 | 0 | 960 | 30 | 2020-10-05 |  | 2020-10-06 |  | DELIVERED | DELIVERED (PIONEERNB)
GA339890046 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-16 |  | 2020-11-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/19 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890037 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-16 |  | 2020-11-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/19 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890036 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-16 |  | 2020-11-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 11/18 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890032 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-18 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890027 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-16 |  | 2020-11-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/19 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890017 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-16 |  | 2020-11-18 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890014 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890072 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890054 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890048 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-18 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/19 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890030 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890022 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-17 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890063 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/20 (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890045 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-19 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890038 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-20 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890035 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-20 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890033 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-20 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
GA339890020 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (400W) | Q.PEAK DUO L G5.3 400 | 43105140 | 0 | 754 | 26 | 2020-11-18 |  | 2020-11-20 |  | DELIVERED | DELIVERED (PIONEERNB); External Warehouse in GA 3551 corporate drive Dalton, GA 30721
CA2410111651 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-18 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111652 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-18 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111653 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-18 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111654 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 609 | 21 | 2020-11-18 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111654 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 29 | 1 | 2020-11-18 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111655 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 609 | 21 | 2020-11-18 |  | 2020-11-24 |  | DELIVERED | DELIVERED - PIONEERNB
CA2410111655 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 29 | 1 | 2020-11-18 |  | 2020-11-24 |  | DELIVERED | DELIVERED - PIONEERNB
CA2410111656 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 493 | 17 | 2020-11-18 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111656 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 145 | 5 | 2020-11-18 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111657 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 609 | 21 | 2020-11-19 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111657 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 29 | 1 | 2020-11-19 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111658 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 406 | 14 | 2020-11-19 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111658 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 232 | 8 | 2020-11-19 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111659 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 464 | 16 | 2020-11-19 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111659 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 174 | 6 | 2020-11-19 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111660 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 406 | 14 | 2020-11-19 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111660 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 174 | 6 | 2020-11-19 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111660 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 58 | 2 | 2020-11-19 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111661 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-19 |  | 2020-11-25 |  | DELIVERED | DELIVERED PIONEERNB
CA2410111662 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 377 | 13 | 2020-11-19 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111662 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 261 | 9 | 2020-11-19 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
CA2410111663 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 551 | 19 | 2020-11-20 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111663 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 87 | 3 | 2020-11-20 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111664 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 435 | 15 | 2020-11-20 |  | 2020-11-25 |  | DELIVERED | DELIVERED PIONEERNB
CA2410111664 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 203 | 7 | 2020-11-20 |  | 2020-11-25 |  | DELIVERED | DELIVERED PIONEERNB
CA2410111665 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 348 | 12 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111665 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 290 | 10 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/24 - PIONEERNB
CA2410111666 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-20 |  | 2020-11-24 |  | DELIVERED | DELIVERED - PIONEERNB
CA2410111667 | CA WH | FTL | XPO | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-20 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
CA2410111668 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 638 | 22 | 2020-11-20 |  | 2020-11-25 |  | DELIVERED | DELIVERED PIONEERNB
CA2410111669 | CA WH | FTL | FQCI | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 580 | 20 | 2020-11-23 |  | 2020-11-25 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
CA2410111670 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 580 | 20 | 2020-11-23 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111671 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 551 | 19 | 2020-11-23 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
CA2410111671 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 29 | 1 | 2020-11-23 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
CA2410111672 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 348 | 12 | 2020-11-23 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
CA2410111672 | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | (WH Transfer CS Energy 410W) | Q.PEAK DUO L-G8P.3/BGT 410 | 30368358 | 0 | 29 | 1 | 2020-11-23 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO ON 12/01 (PIONEERNB)
GA340322459 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322300 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322455 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322447 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322456 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322311 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-20 |  | 2020-11-23 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322291 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-25 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322290 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/25 - PIONEERNB
GA340322298 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322299 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-25 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322448 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-25 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322467 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-23 |  | 2020-11-25 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322294 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322296 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322288 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322289 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322446 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322454 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-25 |  | 2020-11-27 |  | DELIVERED | DELIVERED CLOSED IN CELLO 11/30 (PIONEERNB)
GA340322297 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322453 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322458 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322499 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-12-01 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322295 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 406 | 14 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNB)
GA340322504 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Warehouse Transfer (CS Energy 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 377 | 13 | 2020-11-27 |  | 2020-12-02 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/03 (PIONEERNB)
GA341072625 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer (Entersolar 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNBNEW0)
GA341072809 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer (Entersolar 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNBNEW0)
GA341072848 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer (Entersolar 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-11-27 |  | 2020-12-01 |  | DELIVERED | DELIVERED (PIONEERNBNEW0)
GA341072691 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer (Entersolar 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 580 | 20 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNBNEW0)
GA341072758 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Warehouse Transfer (Entersolar 400W) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 522 | 18 | 2020-11-27 |  | 2020-11-30 |  | DELIVERED | DELIVERED (PIONEERNBNEW0)
CA2020120808T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 261 | 9 | 2020-12-14 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120808T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 435 | 15 | 2020-12-14 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120809T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 348 | 12 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120809T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 348 | 12 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120810T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120811T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-12-21 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120812T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 29 | 1 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120812T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 609 | 21 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120813T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 29 | 1 | 2020-12-18 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120813T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 145 | 5 | 2020-12-18 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120813T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 464 | 16 | 2020-12-18 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120814T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120815T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 145 | 5 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120815T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 493 | 17 | 2020-12-14 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120816T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-12-14 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW20)
CA2020120817T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 58 | 2 | 2020-12-15 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120817T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 87 | 3 | 2020-12-15 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
CA2020120817T | CA WH | PN | TQYL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (TGC 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 493 | 17 | 2020-12-15 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNBNEW20)
GA343538502 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43101140 | 0 | 609 | 21 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE
GA343538500 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 47103140 | 0 | 464 | 16 | 2020-12-22 |  | 2020-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538499 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43107540 | 0 | 116 | 4 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538499 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 47102140 | 0 | 551 | 19 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538501 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538508 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538509 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538510 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538529 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538536 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-22 |  | 2020-12-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/28 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538505 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538506 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538507 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538526 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538527 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538528 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538530 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538531 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538533 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343538504 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (Entersolar DEC) | Q.PEAK DUO L G5.2 400 | 43104140 | 0 | 406 | 14 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343711059 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46101144 | 0 | 174 | 6 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW0); EXTERNAL WAREHOUSE (Horizontal)
GA343711059 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46103144 | 0 | 58 | 2 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW0); EXTERNAL WAREHOUSE (Horizontal)
GA343711059 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46104544 | 0 | 29 | 1 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW0); EXTERNAL WAREHOUSE (Horizontal)
GA343711059 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46104144 | 0 | 116 | 4 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNBNEW0); EXTERNAL WAREHOUSE (Horizontal)
GA343711058 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46104144 | 0 | 696 | 24 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/29 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343711057 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46104144 | 0 | 754 | 26 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
GA343699942 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 46105144 | 0 | 696 | 24 | 2020-12-28 |  | 2020-12-30 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB); EXTERNAL WAREHOUSE (Horizontal)
CA2420122102T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 609 | 21 | 2020-12-24 |  | 2020-12-31 |  | DELIVERED | DELIVERED (PIONEERNB20)
CA2420122102T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 29 | 1 | 2020-12-24 |  | 2020-12-31 |  | DELIVERED | DELIVERED (PIONEERNB20)
CA2420122103T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 580 | 20 | 2020-12-24 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNB20)
CA2420122103T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 58 | 2 | 2020-12-24 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNB20)
CA2420122104T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 638 | 22 | 2020-12-24 |  | 2020-12-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/30 (PIONEERNB20)
CA2420122105T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 377 | 13 | 2020-12-24 |  | 2020-12-31 |  | DELIVERED | DELIVERED (PIONEERNB20)
CA2420122105T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 261 | 9 | 2020-12-24 |  | 2020-12-31 |  | DELIVERED | DELIVERED (PIONEERNB20)
CA2420122106T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (SRE 420W) | Q.PEAK DUO L G6P.2 420 | 30380660R | 20 | 493 | 17 | 2020-12-24 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB20)
CA2420122107T | CA WH | FTL | TQYL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (29pcs 410W) | Q.PEAK DUO L-G7.3 410 | 30367758R | 20 | 29 | 1 | 2020-12-24 |  | 2020-12-29 |  | DELIVERED | DELIVERED CLOSED IN CELLO 12/31 (PIONEERNB20)
401T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-09 |  | 2021-02-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/24 (PIONEERNB20)
402T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-11 |  | 2021-02-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/01 (PIONEERNB20)
403T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-11 |  | 2021-02-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/01 (PIONEERNB20)
404T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-11 |  | 2021-02-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/01 (PIONEERNB20)
405T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-09 |  | 2021-02-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/24 (PIONEERNB20)
406T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-09 |  | 2021-02-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/24 (PIONEERNB20)
407T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 638 | 22 | 2021-02-09 |  | 2021-02-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/24 (PIONEERNB20)
408T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-09 |  | 2021-02-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/24 (PIONEERNB20) DAMAGED PALLET
409T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-10 |  | 2021-02-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/25 (PIONEERNB20)
410T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-10 |  | 2021-02-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/25 (PIONEERNB20)
411T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-10 |  | 2021-02-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/25 (PIONEERNB20)
412T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-10 |  | 2021-02-24 |  | DELIVERED | DELIVERED CLOSED IN CELLO 02/25 (PIONEERNB20)
413T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-11 |  | 2021-02-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/01 (PIONEERNB20)
414T | NJ | FTL |  | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (CS Energy) | Q.PEAK DUO L-G6P.3/BFG 415 | 30381259R | 20 | 580 | 20 | 2021-02-11 |  | 2021-02-28 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/01 (PIONEERNB20)
349966145 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-05 |  | 2021-03-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/09 (GTGBA20)
349966137 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-05 |  | 2021-03-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/09 (GTGBA20)
349966881 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-05 |  | 2021-03-08 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/09 (GTGBA20)
349966141 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-08 |  | 2021-03-10 |  | DELIVERED | DELIVERED (GTGBA20)
349966130 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-08 |  | 2021-03-10 |  | DELIVERED | DELIVERED (GTGBA20)
349966144 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-08 |  | 2021-03-10 |  | DELIVERED | DELIVERED (GTGBA20)
349966885 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-08 |  | 2021-03-10 |  | DELIVERED | DELIVERED (GTGBA20)
349966879 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-08 |  | 2021-03-11 |  | DELIVERED | DELIVERED (GTGBA20)
349963490 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/16 (GTGBA20)
349966129 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/16 (GTGBA20)
349966884 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/16 (GTGBA20)
349966156 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED (GTGBA20)
349966887 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/16 (GTGBA20)
349966882 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-10 |  | 2021-03-12 |  | DELIVERED | DELIVERED (GTGBA20)
349966139 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966157 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966149 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966131 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966880 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966136 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966128 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966146 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966886 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966888 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-12 |  | 2021-03-15 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966894 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966148 | NJ | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966889 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966147 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966133 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20)
349966890 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/26 (GTGBA20)
349966150 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966895 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-15 |  | 2021-03-17 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20)
349966892 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966152 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966896 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966155 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966891 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966151 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966154 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966138 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966134 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/23 (GTGBA20)
349966901 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/23 (GTGBA20)
349966897 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966153 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/23 (GTGBA20)
349966142 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/25 (GTGBA20)
349966893 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 348 | 12 | 2021-03-19 |  | 2021-03-22 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/23 (GTGBA20)
349966898 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966132 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-17 |  | 2021-03-19 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/22 (GTGBA20)
349966899 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/06 (GTGBA20)
349966902 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20)
349966135 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/06 (GTGBA20)
349966900 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/06 (GTGBA20)
349966883 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/06 (GTGBA20)
349966903 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20)
349966140 | TN WH | FTL | CH Robinson | Hanwha | GTG |  | 201 Bay Ave, Elizabeth, NJ 07201 | NextEra Swap to NJ | Q.PEAK DUO L-G7.2 400 | 12002679R | 20 | 754 | 26 | 2021-03-24 |  | 2021-03-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 03/30 (GTGBA20)
CA9800032610T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | NA |  | 2021-04-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/28 (PIONEERNB18)
CA9800032610T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 58 | 2 | NA |  | 2021-04-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/28 (PIONEERNB18)
CA9800032614T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 638 | 22 | NA |  | 2021-04-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/23 (PIONEERNB18)
CA9800032616T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 232 | 8 | NA |  | 2021-04-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/23 (PIONEERNB18)
CA9800032616T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 406 | 14 | NA |  | 2021-04-21 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/23 (PIONEERNB18)
CA9800032619T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 638 | 22 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
CA9800032624T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 348 | 12 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/27 (PIONEERNB18)
CA9800032624T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 290 | 10 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/27 (PIONEERNB18)
CA9800032627T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 58 | 2 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
CA9800032627T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
CA9800032629T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 638 | 22 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
CA9800032632T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 290 | 10 | NA |  | 2021-04-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/27 (PIONEERNB18)
CA9800032632T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 348 | 12 | NA |  | 2021-04-26 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/27 (PIONEERNB18)
CA9800032639T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 580 | 20 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
CA9800032639T1 | CA WH | FTL | TQL | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | Reroute from CA/NY to NJ warehouse for PO# 20098000 (PT2 Branscomb) | Q.PEAK DUO XL-G9P.3/BFG 455 | 30396067F | 18 | 58 | 2 | NA |  | 2021-04-23 |  | DELIVERED | DELIVERED CLOSED IN CELLO 04/26 (PIONEERNB18)
VA0134082210RDAMAGE | VA WH | LTL | XPO | Hanwha | PSS |  | 11C Nicholas Ct. Dayton, NJ 08810 | Damage Pallets from PNCW | Q.PEAK DUO L-G5.2 400 | 12002650R | 20 | 58 | 2 | 2021-04-29 |  | 2021-05-07 |  | DELIVERED | DELIVERED CLOSED IN CELLO 05/11 (Cell# DAMAGE-PSS) 2 Damaged pallets transfer from PNCW (VA) WH to PSS (NJ) WH for inspection
357120511 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-19 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0)
357120541 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-19 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0)
357120547 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-19 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0)
357120509 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-20 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0); AIR BAG TEST LOAD
357120507 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-19 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0); AIR BAG TEST LOAD
357120513 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-20 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0); AIR BAG TEST LOAD
357120508 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-19 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0); AIR BAG TEST LOAD
357120546 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 | 2021-05-18 |  | 2021-05-20 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0); AIR BAG TEST LOAD
357120510 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-21 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120545 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-21 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120552 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-24 |  | DELIVERED | CLOSED IN CELLO 05/26 (PIONEERNBNEW0)
357120550 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-20 |  | DELIVERED | CLOSED IN CELLO 05/24 (PIONEERNBNEW0)
357120566 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-21 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120577 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-21 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120581 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-27 |  | DELIVERED | CLOSED IN CELLO 05/28 (PIONEERNBNEW0)
357120591 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-24 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120555 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 896 | 28 |  |  | 2021-05-24 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
357120589 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (350W) | Q.PEAK DUO G6P+ 350 | 46205130 | 0 | 768 | 24 |  |  | 2021-05-24 |  | DELIVERED | CLOSED IN CELLO 05/25 (PIONEERNBNEW0)
360353653 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-18 |  | 2021-06-21 |  | DELIVERED | CLOSED IN CELLO 06/23 (PIONEERNBNEW0)
360353652 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-18 |  | 2021-06-21 |  | DELIVERED | CLOSED IN CELLO 06/23 (PIONEERNBNEW0)
360353659 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-18 |  | 2021-06-21 |  | DELIVERED | CLOSED IN CELLO 06/23 (PIONEERNBNEW0)
360353660 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-22 |  | DELIVERED | CLOSED IN CELLO 06/23 (PIONEERNBNEW0) DELIVERED; AIR BAG TEST LOAD
360353658 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0) DELIVERED; AIR BAG TEST LOAD
360353655 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0) DELIVERED; AIR BAG TEST LOAD
360353665 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0) DELIVERED; AIR BAG TEST LOAD
360354469 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0) DELIVERED; AIR BAG TEST LOAD
360353657 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0)
360353666 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0)
360353661 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0)
360353654 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-22 |  | DELIVERED | CLOSED IN CELLO 06/23 (PIONEERNBNEW0)
360353656 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0)
360353663 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 | 2021-06-21 |  | 2021-06-23 |  | DELIVERED | CLOSED IN CELLO 06/24 (PIONEERNBNEW0)
361794379 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794461 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794576 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-07 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794664 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839656 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839669 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839674 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839702 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839714 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-09 |  | DELIVERED | CLOSED IN CELLO 07/12 (PIONEERNBNEW0)
361839718 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839707 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839711 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794480 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794498 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361794670 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-06 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
361839653 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839691 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839709 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839703 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839712 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839716 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839705 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-08 |  | DELIVERED | CLOSED IN CELLO 07/09 (PIONEERNBNEW0)
361839715 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Stock Transfer (350W NJWH) | Q.PEAK DUO G6P+ 350W | 46205130 | 0 | 896 | 28 |  |  | 2021-07-07 |  | DELIVERED | CLOSED IN CELLO 07/08 (PIONEERNBNEW0)
CA2326052362T | CA WH | FTL | LSGL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | 4250-CF902324S PT2 | Q.PEAK DUO BLK ML-G9P+380 | 30368517F | 18 | 768 | 24 | 2021-06-18 |  | 2021-07-09 |  | DELIVERED | CLOSED IN CELLO 07/12 (PIONEERNBNEW18)
FL2045062258T | FL WH | FT |  | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | 20-456 R2 (Anderson 3) | Q.PEAK DUO L-G8P.2 425 | 12004246F | 18 | 660 | 22 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/30 (DAMAGE-PIONEERNEW18); DELIVERED PENDING FTD; damage photos are for this or FL2045062258T confirmed by Nathaly; CA shipment Rejected by customer and Reroute to PIONEER-1665 for Inspection
363463039 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463042 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463037 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463038 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463044 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463036 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463048 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463035 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463045 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-22 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463058 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464673 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464676 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464678 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464677 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464671 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464680 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464675 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-23 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW0)
363464672 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464681 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464674 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464682 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464679 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464688 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464689 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464690 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363464687 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-26 |  | DELIVERED | CLOSED IN CELLO 07/27 (PIONEERNBNEW0)
363463049 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-27 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW0)
363463040 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW0)
363463052 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-27 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW0)
363463054 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW0)
363463051 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW0)
363463043 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW0)
363463041 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW0)
363463057 | GA WH | FTL | CH ROBINSON | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | WH Transfer (430W SDS NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-07-27 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW0)
VATRAN072601R | VA WH | FTL | PNCW | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renewables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12004284R | 20 | 145 | 5 |  |  | 2021-07-27 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW20)
FL2021072207T | FL WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 | 2021-07-23 |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW18) PER WAREHOUSE NO DAMAGES FOUND FOR THIS TRANSFER
CA2021072203T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12004928F | 18 | 232 | 8 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW18)
CA2021072203T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 348 | 12 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW18)
CA2021072204T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 696 | 24 |  |  | 2021-07-27 |  | DELIVERED | CLOSED IN CELLO 07/28 (PIONEERNBNEW18)
CA2021072205T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 696 | 24 |  |  | 2021-07-28 |  | DELIVERED | CLOSED IN CELLO 07/29 (PIONEERNBNEW18)
CA2021072206T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 638 | 22 |  |  | 2021-07-30 |  | DELIVERED | CLOSED IN CELLO 08/02 (PIONEERNBNEW18) 7/30-rcvd 4 damaged cartons, exterior damage only
CA2021072207T | CA WH | FTL | TQL | Hanwha | Pioneer |  | 2300 Route 1 North Building 101 North Brunswick, NJ 08902 | Empire Renwables Stock Transfer | Q.PEAK DUO L-G7.2 400 | 12002679F | 18 | 618 | 26 |  |  | 2021-07-30 |  | DELIVERED | CLOSED IN CELLO 08/02 (PIONEERNBNEW18); Total 22 actual pallets with 26 pallet IDs
365143845 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143848 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143849 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143851 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143852 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143853 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143855 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365211501 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/11 (PIONEERNB)
365211502 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/11 (PIONEERNB)
365211503 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
365211504 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L G6P.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
365211505 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
365211506 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
365211507 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
365211508 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-10 |  | DELIVERED | CLOSED IN CELLO 08/11 (PIONEERNB)
365211510 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46108146 | 0 | 696 | 24 |  |  | 2021-08-12 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNB)
365143844 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46104146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143847 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-09 |  | DELIVERED | CLOSED IN CELLO 08/10 (PIONEERNB)
365143854 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46106146 | 0 | 696 | 24 | 2021-08-06 |  | 2021-08-13 |  | DELIVERED | CLOSED IN CELLO 08/16 (PIONEERNB)
365143850 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | WH Transfer (430W NJWH) | Q.PEAK DUO L-G6C.2 430 | 46106146 | 0 | 696 | 24 |  |  | 2021-08-11 |  | DELIVERED | CLOSED IN CELLO 08/13 (PIONEERNB)
368597469 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | SP-20217019 | Q.PEAK DUO BLK-G6P+/HL 340 | 46220128 | 0 | 104 | 4 | 2021-09-10 |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/17 (PIONEERNB) Amicus Solar Cooperative 803 Kings Factory Rd, Charlestown, RI 02813 wrong plt were delivered to Amicus, transfer to Pioneer WH 1665 Jersey ave.
368597469 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | SP-20217020 | Q.PEAK DUO BLK-G6P+/HL 340 | 46220128 | 0 | 104 | 4 | 2021-09-10 |  | 2021-09-15 |  | DELIVERED | CLOSED IN CELLO 09/17 (PIONEERNB) Amicus Solar Cooperative 803 Kings Factory Rd, Charlestown, RI 02813 wrong plt were delivered to Amicus, transfer to Pioneer WH 1665 Jersey ave.
369273706 | GA WH | FTL | CHR | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 4250-CF902607S | Q.PEAK DUO BLK-G6P+/HL 340 | 46220128 | 0 | 624 | 24 |  |  | 2021-09-22 |  | DELIVERED | CLOSED IN CELLO 09/24 (PIONEERNB)
370263223 | GA WH | FTL | FEDEX | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 4250-CF902607S | PL.H_MO.US_1730_1050_143_2X6_120M2 | Wooden Pallet |  | 5 | 1 |  |  | 2021-10-04 |  | DELIVERED | 5 stacks of wooden pallets
370263223 | GA WH | FTL | FEDEX | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 4250-CF902607S | CO.BX_TP.US_1707_1098_1010_120M2 | Boxes |  | 5 | 1 |  |  | 2021-10-04 |  | DELIVERED | The box is bigger than the pallet itself
370263223 | GA WH | FTL | FEDEX | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 4250-CF902607S | CO.LD_OJ.KR_1742_1124_100_BA_120M2 | Lids |  | 5 | 1 |  |  | 2021-10-04 |  | DELIVERED | The Pallet is longer than the Lid
370263223 | GA WH | FTL | FEDEX | Hanwha | Pioneer |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 4250-CF902607S | CO.BL_OJ.KR_1700_1195_8.0_AB120M2 | Blank |  | 5 | 1 |  |  | 2021-10-04 |  | DELIVERED | The pallet is longer than the Blank
NJO002102824FRETURN | Candor, NY | FTL | NOLAN | Hanwha | Empire Valorize LLC |  | 340 South Stiles, Linden, NJ 07036 | 2101PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 522 | 18 | 2021-10-29 |  | 2021-11-01 |  | DELIVERED | CLOSED IN CELLO 11/03 (GTGSS18RETURN)
NJO002102825FRETURN | Candor, NY | FTL | NOLAN | Hanwha | Empire Valorize LLC |  | 340 South Stiles, Linden, NJ 07036 | 2101PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 522 | 18 | 2021-10-29 |  | 2021-11-01 |  | DELIVERED | CLOSED IN CELLO 11/03 (GTGSS18RETURN)
NJO002102825F1RETUR | Candor, NY | FTL | NOLAN | Hanwha | Empire Valorize LLC |  | 340 South Stiles, Linden, NJ 07036 | 2101PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 4 | 1 | 2021-10-29 |  | 2021-11-01 |  | DELIVERED | CLOSED IN CELLO 11/03 (GTGSS18RETURN)
NJO002102101FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-02 |  | 2021-11-03 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102102FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-02 |  | 2021-11-03 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102103FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-02 |  | 2021-11-03 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102505FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-03 |  | 2021-11-04 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102506FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-03 |  | 2021-11-04 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102507FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 551 | 19 | 2021-11-03 |  | 2021-11-04 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102507FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 58 | 2 | 2021-11-03 |  | 2021-11-04 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102508FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-04 |  | 2021-11-05 |  | DELIVERED | CLOSED IN CELLO 12/05 (PIONEERNB18RETURN), wet muddy condition
NJO002102818FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-04 |  | 2021-11-05 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102609FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 116 | 4 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102609FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 435 | 15 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102609FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 480 | 30397472F | 18 | 58 | 2 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102611FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102611FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 25 | 1 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102612FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-08 |  | 2021-11-09 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102713FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 551 | 19 | 2021-11-09 |  | 2021-11-10 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102713FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 58 | 2 | 2021-11-09 |  | 2021-11-10 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition | 210716_J3_GXLC10_475A_723 - damaged
NJO002102714FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-09 |  | 2021-11-10 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102725FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 609 | 21 | 2021-11-09 |  | 2021-11-10 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102816FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 261 | 9 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102816FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 348 | 12 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102817FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 580 | 20 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102817FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 29 | 1 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102610FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397471F | 18 | 87 | 3 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102610FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10BC.C 475 | 30397371F | 18 | 522 | 18 | 2021-11-11 |  | 2021-11-12 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102104FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397471F | 18 | 29 | 1 | 2021-11-15 |  | 2021-11-16 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102104FRETURN | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 522 | 18 | 2021-11-15 |  | 2021-11-16 |  | DELIVERED | CLOSED IN CELLO 12/05, (PIONEERNB18RETURN), wet muddy condition
NJO002102104F4F1RET | Owego, NY | FTL | NXL | Hanwha | Empire Valorize LLC |  | 1665 Jersey Avenue North Brunswick, NJ 08902 | 2102PO002 | Q.PEAK DUO XL-G10B.C 475 | 30397371F | 18 | 609 | 21 | 2021-11-15 |  | 2021-11-16 |  | DELIVERED | CLOSED IN CELLO 12/21, (PIONEERNB18RETURN), wet muddy condition | NJO002102104F-4F1RETURN (too long cello can't take, revised bl#)
NJLINT101510FRETURN | Linton, IN | FTL | NXL |  | Indiana Municipal Power Agency (Linton) |  | 1665 Jersey Ave, North Brunswick, NJ 08902 | 20-456 R3 (Linton) | Q.PEAK DUO L-G8.2 430 | 12005803F | 18 | 750 | 25 |  |  | 2021-11-10 |  | DELIVERED | 11/8/21-IMPA found damage, reject & returned closed in cello 11/12 (PIONEERNB18RETURN)
CA2021111711T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-29 | 9:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111712T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-29 | 9:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111713T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-29 | 10:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111714T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-26 | 11:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111715T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-29 | 8:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111716T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-18 |  | 2021-11-29 | 9:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111717T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-22 |  | 2021-11-30 | 10:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks), PIONEERNBNEW18
CA2021111718T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-19 |  | 2021-11-29 | 11:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111719T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-19 |  | 2021-11-29 | 8:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111720T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-19 |  | 2021-11-29 | 9:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111721T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-19 |  | 2021-11-29 | 10:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111722T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 580 | 20 | 2021-11-19 |  | 2021-11-29 | 11:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111723T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 522 | 18 | 2021-11-23 |  | 2021-11-30 | 8:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111724T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 522 | 18 | 2021-11-23 |  | 2021-11-26 | 9:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111725T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 522 | 18 | 2021-11-23 |  | 2021-11-26 | 10:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
CA2021111726T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 319 | 11 | 2021-11-23 |  | 2021-11-30 | 11:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks) | JSHWJ2108608/ONEYSELB99358400
CA2021111726T | Gardena | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 203 | 7 | 2021-11-23 |  | 2021-11-30 | 11:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks) | JSHWJ2109601/ONEYSELB92841801
CA2021111727T | Ontario | FT |  | KB | SDS/Pioneer | DDP | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | WH Transfer (Dunkleman) | Q.PEAK DUO XL G10C.D/BFG 475 | 30397871F | 18 | 261 | 9 | 2021-11-23 |  | 2021-11-26 | 12:00 | DELIVERED | CAWH --> NJWH Transfer (17 DDP Trucks)
NJ2485122301F | Fredericksburg, PA | FTL | TQL |  | AEE Solar |  | 201 Bay Ave. Elizabeth, NJ 07201 | 112485 | Q.PEAK DUO BLK G6C+ 340 | 30376609F | 18 | 832 | 26 | 2021-12-23 |  | 2021-12-27 |  | DELIVERED | AEE / SUNRUN closed 12/24-12/27, returned to the shipper
NJ2485122302F | Fredericksburg, PA | FTL | TQL |  | AEE Solar |  | 201 Bay Ave. Elizabeth, NJ 07201 | 112485 | Q.PEAK DUO BLK G6C+ 340 | 30376609F | 18 | 832 | 26 | 2021-12-23 |  | 2021-12-27 |  | DELIVERED | AEE / SUNRUN closed 12/24-12/27, returned to the shipper
NJ2485122303F | Fredericksburg, PA | FTL | TQL |  | AEE Solar |  | 201 Bay Ave. Elizabeth, NJ 07201 | 112485 | Q.PEAK DUO BLK G6C+ 340 | 30376609F | 18 | 832 | 26 | 2021-12-23 |  | 2021-12-27 |  | DELIVERED | AEE / SUNRUN closed 12/24-12/27, returned to the shipper
NJ5908120709F2RET | 1230 Bryant Rd, Spartanburg, SC, 29303 | LTL | TQL |  | Radiance Solar, LLC |  | 1665 Jersey Ave, North Brunswick, NJ 08902 | 5908 | Q.PEAK DUO XL G10C.D/BFG 480 | 30397872F | 18 | 58 | 2 | 2022-01-14 |  | 2022-01-20 | 1300 | DELIVERED | CLOSED IN CELLO 1/31/22, put the 2 pallets ON HOLD in Cello; 1/4-per Kristine, QCells wants to close original CR invoice for December and awaiting customer's conf & issue a new CR 3PLT, customer will adivse 2 return plt ids & we need to setup return inbound // 210810_J3_GXLN1D_480A_714, 210809_J3_GXLN1D_480A_703 (PIONEERNB18), 1/19-weather condition, delay in transit
4R56247RET | 5160 CR 664, Bowling Green, Florida 33834 | FTL | JBH |  | Duke Energy - Fort Green |  | 201 Bay Ave., Elizabeth, NJ | (9236413) Fort Green | Q.PEAK DUO XL-G10.3/BFG 480 | 30397572C | 15 | 638 | 22 | 2022-01-11 |  | 2022-01-14 |  | DELIVERED | CLOSED IN CELLO 1/31/22, put the 2 pallets ON HOLD in Cello; 1/11-per David. this load will be returned to NJ for inspection. Once you receive it, please inspect and send us damage report with qty and details (GTGBA15)
4R55408RET | 5160 CR 664, Bowling Green, Florida 33834 | FTL | JBH |  | Duke Energy - Fort Green |  | 5250 Old Louisville Road, Building #33 & 34, Pooler, GA 31322 | (9236413) Fort Green | Q.PEAK DUO XL-G10.3/BFG 480 | 30397572F | 18 | 638 | 22 | 2022-01-05 |  | 2022-01-06 |  | DELIVERED | 1/5 - Moss/Duke are rejecting drivers today. ; Received back into inventory manually in Cello
GA2102022220C | 10 Christina court, Sparrows Point, MD 21219 | FTL | NOLAN |  | Summit Ridge Energy / Diggig and Rigging |  | 201 Bay Ave. Elizabeth, NJ 07201 | HNW2021-02 Sub PO #1 (Sparrows Point) | Q.PEAK DUO XL-G10C.3.1/BFG 475 | 30390371C | 15 | 638 | 22 | 2022-02-28 |  | 2022-03-01 |  | DELIVERED | CLOSED IN CELLO 3/16 GTGBA15
382604297 | EXTERNAL WAREHOUSE | FTL | CHR |  | Amicus Solar Cooperative |  | 2300 RT1, Suite# 101, North Brunswick, NJ 08902 | IP-00001135 | Q.PEAK DUO BLK ML-G10.A+ 400 | 49401140 | 0 | 768 | 24 | 2022-02-25 |  | 2022-03-03 | 1200 | DELIVERED | CLOSED IN CELLO 03/07 PIONEERNBNEW0; This load needs to be re-routed back to NJ warehouse as the customer cannot take it, re-routing to Pioneer warehouse.